## Dashboard
UAE AUTHORITY HANDOVER — NOC & COMPLETION CERTIFICATE DASHBOARD
Editable project control: track only items confirmed by the project authority register, permit conditions, development zone and specialist authority. “Confirm” is a decision gate, not an approval status.
PROJECT |  |  | TOTAL MILESTONES | SCRIPT BASELINE REQUIRED | AUTHORITY-SPECIFIC TO CONFIRM
CLIENT
LOCATION / EMIRATE
AUTHORITY ROUTE
TARGET HANDOVER |  |  | VERIFIED | OPEN HOLD / EXPIRED | OVERALL READINESS
RAG STATUS — REQUIRED / CONFIRM ITEMS | WORKSTREAM | MILESTONES
Green | Asset Record
Amber | Authority Route
Red | Civil Defence
Grey | Client Handover
Client Readiness
Closeout
Commissioning
| Development Zone |  | USE RULES — DO NOT ISSUE HANDOVER GREEN STATUS UNTIL THE PROJECT AUTHORITY MATRIX IS CONFIRMED
| Environmental |  | 1. Confirm every “Confirm” row against the live building permit, completion route, Civil Defence authority, utility requirements, master developer / free-zone rules and client contract.
| Life Safety |  | 2. Enter evidence references, submission/issue dates, certificate expiry or recurring inspection dates, owners and gaps in the Handover Register.
| Municipal Completion |  | 3. “Verified” is a project evidence status, not a replacement for an issued authority certificate. Attach or reference the actual certificate/NOC.
| Municipal Occupancy |  | 4. A Red row blocks the associated handover gate. Do not override it through a dashboard note; close it through verified evidence or an approved authority concession.
Post Handover
Residual Risk
Specialist Safety
Structural
Utilities
Open Project Inputs
Open Handover Register
Open Print Checklist
Open Sources & Instructions

## Project Inputs
PROJECT HANDOVER CONTROL — PROJECT INPUTS
Project name
Client / Asset owner
Project location / emirate
Municipality / building-control authority
Development zone / master developer
Building permit / reference
Target handover date
Project manager
HSE manager
Authority / NOC coordinator
Current handover gate | AMBER — confirm authority route and evidence status
Use this sheet first. The project identifiers above are automatically shown on the printable inspection checklist. Confirm all “Confirm” entries in the Handover Register against the authority matrix, live permit conditions and development-zone rules before treating them as mandatory.

## Handover Register
ID | Authority Stream | Milestone / Certificate | Applicable? Yes / Confirm / No | Evidence to Inspect | Issuer / Verifying Party | Authority Route / Trigger | Script / Source Basis | Planned Due Date | Submitted Date | Status | RAG | Owner | Evidence Link / Reference | Authority / Permit Reference | Notes / Gaps
H-01 | Authority Route | Handover authority matrix and permit-condition register confirmed | Yes | Live authority register listing completion, occupancy, fire/life-safety, utilities, development-zone and specialist conditions; owner and due date for each. | Project manager / authority coordinator | Always confirm against active permit, planning conditions and development zone. | Training script §§13, 93, 111 |  |  | Pending Confirmation
H-02 | Municipal Completion | Municipal building completion-certificate route confirmed | Confirm | Applicable municipality service, submission route, prerequisites, inspection booking, reference number and completion-certificate evidence. | Municipality / building-control authority | Dubai Municipality or relevant development authority as applicable. | Training script §93; DM Building Permit Steps [4] |  |  | Pending Confirmation
H-03 | Municipal Occupancy | Occupancy / conditional occupancy / legalisation route confirmed | Confirm | Applicable occupancy or legalisation certificate requirement, records of submission and issued certificate where required for the project. | DMT / relevant municipality | Abu Dhabi DMT programme is location- and asset-specific. | Training script §93; DMT programme [3] |  |  | Pending Confirmation
H-04 | Development Zone | Master developer / free-zone completion, NOC or handover condition closed | Confirm | NOC, completion notice, inspection acceptance or no-objection documentation required by the development zone / master developer. | Development zone / master developer | Only where the site is within a governed zone or lease requires it. | Training script §§13, 93 |  |  | Pending Confirmation
H-05 | Civil Defence | Applicable Civil Defence final-inspection pathway and submission pack confirmed | Confirm | Civil Defence inspection route, approved drawings, system records and documentary prerequisites confirmed in writing. | Relevant Civil Defence authority | Do not assume a Dubai process applies in Abu Dhabi or another emirate. | Training script §§93, 95 |  |  | Pending Confirmation
H-06 | Civil Defence | Fire and life-safety approval, final inspection and completion evidence obtained | Confirm | Issued approval / final inspection result / completion certificate or equivalent authority evidence, as required by the project route. | Relevant Civil Defence authority | Applicable fire authority and certificate title must be verified against the project route. | Training script §§93, 95; Build in Dubai Service 189 [5] |  |  | Pending Confirmation
H-07 | Life Safety | Fire alarm, fire suppression, hydrant/fire-water and emergency systems testing/commissioning evidence complete | Confirm | System test sheets, commissioning reports, cause-and-effect / functional test records, approved variations and specialist certificates. | Specialist contractor / consultant / Civil Defence as applicable | Specific system evidence is controlled by approved design, authority and project specifications. | Training script §§95, 99 |  |  | Pending Confirmation
H-08 | Life Safety | Emergency lighting, exit signage, evacuation routes and emergency access verified | Yes | Final walkdown and test evidence confirming that physical routes, signage, emergency access and life-safety systems match the as-built asset. | Consultant / HSE / client FM representative | Maintain evidence whether or not a separate authority certificate is issued. | Training script §§95, 99, 101 |  |  | Pending Confirmation
H-09 | Utilities | Electricity / permanent energisation final clearance or connection documentation complete | Confirm | Issued utility NOC, connection / energisation evidence, meter/asset handover documents and final test records where applicable. | Electricity utility / authorised service provider | Authority and utility differ by location and development zone. | Training script §95 |  |  | Pending Confirmation
H-10 | Utilities | Water, sewerage, drainage and dewatering-discharge closeout evidence complete | Confirm | Final connection / discharge / drainage NOC, acceptance or documented closure; temporary systems isolated or transferred. | Utility / receiving-asset owner / municipality | Confirm discharge and temporary-system responsibilities before dismantling. | Training script §§81, 95, 97 |  |  | Pending Confirmation
H-11 | Specialist Safety | Gas installation safety evidence complete | Confirm | Approved gas installation documents, inspection / testing evidence and certificate as required. | Competent specialist / authority as applicable | DMT occupancy programme identifies gas safety as an essential standard. | Training script §93; DMT programme [3] |  |  | Pending Confirmation
H-12 | Specialist Safety | Lift / elevator safety acceptance and handover records complete | Confirm | Testing, inspection, certification, handover and periodic-maintenance records for installed lifts/elevators. | Competent specialist / relevant authority | DMT occupancy programme identifies elevator safety as an essential standard. | Training script §93; DMT programme [3] |  |  | Pending Confirmation
H-13 | Structural | Structural integrity evidence and consultant completion sign-off complete | Confirm | Structural completion documentation, approved changes, inspection records, load-path / temporary-works release evidence and consultant sign-off where required. | Structural engineer / consultant / third party as applicable | Scope and sign-off route are permit- and design-specific. | Training script §§93, 95 |  |  | Pending Confirmation
H-14 | Commissioning | Third-party test, inspection and commissioning certificates collated | Yes | Register of specialist certificates and inspection records with issuer, scope, date, expiry and evidence link. | Approved third-party / consultant | Use the authority matrix to define mandatory providers and certificate types. | Training script §§95, 97 |  |  | Pending Confirmation
H-15 | Asset Record | As-built drawings, approved changes and design deviations reconciled | Yes | Controlled as-built drawing register; approved variations; discipline sign-off that documents reflect the completed asset. | Consultant / design team / client | As-builts must describe the installed asset, not tender intent. | Training script §95 |  |  | Pending Confirmation
H-16 | Asset Record | O&M manuals, manufacturer warranties and periodic-inspection requirements transferred | Yes | Indexed O&M manual, warranty record, supplier contacts, maintenance requirements and periodic inspections schedule. | Contractor / suppliers / client FM | Include all specialist installations and life-safety systems. | Training script §§95, 99 |  |  | Pending Confirmation
H-17 | Client Readiness | Client facilities-team training and familiarisation completed | Yes | Attendance records, operating demonstrations, plant-room access, isolation points, emergency routes and escalation/contact briefings. | Client FM / contractor / specialists | Training should include operating constraints and warranty response process. | Training script §99 |  |  | Pending Confirmation
H-18 | Residual Risk | Residual-risk, restricted-access and maintenance-hazard register accepted | Yes | Residual-risk register showing confined spaces, load limits, restricted areas, maintenance hazards and operating constraints; formal client acknowledgement. | Client / consultant / contractor | Do not remove residual risks from the record merely to achieve a clean dashboard. | Training script §§97, 103 |  |  | Pending Confirmation
H-19 | Closeout | Permits closed or formally transferred; temporary services isolated / transferred | Yes | Permit closeout register; LOTO/isolation records; temporary-power, pump, generator, hoist or system transfer / removal evidence. | Permit issuer / isolating authority / client | Critical safety systems remain active until verified permanent systems take over. | Training script §§77, 85, 97 |  |  | Pending Confirmation
H-20 | Environmental | Waste, hazardous materials and environmental closeout evidence completed | Confirm | Waste-transfer records, authorised disposal evidence, hazardous-material closeout, dewatering/discharge records as relevant. | Authorised contractor / authority / asset owner | Documentation and disposal route vary by emirate and waste stream. | Training script §§81, 97 |  |  | Pending Confirmation
H-21 | Client Handover | Joint walkdown completed and discrepancies entered in controlled closeout register | Yes | Signed walkdown record with client, consultant, contractor and specialists; itemised action register with owner and date. | Client / consultant / contractor | Physical tags, signage, access, manuals, drawings and records should agree. | Training script §101 |  |  | Pending Confirmation
H-22 | Client Handover | Outstanding-defect register controlled and client acceptance recorded | Yes | Defect / punch-list register with risk ranking, owner, due date, client acceptance of residual conditions and formal handover record. | Client / consultant / contractor | Avoid untracked closeout through email chains. | Training script §§101, 103 |  |  | Pending Confirmation
H-23 | Post Handover | Post-completion authority and periodic-inspection obligations assigned | Confirm | Register of certificate renewals, periodic inspections, maintenance contracts, statutory notifications and client ownership. | Client FM / asset owner | Occupancy and specialist systems may have recurring obligations. | Training script §§99, 111 |  |  | Pending Confirmation

## Print Checklist
UAE AUTHORITY HANDOVER — PRINTABLE INSPECTION CHECKLIST
Extracted from the “Site Mobilisation, Demobilisation & Client Handover — UAE Authority Readiness” script. Confirm every Conditional (“Confirm”) milestone against the project authority matrix, live permit conditions and development-zone rules before use.
Project |  | Client |  | Location / Emirate
Authority |  | Permit Ref. |  | Target Handover
ID | Inspection milestone | Evidence to inspect | Applicability / authority trigger | Inspector status | Evidence reference | Initials / date
A. Authority Route & Municipal Completion
☐ Verified ☐ Pending ☐ Hold ☐ N/A
☐ Verified ☐ Pending ☐ Hold ☐ N/A
☐ Verified ☐ Pending ☐ Hold ☐ N/A
☐ Verified ☐ Pending ☐ Hold ☐ N/A
B. Civil Defence & Life-Safety Completion
☐ Verified ☐ Pending ☐ Hold ☐ N/A
☐ Verified ☐ Pending ☐ Hold ☐ N/A
☐ Verified ☐ Pending ☐ Hold ☐ N/A
☐ Verified ☐ Pending ☐ Hold ☐ N/A
C. Utilities, Specialist & Third-Party Evidence
☐ Verified ☐ Pending ☐ Hold ☐ N/A
☐ Verified ☐ Pending ☐ Hold ☐ N/A
☐ Verified ☐ Pending ☐ Hold ☐ N/A
☐ Verified ☐ Pending ☐ Hold ☐ N/A
☐ Verified ☐ Pending ☐ Hold ☐ N/A
☐ Verified ☐ Pending ☐ Hold ☐ N/A
D. Asset, Environmental & Client Handover
☐ Verified ☐ Pending ☐ Hold ☐ N/A
☐ Verified ☐ Pending ☐ Hold ☐ N/A
☐ Verified ☐ Pending ☐ Hold ☐ N/A
☐ Verified ☐ Pending ☐ Hold ☐ N/A
☐ Verified ☐ Pending ☐ Hold ☐ N/A
☐ Verified ☐ Pending ☐ Hold ☐ N/A
☐ Verified ☐ Pending ☐ Hold ☐ N/A
☐ Verified ☐ Pending ☐ Hold ☐ N/A
☐ Verified ☐ Pending ☐ Hold ☐ N/A

## Sources & Instructions
SOURCES, SCOPE AND IMPLEMENTATION NOTES
This workbook is a script-derived project-control template, not a universal statutory schedule for every UAE authority. The video explicitly requires each project to verify its location-specific authority route. “Confirm” rows become mandatory only when required by the project authority register, building permit, development-zone rules, specialist authority, utility, or contract. Do not submit, declare, or rely on this template in place of an actual authority certificate, NOC, inspection outcome, or professional advice.
Ref | Official / Source Document | URL | Use in this Pack
[1] | MOHRE Occupational Health and Safety Guidance | https://mohre.gov.ae/en/guidance-and-awareness-portal-new/occupational-health-and-safety | Federal OSH evidence lifecycle; records, inspection and contractor controls.
[2] | MOHRE Administrative Decision No. 19 of 2023 | https://mohre.gov.ae/assets/download/6786916a/administrative-decision-no-19-of-2023-relating-to-occupational-safety-and-health-and-labour.aspx | OSH programme, emergency, training, equipment inspection and continual-improvement baseline.
[3] | Abu Dhabi DMT Building Occupancy and Legalisation Certificate Programme | https://www.mediaoffice.abudhabi/en/infrastructure/department-of-municipalities-and-transport-launches-building-occupancy-and-legalisation-certificate-programme/ | Abu Dhabi occupancy/legalisation track and cited essential standards.
[4] | Dubai Municipality Building Permit Steps | https://www.dm.gov.ae/municipality-business/building-permit-steps/ | Dubai building-control pathway; verify the current project completion route.
[5] | Build in Dubai — Issue Building Completion Certificate, Service 189 | https://buildindubai.gov.ae/service/189 | Official service result identifies building completion certificate and Civil Defence completion certificate; verify live service prerequisites.
[6] | Abu Dhabi DMT Guidelines for Developing HSE Plan for Building and Construction Sector | https://www.dmt.gov.ae/adm/-/media/Project/DMT/ADM/E-Library/Guidlines-for-developing-EHS-plan---English.pdf | HSE evidence and construction closeout governance.
[7] | Site Safety UAE training video narration script | Internal project file: video_narration_segments.md | Source of the extracted milestones and handover gates.
Decision hierarchy
1. Active authority / municipal / Civil Defence condition or issued permit.
2. Development-zone, master-developer, utility or asset-owner requirements.
3. Approved drawings, technical specifications, consultant instructions and client contract.
4. This training-script extraction and workbook dashboard as the management control layer.

## Lists (hidden)
Pending Confirmation | Yes | Green
Not Started | Confirm | Amber
In Preparation | No | Red
Submitted |  | Grey
In Review
Verified
Expired / Superseded
On Hold
Not Applicable