## 0. Dashboard
SOR and NCR Control Workbook - Project Dashboard
Enter project data once. The registers, KPI sheet and print-ready forms load this information automatically.
Project name | [Insert project name]
Project / contract number | [Insert number]
Project location and emirate | [e.g. Dubai - Business Bay]
Regulatory route | [Dubai Municipality / DDA / Trakhees / free zone / Abu Dhabi DMT / other - state which]
Employer / client | [Insert client]
Employer's Representative | [Name and position]
Main contractor | [Insert contractor]
Contractor QA/QC manager | [Name]
PMC / consultant | [Insert PMC]
PMC Project Director | [Name]
PMC Resident Engineer | [Name]
PMC Quality Manager | [Name]
Contract form and edition | [e.g. FIDIC Red Book 2017 with Particular Conditions]
Contract defects liability period | [e.g. 12 months from taking-over]
SOR response period (calendar days) | 3
NCR acknowledgement period (hours) | 48
NCR minor response period (calendar days) | 7
NCR major response period (calendar days) | 14
Escalation trigger (days past due) | 7
EDMS platform | [e.g. Aconex / Procore / Viewpoint / Asite / other]
Companion document reference | PMC-QA-ART-001 Rev 01 - SOR and NCR on UAE construction sites
Workbook revision | [Rev 01]
Date of issue | [Insert date]
Sheets in this workbook
1. SOR Register - observations with automatic ageing and overdue flags
2. NCR Register - non-conformances with class, root cause, CAPA, verification and closure
3. Escalation Matrix - decision rules and escalation ladder
4. Root Cause and CAPA - five-why analysis and action tracking
5. Closure Evidence Checklist - what to attach for each category of item
6. Authority Matrix - UAE authority reference, editable
7. Authority Tracker - NOC, inspection, certificate and clearance status
8. KPI Dashboard - assurance metrics with formulas and charts
9. RACI - roles and responsibilities
10. SOR Form - print ready, loads the project header from this dashboard
11. NCR Form - print ready, loads the project header from this dashboard
12. Closure Certificate - print ready closure record
13. Definitions and References - glossary and source list
14. Major NCR Field Aid - one-page close-out aid for major non-conformances
15. Major NCR Checklist - contractor QA verification checklist for major items
16. Closure Audit Tracker - retrospective audit of previously closed NCRs (protocol PMC-QA-AUD-004)
17. Decennial Risk Register - open, unverified and residual-risk items over the ten-year period
18. RCA CAPA Tracker - 5 Whys, SMART corrective actions, preventive actions and effectiveness evidence

## 1. SOR Register
Site Observation Register (SOR)
Grey columns calculate automatically. Do not overwrite formulas. Status and discipline use drop-down lists.
SOR ID | Date raised | Discipline | Package / area | Exact location (level, grid, room) | Observation description | Requirement reference (spec / drawing rev / ITP / code) | Evidence reference (photo / measurement) | Raised by (PMC) | Responsible party | Due date | Status | Closure date | Days open | Overdue flag | Closure evidence reference | Closed / verified by | Converted to NCR? | NCR ID | Remarks
Formulas:
Days open = IF([SOR ID]="","",IF([Closure date]<>"",[Closure date]-[Date raised],TODAY()-[Date raised]))
Overdue flag = IF([SOR ID]="","",IF(AND([Closure date]="",TODAY()>[Due date]),"OVERDUE",IF(AND([Closure date]<>"",[Closure date]>[Due date]),"CLOSED LATE","")))

## 2. NCR Register
Non-Conformance Register (NCR)
Grey columns calculate automatically. One row per non-conformance, from raising to verified closure.
NCR ID | Date raised | Class | Discipline | Package / area | Exact location | NCR subject | Requirement breached (clause / drawing rev / ITP hold point / code) | Evidence of non-compliance | Extent and containment | Consequence assessment | Contract / commercial reference | Date issued | Acknowledged date | Contractor owner | Root cause summary | Corrective action | Preventive action | Agreed completion date | Actual rectification date | Verification method | Verification date | Verified by | Closure certificate reference | Closure date | Days open | Overdue flag | Authority-linked? | Authority / NOC reference | Cost impact (AED) | Programme impact (days) | Status | Repeat of previous NCR? | Remarks | Project phase | Auto risk points | Auto risk flag | Alert reason
NCR-0001 | 2026-08-04 | Major | Structural | Podium | Zone 3, grid F7 | Raft reinforcement cover below specification | Specification section 03 30 00 clause 3.4; approved drawing S-204 rev C; ITP hold point H-04 | Cover meter survey showing 22 mm against a 40 mm minimum | Area bounded and barricaded; pour stopped; affected zone marked on the as-built | Reduced durability and fire cover to the raft until rectified | FIDIC Red Book 2017 clause 7.5 | 2026-08-08 | 2026-08-10 | Contractor QA Manager | Cover spacers displaced during the pour | Rectify the affected zone and re-test | Spacer template control | 2026-09-17 |  | Cover meter survey and core testing | [6 empty] | No |  | 250000 | 21 |  | No | Sample row - delete before use | Phase 2 - Construction and fit-out
NCR-0002 | 2026-09-02 | Systemic | Fire and life safety | Core | Level 5 riser | Fire-stopping system reference not recorded for 14 penetrations | Fire-stopping specification section 07 84 00; approved system submittal; Dubai Civil Defence conditions | Site inspection record and dated photographs | All 14 penetrations listed and marked; compartment left incomplete | Compartmentation integrity unproven until the seals are verified | Authority approval conditions and the contract quality clause | 2026-09-04 | 2026-09-07 | Contractor QA/QC Manager | Material control omitted the fire-stopping system from the approved list | Re-inspect and re-document 100 per cent of the penetrations | Add fire-stopping to the controlled material list | 2026-10-02 |  | Physical inspection and system verification |  |  |  | 2026-10-06 |  |  | Yes |  | 40000 | 7 |  | No | Sample row - delete before use | Phase 3 - Testing and commissioning
NCR-0003 | 2026-09-25 | Minor | Architectural | Retail fit-out | Unit R-12 | Tile lippage beyond tolerance at the shopfront threshold | Finishes specification section 09 30 00 clause 2.3; shopfront drawing A-118 rev B | Straight-edge measurement of 3 mm against a 2 mm tolerance | One threshold only; unit access maintained | Appearance and trip risk at the shopfront entry | FIDIC Red Book 2017 clause 7.5 | 2026-09-26 | 2026-09-27 | Subcontractor foreman | Substrate level not checked before fixing | Replace the affected tiles | Add a pre-fix level check to the ITP | 2026-10-05 |  | Visual and dimensional inspection | [6 empty] | No |  | 5000 | 5 |  | Yes | Sample row - delete before use | Phase 4 - Handover and taking-over
Formulas:
Days open = IF([NCR ID]="","",IF([Closure date]<>"",[Closure date]-[Date raised],TODAY()-[Date raised]))
Overdue flag = IF([NCR ID]="","",IF(AND([Closure date]="",TODAY()>[Agreed completion date]),"OVERDUE",IF(AND([Closure date]<>"",[Closure date]>[Agreed completion date]),"CLOSED LATE","")))
Status = IF([NCR ID]="","",IF([Closure date]<>"","Closed",IF(TODAY()>[Agreed completion date],"Overdue","Open")))

## 3. Escalation Matrix
Escalation Matrix and Decision Rules
Publish this page as the one-page decision aid for engineers and inspectors.
Rung | Instrument | Trigger | Consequence | Who authorises
1 | Verbal comment, corrected immediately | Minor issue noticed on a walk-through | None if corrected before the next inspection | Any inspector
2 | SOR - Site Observation Report | Deviation, shortfall or improvement that is not a confirmed non-compliance | Logged item with due date and photographic closure | Any PMC engineer or inspector
3 | NCR - Minor | Confirmed non-compliance, containable, no safety, structural or statutory effect | Rectification and verified closure certificate | PMC Quality Manager or Resident Engineer
4 | NCR - Major | Safety, structural, statutory, concealed or repeated non-compliance | Containment, hold on scope, root cause and CAPA | PMC Resident Engineer
5 | Contractual instruction / Notice to Correct | Not remedied in time, or systemic quality system failure | Contractual notice, payment hold on the item | PMC Project Director
6 | Deduction or back-charge | Cost incurred by the Employer or a third party | Financial recovery in the payment certificate | Employer on the Engineer's recommendation
7 | Defects liability regime | Unresolved at taking-over, or a post-handover defect | Defects register and retention leverage | Engineer under the contract
Time trigger | Automatic PMC action
SOR not closed by the due date | Notify the contractor's QA/QC manager, list at the daily site meeting, flag in the weekly report
SOR repeated or ignored twice | Convert to an NCR referencing the SOR history
NCR not acknowledged within the dashboard SLA | Written notice to the contractor's project manager; instruction to respond
NCR not remedied by the agreed date | Written instruction to correct; withhold valuation of the affected item
Any item 30 days past due | Escalate to the quarterly quality review with the client and require a recovery plan
Systemic or repeated failure | Notice to Correct and a full audit of the contractor's quality management system

## 4. Root Cause and CAPA
Root Cause and Corrective / Preventive Action Record
Complete one sheet per non-conformance. Use five whys as the minimum analysis for major and systemic items.
NCR ID
Date raised
Class
Discipline
Location
Requirement breached
Description of non-conformance
Five why analysis
Level | Question | Answer and evidence
Immediate cause | What physically failed or deviated?
Why 1 | Why did that happen?
Why 2 | Why did that happen?
Why 3 | Why did that happen?
Why 4 | Why did that happen?
Why 5 | Root cause reaching a controllable system, not human error alone
Contributing factors | Which control allowed it to escape detection?
Action type | Action (specific and measurable) | Owner | Target date | Status | Verification of effectiveness
Containment
Corrective action
Preventive action
Verification
Rule: if a preventive action cannot be seen in a document, checklist, training record or physical control, it is not an action.

## 5. Closure Evidence Checklist
Closure Evidence Checklist by Category
Use to define what the contractor must submit, and what the PMC must hold before closing the item.
Category | Acceptance criterion | Verification method | Minimum evidence to close
Workmanship and finish | Compliant with specification and approved sample | PMC visual inspection and benchmark comparison | Before and after photos with metadata, inspection record, benchmark reference
Structural and geotechnical | Verified against design and code | Re-test, NDT, structural review, witnessed inspection | Third-party test report, designer confirmation, re-inspection record
Fire and life safety | Compliant with the fire code and Civil Defence approval | PMC inspection, system testing, authority inspection | Test certificate, authority record or NOC, approved amended drawings
MEP and commissioning | Installed, tested and commissioned to specification | Witnessed testing, commissioning and balancing | Test and commissioning report, calibration records, as-built markups
Materials and products | Compliant with approved material and conformity requirements | Certificate review, sampling, laboratory testing | Conformity certificate, test report, approved submittal, batch traceability
Statutory and authority findings | Accepted by the authority | Authority re-inspection or desk review | Authority letter, NOC, certificate or approved inspection record
Documentation gaps | Record reconstructed and control gap closed | Review against design and as-built condition | Justification statement, supporting evidence, revised procedure
Interface and access | Resolved and confirmed by the affected party | Joint inspection and written confirmation | Signed joint inspection record, NOC from the affected party
Concealed work not verifiable | Accepted by authority or designer | Opening up, NDT, endoscopy, radiographic or ultrasonic testing | Test results, method approval, designer confirmation, authority acceptance

## 6. Authority Matrix
UAE Authority Matrix - editable reference
Generated from the research behind this article. Add project-specific rows: permit issuer, conditions, hold points and evidence.
Authority | Full name / responsible entity | Jurisdiction or emirate | What it regulates | When it engages the project | Link to SOR / NCR | Evidence that closes the item | Final completion or handover instrument | Applicable to this project? (Yes / No / N-A) | Project permit or NOC number | Project hold points | Owner (PMC / contractor / client) | Status
MoIAT / ESMA legacy function | Ministry of Industry and Advanced Technology; Emirates Authority for Standardization and Metrology legacy function | Federal; regulated products also reach free zones | UAE.S standards, technical regulations, product conformity and product safety | Design, procurement, import, delivery and installation | Missing conformity, wrong model, unapproved substitution, invalid label or untraceable batch is a procurement/installation NCR | UAE Certificate of Conformity (ECAS) where applicable, accredited-laboratory report, declaration of conformity, approved submittal and batch/serial traceability | Product conformity file; **not** a general building completion certificate
General Command of Civil Defence / UAE Fire Code framework | General Command of Civil Defence; implemented through the relevant emirate Civil Defence authority | Federal framework; emirate implementation | UAE Fire and Life Safety Code of Practice: escape, alarm, suppression, passive protection and construction fire safety | Fire design, material approval, installation, testing and completion | Fire-stopping, doors, risers, pumps, hydrants, alarms and access are authority-sensitive hold points | Approved fire drawings, inspection records, commissioning/test certificates and as-built fire plans | Relevant emirate Civil Defence completion, clearance or compliance certificate
MOCCAE | Ministry of Climate Change and Environment | Federal policy; local environmental authorities often issue operating permits | Environmental licensing/EIA, pollution, waste and discharge controls | Feasibility/EIA, construction environmental management and operation | Dust, wastewater, spoil route, waste, contaminated soil, noise and marine-impact breaches remain NCRs until conditions are evidenced | Applicable environmental licence/EIA approval, environmental management plan, manifests, laboratory results, monitoring reports and inspection outcome | Final environmental clearance only where issued by the competent authority; **verify current requirement**
MoHRE | Ministry of Human Resources and Emiratisation | Federal | Labour, workplace OHS, accommodation/welfare and heat-stress controls | Mobilisation, construction, camp operation and incident follow-up | Unsafe lifting, excavation, scaffolds, PPE, welfare, incident and midday-break findings require risk removal, not a toolbox talk alone | Corrective-action inspection record, JSA/risk assessment, training/competency, equipment certificates, incident close-out and welfare evidence | Enforcement/corrective-action record; no general building completion instrument
GCAA | General Civil Aviation Authority | Federal; airport/airspace affected areas | Aerodrome obstacle limitation surfaces, cranes, temporary structures, marking and lighting | Planning near aerodromes, crane/height approval, temporary works and aviation commissioning | Height, crane, lighting, laser, dust and work-method non-compliances are controlled conditions beyond local building approval | Applicable GCAA/air-navigation approval or NOC, approved coordinates/heights, aeronautical survey, obstacle-lighting test and removal record | Aviation release or aerodrome/operator acceptance; not a general building certificate
MoEI | Ministry of Energy and Infrastructure; federal transport/road functions | Federal roads and infrastructure | Federal-road access, crossings, drainage, utilities and reinstatement NOCs | Pre-construction NOC, crossings/access, construction and final inspection | Road crossing, access, protection-zone or reinstatement breach is an NOC-condition NCR | Original NOC, approved traffic/utility drawings, inspection and reinstatement records, as-builts | **Completion of Non-Objection Certificate** where MoEI is the issuer
Ministry of Economy and Tourism | Ministry of Economy and Tourism | Federal | Commercial, supplier, warranty and consumer-protection framework | Supplier appointment, commercial supply and warranty period | Supports supplier identity/warranty evidence; does not technically close an installed-work NCR | Trade licence, contract/invoice, warranty and recall/corrective-action record, with technical conformity evidence from the competent body | Commercial/warranty record; no construction completion certificate
UAE Cabinet / federal legislation | UAE Cabinet and federal legal framework | Federal | Federal laws, executive regulations, fees and technical/product-control decisions | Regulatory mapping, product controls and changes needing legal/technical approval | Each NCR must cite the governing law, Cabinet decision, technical regulation or permit condition; consultant approval cannot override a mandatory rule | Official law/Cabinet reference, authority correspondence, conformity or recall/withdrawal evidence and accepted risk assessment where permitted | No project completion instrument; applies through the competent issuing authority
Dubai Municipality (DM) | Dubai Municipality, Buildings Regulation and Permits Agency | Dubai buildings under DM jurisdiction | Building permits, technical inspections, registration and building completion | Design/permit, construction inspections and occupancy/completion | Approved drawings, Dubai Building Code requirements, inspection hold points and permit conditions define corrective work | DM inspection result, approved inspection request, stamped as-builts and supporting tests | **DM Building Completion Certificate**
DDA | Dubai Development Authority | Dubai Development Authority/TECOM areas | Planning, construction permits, inspections, building completion and tenant fit-out | Permit, structural/final inspection, fit-out and handover | Major comments must be closed; approved drawings, survey and structural completion are release criteria | DDA inspection records, approved drawings, consultant compliance, DCD, sewer, traffic and owner evidence as applicable | **DDA Building Completion Certificate** or **DDA Fit-out Completion Certificate**
Trakhees / PCFC | Trakhees Civil Engineering Department, Ports, Customs and Free Zone Corporation | PCFC jurisdiction in Dubai | Construction/modification permits and NOCs, inspections and compliance | Before construction/fit-out, site inspections and before occupation | Work is checked against approved drawings, Modification Permit/NOC and regulations; pending comments require reinspection | Approved inspection status, reinspection record, approved drawings, system download and relevant clearances | **Modification Completion Certificate (MCC)**; occupation/use/storage is prohibited before issue
DCD | General Command of Dubai Civil Defence | Dubai | Fire/life-safety engineering, fire systems, hazardous materials and emergency readiness | Design review, installation/testing and final inspection before occupancy | Fire-stopping, alarms, sprinklers, smoke control, pumps, exits and signage are fire hold points | Approved DCD drawings, witnessed inspection/test and commissioning records | DCD Civil Defence completion/fire-safety certificate required by the applicable completion route
RTA Dubai | Roads and Transport Authority | Dubai | Roads, right-of-way, traffic/access, utilities interfaces and rail protection | Traffic/access design, NOC review, construction and phased monitoring near assets | NOC conditions govern methods, surveys, risk assessment, monitoring and asset protection; a material change can require resubmission | Current approved design/construction/rail NOC, inspection/site release, traffic approval and monitoring/as-built reports | Relevant RTA road/ROW/rail NOC close-out, clearance or accepted reinstatement record
DLD / RERA | Dubai Land Department / Real Estate Regulatory Agency | Dubai | Project registration, escrow/developer oversight, purchaser-facing status and property registration | Registration, sales/escrow monitoring, completion/status reporting and downstream unit registration | Not normally a technical SOR/NCR inspector; project status must not be used as technical acceptance | DLD Project Status Enquiry, developer completion submissions and registration/title evidence as applicable | Downstream registration/status evidence; not a substitute for DM/free-zone/Civil Defence completion
JAFZA | Jebel Ali Free Zone Authority | Dubai free zone | Estate access, lease, modification/fit-out permissions, HSE and NOCs | Before modification/fit-out, during estate controls and at occupation handover | The zone approval is separate from statutory approvals; its published modification NOC is a scope-control gate | Zone-issued modification NOC, inspection/clearance and applicable external certificates | JAFZA modification/fit-out approval or handover letter as applicable; **verify current requirement**
DMCC | Dubai Multi Commodities Centre authority | Dubai free zone | Estate, lease, fit-out/construction, access and HSE controls | Before fit-out/modification, during estate inspection and handover | Zone permit conditions and approved fit-out scope remain separate from DM/DCD/utility conditions | Current zone NOC/fit-out approval, inspection/clearance and applicable statutory approvals | Zone handover/trade or fit-out approval; **verify current requirement**
DAFZA | Dubai Airport Freezone Authority | Dubai free zone | Estate, lease, fit-out/construction, access and HSE controls | Before fit-out/modification, during estate inspection and handover | Zone permit conditions and approved scope form separate acceptance criteria | Current zone NOC/fit-out approval, inspection/clearance and applicable statutory approvals | Zone handover/trade or fit-out approval; **verify current requirement**
Dubai South | Dubai South master/free-zone authority | Dubai free-zone/master-development area | Estate, lease, construction/fit-out permissions, access and HSE | Before works, during estate inspection and at handover | Do not assume a DM/DCD approval replaces the estate-specific NOC or approved scope | Current zone NOC/fit-out approval, inspection/clearance and applicable statutory approvals | Zone handover/trade or fit-out approval; **verify current requirement**
Expo City Dubai | Expo City Dubai master/free-zone authority | Dubai master-development/free-zone area | Estate, lease, construction/fit-out permissions, access and HSE | Before works, during estate inspection and at handover | Estate interface and approved fit-out scope remain distinct from statutory approvals | Current zone NOC/fit-out approval, inspection/clearance and applicable statutory approvals | Zone handover/trade or fit-out approval; **verify current requirement**
Dubai Central Laboratory | Dubai Central Laboratory, Dubai Municipality | Dubai | Municipal material/product conformity and testing services | Material submittal, source approval, sampling/testing and material-NCR disposition | Material NCRs require quarantine, traceable sampling, replacement/approved disposition or compliant testing | Recognised lab report, product conformity/approval evidence, chain-of-custody and consultant/authority acceptance | Test/conformity record; no unsupported “Central Laboratory completion certificate”; **verify current requirement**
DMT | Department of Municipalities and Transport | Abu Dhabi Emirate | Planning, municipal development controls, permits and completion processes | Planning/design, permitting, construction inspection and completion/handover | Permit conditions, approved drawings, inspections and unapproved changes create observations/NCRs | Approved permit/as-builts, inspection records and approved amendments | Municipal certificate-of-completion file/service, as applicable
ADCM | Abu Dhabi City Municipality | Abu Dhabi City | Municipal building control, permit review, site work, completion and occupancy | Permit review, site inspection and completion/occupancy | Municipal comments and permit conditions require corrective work and reinspection; photographs alone do not close them | Municipality inspection/approval record, approved as-builts and completion documentation | Municipal/TAMM completion or occupancy documentation
ADCDA | Abu Dhabi Civil Defence Authority | Abu Dhabi Emirate | Fire prevention, life safety, evacuation and firefighting systems | Design approval, installation/testing and pre-occupation | Fire-stopping, alarms, sprinklers, pumps, emergency lighting and access are inspected hold points | Approved fire drawings, inspection/test and commissioning records | ADCDA Certificate of Compliance / Fire Safety and Protection Equipment certificate
ADQCC / QCC | Abu Dhabi Quality and Conformity Council | Abu Dhabi Emirate | Product conformity, technical regulations, testing and Trustmark/conformity schemes | Before incorporation of specified products and during surveillance | Wrong model, expired certificate, nonconforming batch or missing traceability requires quarantine, replacement and/or retest | Valid Product Conformity Certificate, accredited-lab report, batch records and approved material submittal | Product-conformity record; no building completion certificate
EAD | Environment Agency – Abu Dhabi | Abu Dhabi Emirate | Environmental permitting, impacts, waste, emissions, biodiversity and protected areas | Feasibility/EIA, pre-construction approval and construction monitoring | Dust, noise, waste, discharge, habitat and spill-control permit conditions become NCR criteria | Environmental permit/NOC, monitoring, waste records, compliance report and inspection outcome | Environmental clearance/acceptance where the permit provides one; **verify current requirement**
ADOSH / OSHAD | Abu Dhabi Occupational Safety and Health Center / Abu Dhabi OSH System Framework | Abu Dhabi Emirate | Emirate OSH framework and construction Codes of Practice | Before mobilisation and continuously during construction | Audits/inspections create corrective actions; OSH-CMP requires response timelines and corrective-action reporting | Live/approved OSH-CMP, audit/inspection reports, training, incident and corrective-action reports | Authority/SRA acceptance where required; otherwise controlled OSH close-out record
Estidama Pearl Rating System | DMT-administered sustainability rating system and Pearl Assessor process | Abu Dhabi Emirate | Sustainability design, construction and operation rating requirements | Design rating, construction evidence collection and completion before handover | Missed credits, substitutions, commissioning and as-built deviations are sustainability NCRs | PQP quality-checked submission, product/test/commissioning records, as-builts/photos and Pearl Assessor decision | Pearl verification/rating decision; not a substitute for statutory completion
ADIBC | Abu Dhabi International Building Code; enforced by the applicable building official | Abu Dhabi Emirate | Building minimums, permits, inspections, occupancy, utilities and violations | Design approval through final inspection and occupancy | Work must remain accessible until approved; concealed work without inspection can require opening-up | Permit, required inspection approvals, approved tests and as-builts | Certificate of occupancy/completion through the competent municipal process
DoE Abu Dhabi | Department of Energy | Abu Dhabi Emirate | Energy-sector technical regulation and safe electrical installations | Electrical design, installation, testing and energisation | Unlicensed work, failed insulation/earth tests, unapproved equipment and unnotified alterations are electrical NCRs | Licensed-contractor test forms, distributor inspection/test acceptance and energisation/connection approval | Applicable distribution-company completion/connection evidence; **verify current requirement**
Al Ain City Municipality | Al Ain City Municipality | Al Ain, Abu Dhabi Emirate | Municipal planning/building control, permits, inspections and completion | Permitting, inspections and completion throughout the project | Correct municipal file, permits and local inspection requirements govern deviations; Abu Dhabi City documents are not interchangeable | Approved permit, inspection records and as-builts | Al Ain municipal completion/occupancy documentation
Abu Dhabi Ports / KEZAD | Abu Dhabi Ports / Khalifa Economic Zones Abu Dhabi | Abu Dhabi ports and economic zones | Plot, access, utility interface, logistics, HSE and tenant/operational controls | Plot/design interface, construction access, tie-ins and operational handover | Lease, plot, utility and interface NOCs create project-specific hold points | Signed NOCs, approved methods, zone inspection and commissioning/tie-in acceptance | KEZAD/port contractual handover or operational acceptance; **verify current requirement**
Masdar / Masdar City | Masdar / Masdar City master developer | Abu Dhabi Emirate | Estate design, sustainability, utilities interfaces and fit-out controls | Master planning/design through tenant fit-out and handover | Developer comments, Pearl commitments, estate interfaces and fit-out conditions require separate closure from statutory approvals | Approved design/fit-out package, closed tracker, estate NOCs and commissioning evidence | Masdar handover/tenant acceptance; statutory certificates remain separate
Sharjah Municipality | Sharjah City Municipality | Sharjah | Building/construction permits, approved plans, municipal inspections and completion certification | Design/permit, construction inspections, as-built review and completion | Permit conditions, approved plans, systems/products and site inspections govern deviations and NCRs | Municipal inspection record, approved as-built/revised drawings, tests and photographs | Official building completion certificate
Sharjah Civil Defence Authority | Sharjah Civil Defence Authority / General Directorate of Civil Defence jurisdiction | Sharjah | Fire/life safety, alarms, firefighting, smoke control, access and applicable central gas systems | Fire strategy/design, installation hold points, testing, completion and occupancy | Fire stopping, fire doors, cause-and-effect, hydrant flow, gas and access defects require corrective action and reinspection | Approved drawings, compliance evidence, inspection and commissioning/maintenance records | Civil Defence compliance and building/gas-system completion certificate, coordinated with municipality approval
SEWA | Sharjah Electricity, Water and Gas Authority | Sharjah | Electricity, water and gas network connection, capacity, metering and technical installations | Design/connection applications, utility works, testing, inspection and energisation | Routes, loads, earthing, pressure tests, meter rooms and materials are utility hold points | SEWA NOC/connection approval, inspection and test results, meter/energisation record and applicable as-built/clearance | Utility connection/final clearance; building completion remains municipal
SRTA | Sharjah Roads and Transport Authority | Sharjah | Road corridors/right-of-way, entrances, excavations, utility crossings, temporary occupation and reinstatement | Design NOC before road work, work-zone control and reinstatement inspection | NOC drawings, traffic/side-digging control, asset protection and reinstatement define NCR close-out | SRTA NOC, engineer inspection/reinstatement acceptance and deposit-release evidence where applicable | ROW NOC close-out/reinstatement acceptance
Shurooq | Sharjah Investment and Development Authority | Sharjah | Master-developer/client controls for tourism, heritage, public realm and investment assets | Concept, design, construction, commissioning, operator acceptance and handover | Project brief, conservation, sustainability, quality and public-interface conditions create PMC inspection points | Developer acceptance, punch-list close-out and external municipal/Civil Defence/utility/environmental evidence | Shurooq handover/operation approval together with statutory approvals
HFZA | Hamriyah Free Zone Authority | Sharjah free zone | Free-zone engineering, construction/development planning and EHS | Building permit, construction, completion inspection, plant readiness and operation approval | Building permit, service inspection/testing and EHS conditions are staged release gates | HFZA inspection/test records, service NOCs and EHS documents | **HFZA Building Completion Certificate**, then separate **Operation Permit**
SAIF Zone | Sharjah Airport International Free Zone Authority | Sharjah free zone | Lease/licensing, facility and EHS controls for offices, warehouses and industry | Fit-out/factory construction, EHS inspection, operation and licence renewal | EIA topics, waste, chemicals, proposals and EHS inspections create observation/NCR obligations | SAIF NOC/lease & licensing approval, EHS clearance, safety-fitness evidence and external certificates as applicable | Licence/renewal and operational acceptance; external statutory completion may also be required
BEEAH / environment | BEEAH Environment | Sharjah and service areas | Environmental studies, waste management, waste permits/manifests, monitoring and remediation support | Planning/EIA, construction waste, commissioning and operational controls | Waste, dust/noise, discharge, contaminated soil and chemical issues require manifests and monitoring—not cleanliness photographs | Environmental study/approval where required, BEEAH manifest/acceptance, monitoring/remediation report and authority record | Environmental clearance from competent statutory authority where required; BEEAH is not a substitute regulator
Ajman MPD | Ajman Municipality & Planning Department | Ajman | Land use, planning, building permits, municipal inspections and completion certification | Design approval, construction inspection and handover | Approved drawings, permit conditions, waterproofing and inspection reports are hold points | Building inspection reports, water-insulation guarantee, Civil Defence letter, Roads & Infrastructure clearance, sewerage-certified form and Makani number | Official **Certificate of Completion** after MPD site inspection
Ajman Civil Defence | General Directorate of Civil Defence / Ajman Civil Defence | Ajman | Fire/life-safety design, systems and preventive-safety compliance | Design review, installation/testing and pre-occupation/operation | Fire stopping, rated doors, alarms, sprinklers, pumps, egress and emergency systems require approved drawings and witnessed tests | Approved fire drawings, conformity evidence, test records and inspection/letter | Applicable building/gas-system completion certificate and/or preventive-safety compliance certificate supporting MPD completion
EtihadWE | Etihad Water and Electricity, formerly FEWA | Ajman, Umm Al Quwain, Ras Al Khaimah and Fujairah | Electricity and desalinated-water distribution, connection and activation | Design/interface, utility works, commissioning and occupation | Loads, meters, trenches, chambers, pressure/flow/electrical tests and as-builts are utility hold points | Authority inspection acceptance, approved drawings, tests, meter/connection release and as-builts | Connection/activation/service-release approval; building completion is normally municipal
Ajman Free Zone | Ajman Free Zone / Free Zones Authority of Ajman | Ajman free zone | New-building NOCs and major fit-out permits, including structural, fire, MEP and layout change | Before work starts and during technical review/inspection | Work may not start before approval; scope, risk assessment, Civil Defence drawings and added load are change-control criteria | Electronic New Building NOC or approved Major Fit-Out Permit, with written inspection/completion acceptance if issued | Free-zone written acceptance; do not treat trade licence as construction completion certificate; **verify current requirement**
Ajman Port | Ajman Port | Ajman port estate | Port land, marine, logistics, security, traffic, access and utilities interfaces | Before/during port-area works and at handback | Port NOCs, work permits, inductions, traffic plans and reinstatement conditions are acceptance criteria | Port work/access NOC, inspection sign-off, reinstatement and joint handback records | Port handback/clearance letter where applicable; **verify current requirement**
Umm Al Quwain Municipality | Municipality of Umm Al Quwain | Umm Al Quwain | Municipal/urban-planning permits, contractor/consultant controls, inspection and completion | Planning/design approval, construction inspection and completion | Stamped permit, approved drawings and field comments govern deviations, setbacks and structural/MEP records | Inspection reports, approved revisions and relevant utility/Civil Defence clearances | Municipal building-completion certificate or permit close-out if issued; **verify current requirement**
UAQ Civil Defence | Umm Al Quwain Civil Defence | Umm Al Quwain | Fire/life safety blueprint approval, system testing and preventive-safety compliance | Design, installation/testing and pre-occupation/operation | Fire systems, occupancy, hazardous storage, access and cause-and-effect need traceable test evidence | Approved drawings, test certificates and Civil Defence inspection/approval | Applicable clearance, completion or preventive-safety certificate; **verify current requirement**
UAQ FTZA | Umm Al Quwain Free Trade Zone Authority | Umm Al Quwain free zone | Free-zone licensing, premises, tenant fit-out/construction controls and operational acceptance | Lease/fit-out before works, access/inspection and handover/licensing | Approved layout, work permit, contractor access and reinstatement obligations are acceptance criteria | Current FTZA premises/fit-out/construction approval, written clearance and external approvals | Handover/operational or licensing acceptance; published profile does not name a construction completion certificate—**verify current requirement**
RAK Municipality | Ras Al Khaimah Municipality Department – Buildings Administration | Ras Al Khaimah | Plan audits, building permits, inspections, implementation supervision, standards conformity and completion | Pre-design/permit, construction inspection and final completion review | Approved drawings, permits, specifications, workmanship and site safety drive NCR close-out | Inspector report, approved preliminary handover, Barjeel report/documents and Civil Defence achievement certificate where required | Electronic **Building Completion Certificate** after review
RAK public-service / utility interfaces | Relevant RAK public-service custodians, including RAKWA, Etisalat and General Resources Authority references in municipal completion process | Ras Al Khaimah | Service corridors, public infrastructure, utility connection and NOCs | Enabling works, excavation, diversion/tie-in, testing and connection | Protection, installation, testing, reinstatement and as-built observations remain open until asset-owner acceptance | Utility inspection/connection approval, NOC/clearance, tests/commissioning and approved as-built | Utility acceptance plus RAK Municipality completion; exact custodian/process—**verify current requirement**
RAK Civil Defence | Ras Al Khaimah Civil Defence / General Directorate of Civil Defence jurisdiction | Ras Al Khaimah | Preventive fire safety, fire engineering, systems approval and inspection | Fire design, installation/commissioning and final fire acceptance | Fire stopping, alarm, sprinkler, smoke control, pumps, exits and emergency lighting need specialist test/reinspection | Approved fire drawings, engineering/achievement evidence, tests and inspection records | Civil Defence completion/achievement and applicable preventive-safety compliance certificate
Marjan | Marjan / Al Marjan Island master developer | Ras Al Khaimah developments | Master-developer design, plot/interface, infrastructure, access, coastal and logistics controls | Before design approval through construction/interface and developer handover | Developer NOCs/comments are separate from Municipality approval | Written design/development NOC, approved IFC/interface drawings and inspection sign-offs | Developer clearance/handover where issued, alongside Municipality/Civil Defence certificates; **verify current requirement**
RAKEZ | Ras Al Khaimah Economic Zone | Ras Al Khaimah economic zone | Plot development, drawing review, building/modification permits, HS&E and staged construction approvals | Before mobilisation; Stage 1 before work, Stage 2 at 6 m and Stage 3 at 24 m/before 30 m; completion/operation | Stage approvals, night work, excavations, hazardous works and HS&E obligations are release gates | Written stage approvals, NOCs, HS&E inspection/operational-fitness evidence, incident and equipment/test records | RAKEZ building/modification completion NOC and operational fitness/acceptance as applicable
Fujairah Municipality | Fujairah Municipality – Engineering and Lands Department, Building Section | Fujairah | New permits, drawing submissions, concrete-pour and building-completion services | Design/permit, construction inspection and final completion | Structural, waterproofing, MEP and concrete defects need permit-aligned test and reinspection evidence | Approved permit/amendments, inspection records, tests and temporary-utility evidence if applicable | **Building Completion Certificate**
Fujairah Civil Defence | Fujairah Civil Defence / General Directorate of Civil Defence jurisdiction | Fujairah | Fire-preventive safety and fire-system engineering/inspection | Fire design, installation, commissioning, monitoring and final acceptance | Fire systems, compartmentation, cause-and-effect, access and evacuation findings require witnessed tests and reinspection | Approved fire documents, installer/maintenance evidence, tests and inspection records | Civil Defence building/gas-system completion and preventive-safety compliance certificate
FFZA | Fujairah Free Zone Authority | Fujairah free zone | Licensing, premises, fit-out and operational controls; special permits with government departments | Business setup, premises/fit-out, access, utilities, hazardous activity and operational licensing | Fit-out, access, utilities and operational observations can block licensing/occupation even after physical completion | FFZA premises/fit-out/operational approval, lease/licence records and relevant government NOCs | Operational/licensing acceptance; exact construction instrument—**verify current requirement**
Fujairah Ports Authority / Port of Fujairah | Fujairah Ports Authority / Port of Fujairah | Fujairah port areas | Port land, marine/terminal infrastructure, operational safety, access and interfaces | Before port-area works, during marine/terminal construction and commissioning/operational handover | Port permit, lifting, hot-work, traffic, berth, pipeline, environmental and safety conditions are NCR criteria | Work/access/operational approvals, inspection, commissioning, as-builts, tests and required external clearances | Port commissioning/operational handover acceptance
DEWA | Dubai Electricity and Water Authority | Dubai | Electricity/water networks, design/NOC, construction, substations, LV/HV inspection and connections | Design/NOC, construction, substation/LV/HV inspection and connection | Material approvals, hold-point inspections and snag notices require rectification and resubmission | Inspection notice/result, approved drawings, site photos, test certificates and portal approval | DEWA connection/supply release, **Completion Certificate**, **As Built Approval** and GIS update as applicable
ADDC | Abu Dhabi Distribution Company / TAQA Distribution | Abu Dhabi City | Electricity and water distribution | Design NOC, infrastructure installation, inspection, energisation and handover | Materials, pressure/electrical tests, meter/substation readiness and snags require distributor acceptance | Approved materials, inspection requests, tests, signed snag closure and as-builts | Connection/energisation approval, clearance/NOC and accepted as-builts
AADC | Al Ain Distribution Company / TAQA Distribution | Al Ain | Electricity and water distribution | Design, construction, inspection, energisation and handover | Materials, readiness, tests and signed snag closure are utility hold points | Approved materials, inspection requests, test results, connection readiness and as-builts | Connection/energisation approval, clearance/NOC and accepted as-builts
TRANSCO | Abu Dhabi National Energy Company transmission operator | Abu Dhabi Emirate | High-voltage electricity and water transmission assets | Proximity, crossing, diversion and protection design/construction | Protection and monitoring conditions are permit hold points | Approved method statement, protection/monitoring records, inspection/test, survey/as-built and written release | Transmission crossing/diversion/protection NOC and handover/acceptance record
TAQA | Abu Dhabi National Energy Company group | Abu Dhabi Emirate | Ownership/governance umbrella for operating technical entities | Project-specific; actual asset custodian determines involvement | A generic TAQA reference does not close an NCR: identify ADDC, AADC, TRANSCO or other asset custodian | Entity-specific NOC, inspection and acceptance evidence | Entity-specific connection, clearance, energisation or asset-handover acceptance
Empower | Emirates Central Cooling Systems Corporation | UAE district-cooling service areas | District-cooling networks, energy-transfer stations and customer interfaces | Master planning/design, ETS installation, pressure/flushing, testing and commissioning | Equipment, insulation, hydraulic, controls and interface defects require operator-witnessed evidence | Approved submittals, pressure/flushing reports, inspection, commissioning and BMS records | Operator connection and commissioning/operation acceptance; **verify current requirement**
Tabreed | National Central Cooling Company | UAE district-cooling service areas | District-cooling plants, networks and customer connections | Design, connection, construction, testing and commissioning | Equipment, hydraulic, insulation and interface NCRs close only through witnessed tests and commissioning | Connection/NOC, test and commissioning records, operator inspection | Operator connection/operation acceptance or handover certificate; **verify current requirement**
Emicool | Emirates District Cooling | UAE district-cooling service areas | District-cooling networks and customer connections | Design, ETS installation, pressure/flushing tests and commissioning | Material, installation, controls, meter and commissioning observations require operator acceptance | Approved materials, test/commissioning reports and operator inspection | Operator connection/acceptance; **verify current requirement**
e& | e& (Etisalat) | UAE telecom service areas | Telecom outside-plant and in-building fibre infrastructure | Early design NOC, material validation, implementation inspection and final testing | Duct routes, components, labels, room conditions and end-to-end tests are closure criteria | Lead-operator inspection, approved materials, test results and as-built/ODF record | Telecom NOC and operator completion/acceptance certificate
du | du / Emirates Integrated Telecommunications Company | UAE telecom service areas | Telecom outside-plant and in-building fibre infrastructure | Design NOC, approved materials, implementation and acceptance testing | Wrong route/component, labels, room condition or failed fibre test keeps the item open | Approved drawings/materials, inspection, end-to-end tests and as-builts | Operator completion/acceptance certificate
Etihad Rail | Etihad Rail | National railway corridors | Railway right-of-way/protection zones for buildings, bridges, utilities, excavation and machinery | Information/design/construction NOCs and activity-specific releases | Layouts, methods, risk assessments, monitoring and protected-zone conditions are rail hold points | Monitoring data, third-party studies where required, inspection records, as-built survey and written rail release | Activity-specific NOC close-out and rail-interface acceptance/handover
ITC / Abu Dhabi Mobility | Integrated Transport Centre, now Abu Dhabi Mobility | Abu Dhabi Emirate | Traffic operations, detours and works in the road right-of-way | Road-work planning, detour application, execution and reinstatement | Barriers, signage, lane geometry, access, timing and safety observations require permit closure | Traffic-control inspection, approved detour completion and safety records | Traffic-detour/road-works permit closure and traffic-management acceptance
Municipal road/drainage departments | DMT/Abu Dhabi, Abu Dhabi City Municipality, Al Ain Municipality, Western Region municipality functions and Dubai Municipality, as applicable | Abu Dhabi and Dubai municipal territories | Roads, stormwater/drainage, public realm, trench coordination and asset handover | Planning/design NOC, construction, road/drainage inspection and final handover | Trench, drainage tests, road base/asphalt and reinstatement are municipal hold points | Municipal inspection pass, CCTV/pressure/compaction test as applicable, survey/as-built and handed-over asset record | Municipal road/drainage handover, clearance NOC or phased permit close-out

## 7. Authority Tracker
Authority NOC, Inspection and Certificate Tracker
Every authority instrument that must be obtained. Never mark an authority-linked item closed without the instrument reference.
Item ID | Authority | Instrument required (NOC / inspection / certificate) | Linked SOR or NCR ID | Responsible party | Date requested | Target date | Actual date | Status | Instrument reference | Expiry date | Evidence location (EDMS path) | Blocker / escalation | Comments

## 8. KPI Dashboard
Quality Assurance KPI Dashboard
All values calculate from the registers. Enter the year in cell C4 to drive the monthly trend.
| Reporting year | 2026
KPI | Value
SOR raised (total recorded)
SOR closed
SOR open (including overdue)
SOR overdue
SOR closure rate
SOR to NCR conversion rate
Average SOR age of open items (days)
NCR raised (total recorded)
NCR closed
NCR open (including overdue)
NCR overdue
NCR closure rate
Mean time to close NCR (days)
NCR open more than 30 days
Repeat non-conformances (count)
Repeat rate
Cost of non-conformance recorded (AED)
Programme impact recorded (days)
Authority-linked items raised
Authority-linked items closed
Authority-linked closure rate
Inspections accepted first time (enter manually)
Inspections presented (enter manually)
Inspection pass rate
Monthly trend - items raised and closed
Month | NCR raised | NCR closed | SOR raised | SOR closed

## 9. RACI
Roles and Responsibilities (RACI)
R responsible, A accountable, C consulted, I informed. Adapt to the project organisation.
Activity | PMC inspector / engineer | PMC Quality Manager | PMC Resident Engineer | PMC Project Director | Contractor QA/QC | Contractor Project Manager | Client / Employer's Representative
Capture the observation and evidence | R | I | I | I | C | I | I
Classify and triage the finding | R | A | C | I | C | I | I
Issue the SOR | R | C | I | I | I | I | I
Issue the NCR | C | A | R | I | I | I | I
Approve the containment plan | C | C | A | I | R | C | I
Accept the root cause and CAPA | C | A | C | I | R | C | I
Verify rectification and witness tests | R | C | A | I | C | I | C
Sign the closure certificate | C | R | A | I | R | C | C
Maintain the register | C | A | I | I | R | I | I
Escalate overdue items | C | R | A | C | C | C | I
Issue contractual notices | I | C | R | A | I | C | C
Produce the monthly assurance pack | C | R | A | A | C | I | I
Close authority-linked items | R | C | A | I | R | C | I
Handover dossier and open item schedule | C | R | A | A | R | C | C
Defects register after taking-over | R | A | C | I | R | C | C

## 10. SOR Form
SITE OBSERVATION REPORT (SOR)
Project header loads automatically from the Dashboard sheet.
Project
Project / contract number
Location and emirate
Employer / client
PMC / consultant
Main contractor
SOR number
Date and time of observation
Discipline
Package / area
Exact location (level, grid, room)
Drawing number and revision
Requirement reference (specification / ITP / code)
Description of the observation
Required action
Risk if not corrected
Responsible party
Due date
Evidence reference (photograph / measurement)
Closure description and evidence reference
Closure date
Closed and verified by
Status
Converted to NCR (Y/N and NCR number)
Signed - PMC inspector
Signed - contractor representative

## 11. NCR Form
NON-CONFORMANCE REPORT (NCR)
Project header loads automatically from the Dashboard sheet.
Project
Project / contract number
Employer / client
PMC / consultant
Main contractor
Contract form and edition
Part 1 - Raised by the PMC
NCR number
Date raised
Raised by
Reviewed and issued by
Class (Minor / Major / Systemic / Documentation)
Discipline
Package / area and exact location
Drawing number and revision
Requirement breached (clause / ITP hold point / code)
Description of the non-conformance
Evidence of non-compliance attached
Extent and quantity affected
Containment required or applied
Effect on safety, structure, statutory approval, programme and cost
Response required by
Part 2 - Contractor response
Acknowledged by and date
Containment action and evidence
Root cause analysis (five why summary)
Corrective action with owner and date
Preventive action with owner and date
Proposed verification method
Programme impact and revised dates
Signed - contractor QA/QC manager
Signed - contractor project manager
Part 3 - PMC verification
Acceptance criteria
Verification method
Verification date and result
Test or inspection record reference
Instrument and calibration reference
Witnesses present (client / authority)
Verified by
Outstanding items, if any
Part 4 - Closure
Closure statement
Preventive action verified
Residual conditions with owner and date
Closure date
Evidence index reference
Signed - contractor QA/QC manager
Signed - PMC verifier
Signed - PMC Quality Manager
Signed - client representative (where required)
Part 5 - Commercial and programme record
Cost treatment
Back-charge reference
Programme or claim reference
Instruction or notice reference

## 12. Closure Certificate
NON-CONFORMANCE CLOSURE CERTIFICATE
Print-ready closure record. Load the project header from the Dashboard sheet.
Project
Project / contract number
Contractor
PMC / consultant
NCR number and title
Class and date raised
Date of this certificate
Closure statement
The non-conformance described above has been addressed in accordance with the approved corrective action. The works have been re-inspected or re-tested against the stated acceptance criteria and are confirmed to comply with the contract requirements referred to in the non-conformance report. The preventive action recorded has been implemented and verified. This non-conformance is closed, subject to any residual conditions listed below.
Verification basis (re-inspection or re-test record, acceptance criteria, result, instrument and calibration reference, witnesses)
Preventive action verified (description and effective date)
Residual conditions with owner and date, or 'None'
Evidence index (numbered list of attached evidence references)
Signature | Name | Position | Organisation | Date
Contractor QA/QC manager
PMC verifier
PMC Quality Manager
Client representative (where required)

## 13. Definitions and References
Definitions, Abbreviations and References
Single-page reference for site staff.
Term or abbreviation | Meaning
CAPA | Corrective action and preventive action, tracked with owners, dates and effectiveness verification
Closure certificate | Signed record confirming correction, verification and closure, subject to any residual conditions
Containment | Immediate action to stop a non-conformance spreading or to segregate affected work or materials
DLP | Defects liability period, during which the contractor remains responsible for remedying defects
Hold point | Point in the inspection and test plan at which work must not proceed until inspection or testing has been accepted
ITP | Inspection and test plan defining inspections, tests, acceptance criteria, frequency and hold and witness points
NCR | Non-conformance report raised when non-compliance with an approved requirement is confirmed
NOC | No objection certificate issued by an authority, utility or third party
Observation | Recorded concern or deviation that may not yet be a confirmed non-conformance
Residual condition | Condition attached to a closure, such as monitoring or documentation to be completed later
Snag list | Closeout completion items prepared before handover for otherwise compliant works
SOR | Site observation report; a logged observation with a due date and photographic closure
Taking-over | Point at which the Employer accepts the works, starting the defects liability period
Witness point | Point at which the PMC, client or authority may attend and record an inspection or test
Authority references | See the Authority Matrix sheet for the full UAE authority list and the evidence each authority requires

## 14. Major NCR Field Aid
MAJOR NCR CLOSE-OUT FIELD AID
Print on one sheet. Project header loads automatically from the Dashboard sheet.
Project
Contract
PMC
Contractor
NCR number
Class
Date raised
Location
Requirement breached
Contractor owner
PMC verifier
Target closure date
Authority involved
The seven gates - the item is closed only when all seven pass
Gate | Question to answer | Evidence that passes the gate | Status
G1 | Is the requirement and the acceptance criterion fixed and quoted? | Clause / specification section, drawing number and revision, ITP hold point or code reference, plus the objective criterion that defines compliance | Open
G2 | Is containment complete and is the affected extent bounded? | Stop / segregation / barricade record with dates and photographs; written boundary of affected work; hold notice reference | Open
G3 | Does the root cause reach a controllable system cause? | Five-why chain ending in a system cause, not human error alone; contributing control failures identified | Open
G4 | Is the CAPA complete and verifiable? | SMART corrective action; measurable preventive action; named management responsibility; implementation schedule and target dates; monitoring mechanism; evidence of long-term effectiveness | Open
G5 | Has the correction been verified by the right party? | Re-inspection or re-test against the stated criteria, calibrated instruments, witness signatures, designer confirmation, third-party test where required | Open
G6 | Where an authority or designer was engaged, has that party accepted? | Authority inspection record, NOC, certificate or approved revised drawing. The item cannot be closed on PMC inspection alone | Open
G7 | Is the evidence pack complete, indexed and filed, and are the as-builts updated? | Numbered evidence index, revised as-built markup, handover dossier and O&M update, register updated with closure certificate reference | Open
Time box and automatic escalation
Elapsed time | What must have happened | Record to hold | Escalation if not achieved
0 to 24 hours | Containment applied; NCR issued and distributed | Containment record, photographs, hold notice | Raise a written instruction to the contractor's project manager
24 to 48 hours | Written acknowledgement; single named owner appointed | Acknowledgement with owner and contact | Escalate to the contractor's project manager; withhold valuation of the affected item
Day 3 | Rectification method statement submitted and approved | Approved method statement and programme | Issue a written instruction to submit within 48 hours
Day 7 (minor) / Day 14 (major) | Root cause, corrective and preventive action submitted and accepted | Five-why analysis, CAPA with owners, schedule and monitoring | Reject and require resubmission; start the escalation ladder
Day 5 after approval | Rectification started with resources on site | Labour and material allocation record | Instruction to proceed; consider the Notice to Correct route
Completion plus 5 days | Re-inspection or re-test carried out and result recorded | Inspection or test record with acceptance criteria | Instruction to re-present; consider third-party verification
Successful verification plus 3 days | Closure certificate signed by the PMC and the contractor | Signed closure certificate and evidence index | Report the overdue closure in the monthly assurance pack
Any item 7 days past due | Written instruction to remedy | Instruction referencing the NCR and the contract clause | Automatic escalation to the PMC Resident Engineer
Any item 14 days past due | Notice to Correct issued in parallel with the quality record | Contractual notice with the obligation, the requirement and the stated time | PMC Project Director and client notified the same day
Any item 28 days past due | Payment and cost action | Withholding note, back-charge statement, delay record | Client escalation and a written recovery plan from the contractor
Safety, structural or statutory item | Immediate escalation, no waiting period | Instruction with the authority or code reference | Notify the client and, where required, the authority
Red flags: escalate immediately if any of these appear
• Photographs offered as the only evidence of closure
• Root cause stated as “carelessness”, “subcontractor error” or “misunderstanding” with no system cause
• Preventive action with no document, checklist, hold point, training record or physical control behind it
• No acceptance criterion recorded when the NCR was issued
• Verification proposed by the party who executed the work, with no independent check
• Authority-linked finding with no authority instrument referenced
• Correction executed before the design or authority consequences were assessed
• Item aged beyond 30 days with no recovery plan or programme impact assessment
Evidence pack checklist: tick only when the document is in the closure dossier
☐ NCR with clause, drawing revision, ITP hold point or code reference and the acceptance criterion
☐ Photographs with date and location metadata, before and after
☐ Containment record and hold notice
☐ Method statement, approved, with the revision number
☐ Test or inspection record with results and the calibration reference of instruments used
☐ Third-party or accredited laboratory report where applicable
☐ Material conformity, batch or serial traceability for replaced products
☐ Designer or engineer confirmation where the correction affects the permanent works
☐ Authority inspection record, NOC, certificate or approved revised drawing
☐ Revised as-built markup and handover dossier update
☐ Signed closure certificate with the evidence index
Rule: no authority or designer linked item is closed by PMC inspection alone; no major item is closed on corrective action alone.
Signature | Name | Position | Date
Contractor QA/QC manager
PMC verifier
PMC Quality Manager

## 15. Major NCR Checklist
Major NCR Close-Out Checklist - Contractor's QA/QC Team
Work top to bottom. No step may be skipped, and the PMC will not accept a closure offer until every applicable line is evidenced.
# | Phase | Checkpoint | Action required | Evidence required | Owner | Target date | Status | PMC verification | Comment
1 | A. Immediate - within 24 hours | Acknowledge the NCR in writing and appoint one named owner |  | Written acknowledgement naming the owner and contact | Contractor QA/QC manager |  | Not started
2 | A. Immediate - within 24 hours | Stop, segregate or barricade the affected scope and record it |  | Containment record with photographs and hold notice reference | Contractor site manager |  | Not started
3 | A. Immediate - within 24 hours | Bound the affected extent physically and in writing |  | Marked-up plan showing the affected area and quantity | Contractor QA/QC engineer |  | Not started
4 | A. Immediate - within 24 hours | Verify the exact requirement and the acceptance criterion |  | Clause, specification section, drawing revision, ITP hold point or code reference | Contractor QA/QC manager |  | Not started
5 | A. Immediate - within 24 hours | Identify whether an authority, designer or utility is engaged |  | Authority or designer reference and the instrument that will prove acceptance | Contractor authority coordinator |  | Not started
6 | B. Within 48 hours | Assess the effect on safety, structure, statutory approval, programme and cost |  | Written impact assessment with the affected activities listed | Contractor project manager |  | Not started
7 | B. Within 48 hours | Withdraw or quarantine non-conforming materials and record batch details |  | Quarantine record with batch or serial numbers and delivery references | Contractor QA/QC + stores |  | Not started
8 | B. Within 48 hours | Assess whether the correction requires a design change or a revised drawing |  | Designer's preliminary position or a request for assessment | Contractor design manager |  | Not started
9 | C. Method and planning | Prepare and submit the rectification method statement |  | Method statement with sequence, materials, plant and safety controls | Contractor QA/QC manager |  | Not started
10 | C. Method and planning | State the acceptance criterion and the proposed verification method in the submittal |  | Verification plan naming the test or inspection, the standard and the witness | Contractor QA/QC manager |  | Not started
11 | C. Method and planning | Obtain approval before execution, including the revised drawing revision where applicable |  | Approved method statement and approved drawing revision | PMC and, where applicable, the designer |  | Not started
12 | C. Method and planning | Confirm whether the authority must approve or re-inspect before or after execution |  | Confirmed authority route and the re-inspection request date | Contractor authority coordinator |  | Not started
13 | D. Root cause and CAPA | Complete the five-why analysis to a controllable system cause |  | Five-why chain with evidence for each step | Contractor QA/QC manager with the production team |  | Not started
14 | D. Root cause and CAPA | Identify the control that allowed the escape (inspection, approval, material control, information) |  | Contributing factor analysis linked to the failed control | Contractor QA/QC manager |  | Not started
15 | D. Root cause and CAPA | Define the SMART corrective action for the affected works |  | Corrective action with the defined scope, method and acceptance criterion | Contractor project manager |  | Not started
16 | D. Root cause and CAPA | Define the measurable preventive action that addresses recurrence project-wide |  | Documented change to a procedure, checklist, hold point, training or physical control | Contractor project manager |  | Not started
17 | D. Root cause and CAPA | Assign named management responsibility for each action |  | Action register showing owner, position and accountability | Contractor project manager |  | Not started
18 | D. Root cause and CAPA | Set the implementation schedule with target completion dates |  | Schedule extract showing each action with dates | Contractor planner |  | Not started
19 | D. Root cause and CAPA | Define the monitoring mechanism and the effectiveness evidence |  | Monitoring plan and the evidence that will demonstrate long-term effectiveness | Contractor QA/QC manager |  | Not started
20 | E. Execution | Mobilise labour, materials and access so the correction is not delayed |  | Resource allocation and access record | Contractor site manager |  | Not started
21 | E. Execution | Execute to the approved method with hold points respected |  | Daily records, inspection requests and hold point releases | Contractor QA/QC engineer |  | Not started
22 | E. Execution | Maintain material traceability for replacement products |  | Conformity certificate, batch or serial number and delivery record | Contractor QA/QC + procurement |  | Not started
23 | E. Execution | Record the works photographically with date and location metadata |  | Before, during and after photographs | Contractor QA/QC engineer |  | Not started
24 | F. Verification | Self-inspect against the acceptance criterion before offering the works |  | Contractor's own inspection record with results | Contractor QA/QC manager |  | Not started
25 | F. Verification | Submit the inspection or test request with the required notice period |  | Inspection request and the agreed witness arrangements | Contractor QA/QC manager |  | Not started
26 | F. Verification | Support testing with calibrated instruments and current certificates |  | Calibration certificates for every instrument used | Contractor QA/QC engineer |  | Not started
27 | F. Verification | Obtain third-party or accredited laboratory testing where the category requires it |  | Third-party or accredited test report | Contractor QA/QC manager |  | Not started
28 | F. Verification | Attend the re-inspection and respond to any failure immediately |  | Attendance record and closure of any new comment | Contractor QA/QC manager |  | Not started
29 | G. Authority and designer | Submit the authority re-inspection request or the revised drawing for approval |  | Submission receipt and reference number | Contractor authority coordinator |  | Not started
30 | G. Authority and designer | Attend and support the authority inspection and close every comment raised |  | Authority inspection record with comments closed point by point | Contractor authority coordinator + QA/QC |  | Not started
31 | G. Authority and designer | Obtain the designer's written confirmation where the permanent works were affected |  | Designer's confirmation letter or approved calculation | Contractor design manager |  | Not started
32 | H. Documentation and closure | Compile the indexed evidence pack for the record |  | Numbered evidence index with every document referenced | Contractor document controller |  | Not started
33 | H. Documentation and closure | Update the as-built drawings and the O&M information affected |  | Revised as-built markup and O&M update | Contractor design manager |  | Not started
34 | H. Documentation and closure | Sign the closure certificate with the PMC and the client where required |  | Signed NCR closure certificate with the evidence index | Contractor QA/QC manager |  | Not started
35 | H. Documentation and closure | Update the contractor's own register to mirror the PMC register |  | Updated contractor register with the same identifier | Contractor QA/QC manager |  | Not started
36 | I. Prevention and monitoring | Implement the preventive action and record the effective date |  | Updated procedure, checklist, training record or hold point | Contractor QA/QC manager |  | Not started
37 | I. Prevention and monitoring | Verify effectiveness over a defined observation window |  | Follow-up inspection or audit result showing no recurrence | Contractor QA/QC manager with PMC verification |  | Not started
38 | I. Prevention and monitoring | Brief the relevant teams and subcontractors on the change |  | Attendance records and briefing material | Contractor project manager |  | Not started

## 16. Closure Audit Tracker
16. Retrospective closure audit tracker
One row per closed NCR. Amber cells are manual inputs; score columns drive the tier. Tier 1 (18 or more) is mandatory 100 per cent verification; Tier 2 (10 to 17) is targeted; Tier 3 (9 or less) is statistical, plus any item carrying a red flag or a missing record. Tiers, dispositions and test methods follow the protocol PMC-QA-AUD-004, Appendix B, G and E.
NCR ref | Rev | Element | Location / level | Works class | Authority linked (Y/N) | Payment linked (Y/N) | Concealed (Y/N) | Impact score (0-24) | Evidence weakness (0-12) | Total score | Tier (1/2/3) | Evidence status | Evidence gap named | Forensic red flag (Y/N) | Test method (App. E) | Test date | Result | Pass / fail | Designer: stability or safety affected? | Disposition (A-F) | Required action | Action owner | Target date | Status | Re-test date | Re-test result | Retrospective certificate ref | Decennial review date | Notes
NCR-0142 | B | Structural - raft | Zone 3, grid F7 | Structural | Y | Y | Y | 18 | 10 |  |  | Absent | Cube results and pour card not traceable | Y | Core compressive strength |  |  |  | Designer confirms the core results meet the specified strength; durability accepted with monitoring | C | Rectify or accept with monitoring; issue the retrospective closure certificate | Contractor QA Manager, verified by PMC |  | Rectification required |  |  |  |  | Sample row - delete before use
NCR-0157 | A | Waterproofing - podium | Podium, level 2 slab | Waterproofing | N | Y | Y | 9 | 6 |  |  | Partial | No flood test record before covering | N | Flood test + thermography |  |  |  | Specialist confirms the membrane is intact | B | Re-inspect and produce the missing flood test record | PMC Resident Engineer |  | In verification |  |  |  |  | Sample row - delete before use
NCR-0203 | C | Fire stopping - riser | Core, level 5 riser | Fire and life safety | Y | N | Y | 13 | 5 |  |  | Partial | Penetration seal system reference missing | N | Physical inspection + system verification |  |  |  | Fire specialist confirms the seals match the approved system | B | Re-inspect 100 per cent of penetrations and file the system references | Contractor QA/QC Manager |  | In verification |  |  |  |  | Sample row - delete before use
Audit summary
Closed NCRs in the register
Tier 1 items (mandatory 100 per cent)
Tier 2 items
Tier 3 items
Items with absent evidence
Items with partial evidence
Items carrying a red flag
Disposition A - verified closed
Disposition B - compliant, evidence deficient
Disposition C - unverified and non-compliant
Disposition D - stability or safety implication
Disposition E - falsification indicators
Disposition F - record missing
Verified closed
Closed with evidence complete (per cent)

## 17. Decennial Risk Register
17. Decennial risk register
Items that remain open, unverified or subject to a residual risk after the retrospective audit. Risk score = likelihood x severity. Review at least annually and on every trigger event in Section 4 of the protocol. Years remaining is calculated from the delivery date entered in cell D212.
Ref | Item / defect | Element | Location | Stability or safety impact (Y/N) | Statutory instrument affected | Age at review (years) | Years remaining in the ten-year period | Likelihood (1-5) | Severity (1-5) | Risk score | Band | Mitigation and monitoring | Owner | Status | Last review | Next review | Residual risk
DR-001 | Podium slab waterproofing - no flood test record; membrane opened up and found intact | Waterproofing | Podium, level 2 | N | None | 2 |  | 2 | 3 |  |  | Thermographic survey at 6-month intervals; moisture monitoring in the retail unit below | PMC Quality | Monitoring |  |  | Low - fabric intact, residual risk monitored
DR-002 | Raft raft-zone cube results not traceable; cores taken, strength within specification | Structural - raft | Zone 3, grid F7 | N | None | 2 |  | 1 | 4 |  |  | Core results filed in the dossier; no further action, monitoring by review only | PMC Quality | Closed with record |  |  | Low - verified by core testing
DR-003 | Fire-stopping system reference missing at level 5 riser penetrations; seals verified and re-documented | Fire and life safety | Core, level 5 | Y | Civil Defence certificate - verify scope | 2 |  | 2 | 5 |  |  | Physical re-inspection of 100 per cent of penetrations; certificate scope check with the applicant | PMC Quality | In progress |  |  | Medium - verified physically, instrument check pending
Portfolio position
Project delivery or handover date
Items in the register
Items with a stability or safety impact
High band items
Medium band items
Open or in progress
Aggregate risk score

## 18. RCA CAPA Tracker
18. Root cause and CAPA tracker
Every rectified item under the retrospective audit protocol carries a completed 5 Whys chain, a SMART corrective action, a measurable preventive action with a monitoring mechanism, named responsibilities and dates, and evidence of effectiveness reviewed at least one cycle after implementation. An action without effectiveness evidence remains open.
Ref | Item / NCR ref | Why 1 | Why 2 | Why 3 | Why 4 | Why 5 | Root cause | Corrective action (SMART) | Specific | Measurable | Achievable | Relevant | Time-bound | Preventive action (measurable) | Monitoring mechanism | Frequency | Responsible (named) | Start date | Target date | Actual date | Status | Rectification method | Rectification evidence ref | Effectiveness evidence | Effectiveness reviewed on | Effectiveness confirmed (Y/N)
RCA-001 | NCR-0142 | The closure certificate was signed without the cube results | The closure template had no mandatory evidence field | The quality plan required evidence but the template was not aligned to it | The template was issued before the quality plan was revised | No review of the template against the approved plan | Closure template not aligned to the quality plan, with no review control | Revise the closure certificate to require a mandatory evidence list with a reference for each item | The revised template is issued under a controlled revision | Completeness checked on 20 sample closures | Template change is within the QA function's control | Directly removes the root cause of the finding | Within 14 days of the disposition | Six-monthly template-to-plan alignment review added to the QA calendar | Sample audit of new closures against the revised template | Monthly | PMC Quality Manager |  |  |  | In progress | Re-test the element and file the results | RC-001 supporting pack | 20 consecutive closures with complete evidence packs
RCA-002 | NCR-0203 | Penetration seals were closed without a system reference | The installer used an unapproved system on site | Material control did not check the fire-stopping system against the approval | The store issue process had no fire-safety control | Fire-stopping was not treated as a controlled material | Material control process omitted fire-stopping systems | Add fire-stopping systems to the controlled material list with approval verification at issue | All fire-stopping systems issued only against an approved submittal | Zero unapproved systems on the next monthly store audit | Store control is within the contractor's control | Prevents recurrence at source | Within 21 days | Inspector competency refresher for passive fire protection | Monthly store audit plus 100 per cent penetration re-inspection | Monthly | Contractor QA Manager, verified by PMC |  |  |  | In progress | Re-inspect and re-document 100 per cent of penetrations | RC-002 supporting pack | Zero findings in the following two quarterly inspections

## 19. Risk Alert Engine
19. Risk alert engine - instant high-risk flags by project phase
Every count below is live: it recalculates from the NCR Register (sheets 2 and 16) and the Decennial Risk Register (sheet 17) as data is entered, so the high-risk position is visible without any manual sorting. The per-item score, flag and reason are calculated in columns AJ to AL of the NCR Register. For cross-project, ranked and time-series analysis, run the SQL query pack (ncr_flag_queries.sql) through the runner (ncr_risk_engine.py).
Rule | Project phase | Alert condition (fires automatically) | Live count | Threshold | Automatic action | Owner
R-01 | Phase 1 - Design, permits and authority | Authority-linked or NOC-linked NCRs still open (column AB = Yes and no closure date) |  | Any | Weekly written instruction; withhold the affected valuation line; notify the applicant | PMC Resident Engineer
R-02 | Phase 1 - Design, permits and authority | Authority-linked closures with no authority / NOC reference recorded |  | Any | Verify the instrument directly; re-open the item internally until the instrument is produced | PMC Quality Manager
R-03 | Phase 1 - Design, permits and authority | Phase 1 items open past their agreed completion date |  | Any | Weekly delay list to the contractor's project manager; design or permit hold reviewed | PMC Resident Engineer
R-04 | Phase 2 - Construction and fit-out | Major or systemic NCRs open past the agreed completion date |  | > 0 | Instruction to correct; escalate to Notice to Correct at 14 days past due; payment hold on the item | PMC Project Director
R-05 | Phase 2 - Construction and fit-out | NCRs recorded as a repeat of a previous NCR and still open |  | > 1 | Systemic quality review; audit the contractor's quality management system (ISO 9001 process control); require a system-level CAPA | PMC Quality Manager
R-06 | Phase 2 - Construction and fit-out | Closed items in the audit tracker with absent evidence and a recorded red flag |  | Any | Stop the technical review on the affected items; preserve originals; take legal advice | PMC Project Director
R-07 | Phase 3 - Testing and commissioning | Items closed with no verification date recorded (closure on assurance) |  | Any | Re-verify physically and re-issue the closure through the retrospective certificate route | PMC Resident Engineer
R-08 | Phase 3 - Testing and commissioning | Items closed without a closure certificate reference |  | > 0 | Issue the closure certificate from sheet 12 and file the evidence pack; do not accept verbal closure | PMC Quality Manager
R-09 | Phase 3 - Testing and commissioning | Discipline NCRs (MEP, fire and life safety) open for 14 days or more |  | Any | Testing and commissioning hold; witness testing schedule reviewed with the contractor | PMC Discipline Lead
R-10 | Phase 3 - Testing and commissioning | Tier 1 audit items with no test or inspection date recorded |  | Any | Physical verification cannot be closed; schedule the test under the approved test plan | PMC Quality Manager
R-11 | Phase 4 - Handover and taking-over | Any NCR open for more than 30 calendar days |  | Any | Escalation to the quarterly quality review with the client; recovery programme required | PMC Project Director
R-12 | Phase 4 - Handover and taking-over | Phase 4 (handover) items open past the agreed completion date |  | Any | Taking-over readiness review; the item is listed in the defects register with retention leverage | PMC Resident Engineer
R-13 | Phase 5 - Defects liability and decennial | Decennial register items in the high band not closed with a record |  | Any | Monitoring plan re-approved; next review date set; client informed in the assurance pack | PMC Quality Manager
R-14 | Phase 5 - Defects liability and decennial | Decennial items with a stability or safety impact and no next review date |  | Any | Immediate review date assignment; specialist re-assessment where the defect is progressive | PMC Project Director
R-15 | Phase 5 - Defects liability and decennial | Audit tracker items carrying an unresolved forensic red flag |  | Any | Escalate under Appendix G category E within 30 days of the flag being recorded | PMC Quality Manager
Item-level flags calculated in the NCR Register (columns AJ to AL)
F-01 | All phases | NCRs flagged CRITICAL (auto score 10 or more) |  | Any | Same-day notification to the Project Director and the client's representative | PMC Project Director
F-02 | All phases | NCRs flagged HIGH (auto score 6 to 9) |  | Any | Included in the weekly assurance pack with the action owner and date | PMC Quality Manager
F-03 | All phases | NCRs flagged WATCH (auto score 3 to 5) |  | Any | Routine monitoring at the discipline meeting; review the score at the next update | PMC Discipline Lead
F-04 | All phases | Highest single auto risk score on the register |  | Report only | Benchmark for trending; investigate any score of 12 or more as a priority item | PMC Quality Manager
F-05 | All phases | Average auto risk score across the open population |  | Report only | Trend indicator for the monthly assurance report | PMC Quality Manager
Runbook - what to run, when, and for whom
Daily | Open sheet 2 and filter column AK on CRITICAL and HIGH; clear the daily site-meeting list | Highlighted NCR list with the alert reason | Resident Engineer and contractor QA/QC manager
Weekly | Refresh sheet 19; issue the alert counts with new, closed and overdue items | Weekly assurance one-pager | Contractor's project manager and PMC Project Director
Fortnightly | Run the SQL query pack (ncr_flag_queries.sql) through the runner for ranked, cross-phase and cross-project flags | NCR_Risk_Query_Report.xlsx with one tab per query and the ranked Q-99 priority list | PMC Quality Manager and client quality representative
Monthly | Run the closure audit refresh (sheet 16) and the decennial review (sheet 17) | Audit progress and residual risk position | Client and PMC Project Director
Quarterly | Run the CAPA effectiveness queries (Q-70 to Q-72) and the repeat root cause analysis | Systemic failure list and preventive action view | Employer's Representative and PMC Project Director
On trigger | Any audit trigger event in Section 4 of protocol PMC-QA-AUD-004: run queries Q-40 to Q-52 against the closed population | Retrospective audit worklist by disposition | PMC Quality Manager, escalated to the client