# Authority Notification and Industrial / Free-Zone Utility Handover Pack

| Document control | Detail |
| --- | --- |
| Prepared by | Intermass |
| Purpose | Provide a professional authority-notification email and a detailed checklist for final site clearance, environmental handover, permanent utility-meter handover and meter-removal scenarios. |
| Users | Project managers, MEP managers, utility coordinators, HSE/environment managers, document controllers and client representatives. |
| Jurisdictions | Dubai, Abu Dhabi and free-zone/industrial developments. The exact plot authority, utility provider, master developer and permit conditions must be confirmed before use. |
| Core distinction | A permanent-meter handover is normally a transfer/acceptance process. A permanent-meter closure/removal is normally a demolition, redevelopment or no-longer-required-service process. |

## 1. Before sending: select the correct notification type

| Notification type | Use it when | Do not use it when | Expected result |
| --- | --- | --- | --- |
| Final site-clearance / environmental-handover request | Works are complete and an authority or jurisdictional body must confirm closure, acceptance, inspection or permit-condition compliance. | A final inspection, waste record, rehabilitation action or utility task remains open. | Written direction, inspection appointment, portal acknowledgement or clearance/closeout confirmation. |
| Permanent utility handover notification | The asset will remain occupied/operational and permanent services transfer to the client, landlord, facility manager or nominated account holder. | The permanent meter must be removed because the asset is being demolished/redeveloped. | Account-holder/occupancy transition, meter reading/acceptance and operating-responsibility record. |
| Permanent meter removal / closure request | Owner-approved demolition, redevelopment or cessation of the service makes the meter unnecessary. | The client needs the permanent service after construction handover. | Approved removal, isolation/disconnection and site/meter closure confirmation. |
| Free-zone lease/licence termination notice | The entity is closing a lease, licence or company operation. | The project is only handing over a completed facility while the tenant/client remains operational. | Separate corporate/lease closure workstream with free-zone clearances. |

Management rule: Do not allow a “close meter” task to be marked required until the client, owner and project director have signed the end-state decision. This avoids disconnecting a building that is due to operate on Day One after handover.

## 2. Authority notification email template

### Email subject

Request for Final Site Clearance and Environmental Handover — [Project Name] — [Plot / Lease / Building No.] — [Authority Reference]

### Email body

To: [Named authority officer / authority inbox]

      Cc: [Client representative]; [Consultant]; [Master developer/free-zone authority]; [HSE/environment manager]; [Utility coordinator]

      From: Intermass — [Project manager name / title]

Dear [Title and name / Authority Team],

Intermass, on behalf of [Client / Permit Holder], respectfully notifies [Dubai Municipality / Abu Dhabi Municipality / Department of Municipalities and Transport route / relevant free-zone authority] that the works at [Project Name], Plot/Lease/Building [reference], located at [full location and jurisdiction], have reached the final site-clearance and handover stage.

The project scope comprised [brief scope] under [building permit / environmental permit / environmental clearance / NOC / lease reference]. We request your review and confirmation of the remaining authority requirements for final clearance and environmental handover, including whether an inspection, portal submission, additional NOC, permit-condition closeout, utility evidence or site rehabilitation confirmation is required.

Current closeout status

| Closeout item | Status | Reference / evidence |
| --- | --- | --- |
| Physical works and site housekeeping | [Complete / in progress] | [Completion report / photographs] |
| Environmental permit / clearance conditions | [Complete / conditional / not applicable] | [Permit reference / conditions register] |
| Waste and hazardous-material records | [Complete / in progress / not applicable] | [Manifest / transfer note / disposal certificate] |
| Temporary utility removal | [Complete / in progress / not applicable] | [Request / isolation / removal reference] |
| Permanent service end state | [Transferred to client / remains in client account / removal requested] | [Utility request / client acceptance] |
| Site rehabilitation / equipment removal | [Complete / in progress / not applicable] | [Final inspection / photographs / inventory] |

Attached for your review are the [completion certificate / approved as-built drawings / environmental closeout register / waste records / final site photographs / utility evidence / client handover record]. A detailed attachment schedule is included below.

We kindly request confirmation of the appropriate final-clearance route and, where applicable, an inspection appointment or written confirmation of the remaining actions. Please advise if a specific portal submission, form, fee, original document or additional clearance is required.

The project team contact for this request is [name, mobile number, email]. We would appreciate acknowledgement of receipt and direction on the next step by [reasonable requested date].

Yours faithfully,

For Intermass

      [Name]

      [Title]

      [Mobile] | [Email]

      [Project address]

### Mandatory attachment schedule

| Attachment | Include when | Suggested file name |
| --- | --- | --- |
| Authority / permit / NOC register | Every request | 01_Authority_Register_[Project].pdf |
| Completion and site-clearance report | Every request | 02_Final_Site_Clearance_Report_[Project].pdf |
| Environmental conditions closeout register | Permit/clearance has environmental conditions | 03_Environmental_Conditions_Closeout_[Project].pdf |
| Waste and hazardous-material evidence | Waste/hazardous materials generated or removed | 04_Waste_Manifests_and_Disposal_[Project].pdf |
| Final photos and rehabilitation record | Equipment/site removal, land reinstatement or vacant-land confirmation applies | 05_Rehabilitation_and_Final_Photos_[Project].pdf |
| Utility handover/closure dossier | Any utility transfer, account closure, meter removal or final bill applies | 06_Utility_Handover_or_Closure_[Project].pdf |
| Client/owner authority letter | Authority needs owner/permit-holder consent or utility account-holder approval | 07_Client_Owner_Authorisation_[Project].pdf |
| As-built / testing / commissioning dossier | Permanent service handover, MEP acceptance or building completion applies | 08_AsBuilts_Testing_and_Commissioning_[Project].pdf |

## 3. Jurisdiction-specific email wording to insert where applicable

| Jurisdiction | Recommended wording | When to use |
| --- | --- | --- |
| Dubai mainland / Dubai Municipality route | “Please confirm the applicable final clearance, environmental-condition closeout and inspection route for this location, including any portal submission or authority-specific evidence required.” | Use the named permit/clearance reference; do not assume Dubai Municipality controls a plot that is governed by a master developer or special authority. |
| Abu Dhabi Municipality / DMT route | “Please confirm the applicable municipal final-clearance route and whether utility-assets clearance, plot/site approval or environmental-condition confirmation remains required for this location.” | Use the authority name shown on the permit and location system; include DMT/ADM wording only after confirming the assigned jurisdiction. |
| EAD / Abu Dhabi industrial facility | “The permit holder requests confirmation of the remaining environmental-permit conditions and whether any cancellation, variation, monitoring submission or decommissioning documentation is required.” | Use only when an EAD environmental permit/licence or its conditions apply. |
| JAFZA / Trakhees / PCFC zone | “Please confirm the applicable free-zone, Trakhees/PCFC and asset/lease clearances required before final facility handover or, where applicable, lease/licence termination.” | Separate facility handover from company/lease termination. JAFZA’s termination guidance requires DEWA final-bill settlement/clearance for relevant leased facilities and further clearances depending on formation/operation. 1 |
| Other industrial/free-zone authority | “Please confirm the zone’s NOC, asset/lease, utility, environmental/HSE and final-inspection requirements for the facility and the planned client operating model.” | Use for KEZAD, Dubai South, DMCC, DAFZA, SAIF Zone, Hamriyah, RAKEZ or any master-developer-controlled site. |

## 4. Detailed permanent utility handover and meter-closure checklist

| ID | Control | Handover / closure rule | Required evidence | Primary owner | Applies to |
| --- | --- | --- | --- | --- | --- |
| PM-01 | Confirm plot jurisdiction | Identify municipality, utility, master developer/free zone, landlord and environmental regulator; record written confirmation where the plot route is unclear. | Jurisdiction map, lease/plot plan, authority email/NOC. | Project manager | Every project |
| PM-02 | Confirm client operating model | Confirm who will occupy, operate and pay for each permanent service from handover. | Signed client/owner operating-responsibility matrix. | Project director | Every project |
| PM-03 | Select meter end state | Select A. Transfer/retain, B. Temporary meter removal, or C. Permanent meter removal. | Approved end-state decision. | Project director | Every meter/service |
| PM-04 | Establish service inventory | List electricity, water, sewerage, gas, district cooling, telecom, fire-service connections, drainage pumps and generators; identify meter/account/serial numbers and isolation points. | Meter and service inventory. | Utility coordinator | Every project |
| PM-05 | Classify service | Mark each service permanent, temporary construction, landlord/master-metered, district utility or embedded zone utility. | Classification register signed by MEP/client. | MEP manager | Every project |
| PM-06 | Confirm service ownership | Record account holder, meter owner, service owner, final-bill payer, deposit recipient and future FM contact. | Utility account/ownership declaration. | Commercial manager | Every account |
| PM-07 | Verify technical readiness | Complete energisation, commissioning, protection settings, testing, labelling, access and safe operation of permanent systems. | Test certificates, commissioning records, single-line diagrams, O&M manuals. | MEP/commissioning manager | Transfer/retain |
| PM-08 | Prepare permanent handover pack | Provide as-builts, warranties, O&M manuals, training, spare-parts list, meter data and emergency contacts to client/FM. | Signed technical handover dossier. | Document controller | Transfer/retain |
| PM-09 | Take joint final meter readings | Read meters with client/utility/landlord as required; photograph serial numbers and seals. | Joint meter-reading form and photographs. | Utility coordinator | Every handover/closure |
| PM-10 | Transfer or establish client account | Obtain the correct account transfer, move-in, tenancy/lease and business documentation; confirm payment/deposit treatment. | Utility request, lease/tenancy, trade licence, client account confirmation. | Utility coordinator | Transfer/retain |
| PM-11 | Settle outgoing account | Clear outstanding amounts before deactivation, transfer or clearance request, as relevant. | Final invoice, paid receipt, clearance certificate. | Commercial manager | Account closure / Dubai transfer |
| PM-12 | Confirm DEWA transfer route | For Dubai, use the appropriate DEWA route and retain the premises/account identifiers, valid tenancy/lease documentation and trade licence where relevant to the customer type. DEWA’s Move-to service includes business customers and states that outstanding dues for existing premises must be settled; it lists a valid tenancy contract for free-zone customers and a trade licence for relevant non-DED customers. 2 | DEWA request reference, supporting documents and client confirmation. | Utility coordinator | Dubai |
| PM-13 | Confirm Abu Dhabi removal route | For a genuine permanent-meter removal, confirm owner approval and demolition/redevelopment scope before submitting the TAQA route. TAQA.33 applies to industrial and commercial customers and publishes a four-working-day service time; its listed documents include owner demolition application, municipal demolition permit showing meter count and land plan. 3 | TAQA application, owner letter, permit, land plan and closure/work-order evidence. | Utility coordinator | Abu Dhabi removal only |
| PM-14 | Close temporary electricity/water systems | Isolate, lock out, remove temporary panels/cables/pipes, record final reading and remove temporary account/meter only after permanent handover is safe. | LOTO certificate, removal record, final reading and utility confirmation. | MEP manager | Temporary services |
| PM-15 | Obtain zone/master-developer NOC | Confirm whether the zone requires NOC, approved as-builts, lease/affection plan, photographs, inspection or asset handover before modifying/removing/handing over systems. JAFZA’s NOC guidance lists trade licence, permits, approved drawings and, for plot facilities, Trakhees lease/affection plan and approved as-builts. 4 | Zone NOC/acceptance, inspection report and approved drawings. | Project manager | Free-zone/industrial development |
| PM-16 | Close free-zone facility vs company/lease track | Decide whether the facility only hands over, or the tenant/company/lease closes. The latter triggers a separate licence/lease termination plan with finance, visas, customs, telecom, utility and authority clearances as applicable. 1 5 | Management decision and jurisdiction-specific closure checklist. | Client / commercial manager | Free zones |
| PM-17 | Close industrial environmental conditions | Reconcile environmental permit/clearance conditions, monitoring, waste, chemicals, spills/contamination, equipment removal and land rehabilitation. | Conditions register, manifests, inspection/remediation evidence and authority correspondence. | HSE/environment manager | Industrial / permitted activity |
| PM-18 | Retain utility and environmental evidence | Build an indexed evidence pack with request references, approvals, bills, readings, photos, certificates, NOCs and client acceptance. | Final indexed dossier. | Document controller | Every project |
| PM-19 | Conduct dual readiness review | Confirm Authority/utility ready and Client/FM ready statuses independently. List all exceptions, live services and owners. | Signed readiness review and exception register. | Project director | Every project |
| PM-20 | Release final demobilisation | Remove the final temporary support only when permanent services, live asset protection and client/authority dependencies are resolved. | Demobilisation release authorisation. | Project director | Every project |

## 5. Jurisdiction and industry decision matrix

| Scenario | Meter action | Authority / documentation route | Critical cautions |
| --- | --- | --- | --- |
| Completed industrial facility will operate under the client | Transfer/retain permanent meter. | Utility provider + client account holder + client/FM technical acceptance + zone/master-developer NOC as applicable. | Do not submit permanent-meter removal. Maintain life-safety, process and operational services. |
| Construction temporary supply no longer required | Disconnect/remove temporary service. | Utility provider + contractor/owner authority + LOTO/removal evidence. | Do it only after permanent systems are safe/operational or occupation is not required. |
| Industrial facility is demolished/redeveloped | Remove permanent meter only where approved. | Owner approval, demolition permit, land plan, utility application, master-developer/zone clearance and environmental controls. | Confirm every meter is named on the permit/application and all cables/services are isolated. |
| JAFZA/Trakhees facility is handed over but business continues | Transfer/retain service; close facility construction items. | Zone NOC/asset handover + utility/client account steps; retain environmental/HSE evidence where applicable. | Do not confuse building/facility handover with licence/lease termination. |
| JAFZA/Trakhees tenant/company/lease is terminating | Close/clear services as the zone requires. | JAFZA/Trakhees termination workflow, DEWA clearance/final settlement for relevant facility types, telecom/finance/customs/visa clearance as applicable. 1 | Corporate deregistration has additional conditions and should run as a dedicated workstream. |
| Abu Dhabi industrial facility is permanently removed | Remove meter only for approved decommissioning/demolition. | TAQA removal route, owner documentation, municipality demolition permit and land plan; EAD conditions/cancellation if the facility holds the applicable permit/licence. 3 | TAQA’s published service time is a service indicator, not a substitute for the wider demolition or environmental closeout programme. |

## 6. Suggested target dates and escalation triggers

| Milestone | Target before handover / demolition | Escalate when |
| --- | --- | --- |
| Jurisdiction, operating model and meter end-state decision | 8 weeks | Plot/utility/master-developer route remains unclear beyond the target date. |
| Utility inventory, account ownership and client FM nomination | 6 weeks | Account holder, meter ownership or payer is disputed. |
| Zone NOC / technical dossier / environmental closeout review | 6 weeks | A zone/permit condition requires an inspection, as-built correction or rehabilitation. |
| Transfer or removal submission package | 4 weeks | Owner letter, lease, trade licence, permit or client authorisation is missing. |
| Joint readings, final bills, clearance and client acceptance | 2 weeks | Permanent services are not accepted, final bill is unpaid or closure may interrupt client operation. |
| Final demobilisation release | Handover day | Any life-safety service, temporary service, environmental condition or authority/client exception remains open. |

## References

Use note. This pack is designed to support authority communication and management control. Before sending, replace every bracketed field, confirm the current service route on the authority/utility portal, and obtain the permit holder/client’s approval. For controlled zones, follow the zone’s current requirements even when an emirate-level utility service appears applicable.