## Dashboard
CRANE ABOVE FORMWORK — DAILY SIMOPS & PERMIT CONTROL
Project inputs below automatically populate the daily checklist and control sheets. Complete before printing or issuing the shift pack.
PROJECT / SHIFT INPUTS
Project name |  | Location / authority
Work package | Heavy crane operations above active internal formwork floors | Date
Shift |  | SIMOPS coordinator
Appointed person / lifting supervisor |  | Formwork supervisor
Temporary-works coordinator |  | Dewatering supervisor
Crane ID / type |  | Lift plan no. / revision
Excavation PTW no. / expiry |  | Formwork permit / ITP release
Weather / wind check |  | Emergency radio channel
DAILY DECISION GATES
1. Documents current | Excavation PTW, lift plan, formwork release and SIMOPS plan are valid for the named workface.
2. Crane / ground accepted | Crane configuration, position, bearing, set-back and surcharge check are accepted.
3. Formwork floor accepted | Falsework/formwork configuration and floor capacity are released for intended work and landing loads.
4. Exclusion zone ready | Lift/fall zone is physically barricaded; the formwork floor is cleared before any load enters.
5. Water / monitoring normal | Dewatering resilience and latest movement/groundwater status show no unresolved trigger.
6. Communications tested | One radio channel, banksman/signal method and stop-work handback protocol are confirmed.
Shift release decision | PROCEED only if every gate is YES and no project-specific hold point remains open. |  | Decision

## NDT Acceptance
IN-SITU CONCRETE STRENGTH — ACCREDITATION & ACCEPTANCE HIERARCHY
Do not approve a shoring/strut release from indirect NDT alone. The structural engineer and temporary-works designer define the stage criterion and acceptance logic.
Evidence tier | Method / standard | Permitted role | Accreditation / scope check | Engineering acceptance | Release status | Comments / report reference
Laboratory qualification | ISO/IEC 17025:2017 | Competence framework for testing laboratory | ENAS/EIAC or authority/consultant accepted body; current scope covers exact method | Consultant verifies prequalification
Primary production evidence | Traceable cured cubes / project specification | Normal strength evidence cited by CoP 40.0 | Scope covers concrete compression method | Structural engineer compares with stage criterion
Early-age support | ASTM C1074 maturity | Early estimate only where approved mixture relationship exists | Scope covers maturity method if laboratory performs it | Written engineer acceptance of relationship and criterion
Indirect NDT | ASTM C805/C805M or EN 12504-2 rebound hammer | Uniformity / comparative mapping; not stand-alone release strength | Scope covers rebound method; equipment check documented | Engineer accepts project-specific correlation
Indirect NDT | ASTM C597 or EN 12504-4 UPV | Uniformity / discontinuity screening; not direct strength | Scope covers UPV method; equipment verification documented | Engineer accepts interpretation / correlation
Complementary in-place test | ASTM C803/C803M penetration or ASTM C900 pull-out | Additional project-specific strength evidence | Scope covers selected method | Engineer defines sampling and acceptance
Direct in-place evidence | ASTM C42/C42M or EN 12504-1 cores | Resolution of uncertainty / representative in-place strength | Scope covers core preparation and compression | Engineer approves core plan and interprets results
Final decision | Combined strength assessment | Reconciles cubes, NDT, cores, maturity if used and full load path | Report signed by laboratory authorised signatory | Structural engineer + TWD + consultant issue staged release
RELEASE DECLARATION
Structural engineer conclusion
Temporary-works designer release
Consultant / Dubai anchor written consent where applicable
Permit issuer PTW revalidation

## SIMOPS Checklist
DAILY SIMOPS COORDINATION CHECKLIST — CRANE ABOVE ACTIVE FORMWORK
Complete at shift start, before each high-risk lift, after every change event and at handover. Default rule: no formwork/rebar/concreting work below a suspended load or inside the lift/fall zone.
Ref | Daily check | Status | Evidence / record | Responsible role | Time checked | Action / hold point | Close-out by
A1 | One named SIMOPS coordinator with stop-work authority is appointed for the shift. |  |  | Principal Contractor
A2 | Daily workface map identifies crane position/radius, lift corridor, landing zone, formwork floors, plant routes, pumps and evacuation routes. |  |  | SIMOPS Coordinator
A3 | Excavation PTW, lift plan, formwork release/ITP, plant certificates and specialist permits are current. |  |  | Permit Issuer / HSE
A4 | Handover confirms support status, incomplete lifts, water/monitoring results and outstanding hold points. |  |  | Shift Supervisors
A5 | One radio channel, banksman/signal protocol and emergency communications test are complete. |  |  | Lifting Supervisor
B1 | Crane, operator/rigger/slinger and lifting accessories have valid inspection/certification/competence evidence. |  |  | Appointed Person
B2 | Lift plan matches actual load, radius, configuration, lift route, landing location and weather condition. |  |  | Appointed Person
B3 | Crane/outtrigger/track position has an accepted ground-bearing and shoring-surcharge check. |  |  | TWC / Geotechnical Authority
B4 | Planned lift route does not cross any occupied formwork, rebar, concrete-pour or egress area. |  |  | Lifting Supervisor
B5 | Critical/non-routine lift classification and additional approval are verified where applicable. |  |  | Appointed Person
B6 | Wind, visibility, lighting, blind-lift arrangements and signal method meet the approved lift plan. |  |  | Crane Operator / Lifting Supervisor
C1 | Formwork/falsework configuration is approved and the permit to load/pre-pour release is valid. |  |  | Formwork Supervisor / Consultant
C2 | Floor/work-platform capacity has been checked for the planned landing, storage, dynamic and crane-induced loads. |  |  | Structural / TWD
C3 | No scaffold/formwork/falsework deck is being altered, struck or overloaded in the crane influence zone. |  |  | Formwork Supervisor
C4 | Formwork/rebar crews are briefed on the work freeze, barriers and all-clear handback method. |  |  | Structural Work Supervisor
C5 | Protected emergency egress remains clear of lifting gear, materials, hoses and temporary services. |  |  | SIMOPS Coordinator
D1 | Physical barriers, signs and a sentry isolate lift/fall zone from the active internal floor. |  |  | Lifting Supervisor
D2 | Affected floor is cleared before load enters; nobody is beneath suspended load or in the fall zone. |  |  | Lifting + Formwork Supervisors
D3 | Earthmoving, telehandler, pump and delivery activity is frozen where it could affect lifting, shoring or egress. |  |  | SIMOPS Coordinator
D4 | Tag lines, load control, landing-zone controls and pinch-point precautions are active. |  |  | Rigger / Slinger
D5 | Zone-clear command before lifting and documented all-clear before work resumes are confirmed. |  |  | Lifting Supervisor
E1 | Duty and standby dewatering pumps are operational; no pump isolation endangers stability. |  |  | Dewatering Supervisor
E2 | Latest instrumentation and visual inspection show no unresolved movement, water or support trigger. |  |  | Monitoring / TWC
E3 | Rescue access, first aid, emergency equipment, contacts and alarm method remain ready/unobstructed. |  |  | HSE Lead
E4 | Stop/revalidate protocol is known for rain, wind, pump fault, monitoring alert, support damage, crane fault or lost communications. |  |  | SIMOPS Coordinator
SHIFT RELEASE / HANDOVER
SIMOPS coordinator release
Lifting supervisor release
Formwork supervisor release
Permit issuer decision
Shift handover / open holds

## Permit Matrix
CRANE / FORMWORK / EXCAVATION PERMIT-INTERFACE MATRIX
Work interface | Controlling document | Linked permit / release | Required acceptance before work | Stop / revalidate trigger | Lead authority | Status / comments
Crane lift above/adjacent to active internal formwork floor | Approved lift plan (CoP 34.0) | Routine/critical lift authorisation + daily SIMOPS release | Load, radius, route, crane position, ground bearing, exclusion zone and floor clearance accepted. | Load/radius/path/wind/occupancy/communications change. | Appointed Person / Lifting Supervisor
Active formwork / falsework below crane influence area | Formwork design + CoP 40.0 permit-to-load / permit-to-strike | Pre-pour / permit-to-load release; controlled handback | Capacity, configuration, inspection status, protected egress and crew briefing accepted. | Formwork change, damage, overloading or lift-zone intrusion. | Formwork Supervisor / Consultant
Excavation and temporary shoring | Excavation PTW + TWD/dewatering/monitoring plan | Stage-release permit for support change + monitoring review | Shoring, water, monitoring and surcharge/bearing condition accepted. | Trigger breach, water event, plant move, support defect or unapproved load. | TWC / Geotechnical Authority
Crane setup / outriggers near excavation | Lift plan + bearing/surcharge check | Plant-position release / ground-bearing certificate if project procedure requires | Designer-accepted set-back, mats/base plates, actual ground condition and exclusion zone. | Settlement, rain, location change or monitoring concern. | TWC / Appointed Person
Electrical / dewatering conflict | Electrical PTW + LOTO | Isolation certificate / LOTO + standby pump verification | Alternative pumping, backup and water-level resilience proven before isolation. | Backup loss, water rise, electrical fault or maintenance delay. | Electrical AP / Dewatering Supervisor
Hot work near formwork / waterproofing | Hot-work PTW | Hot-work permit + fire watch | Combustibles controlled, ventilation suitable and escape route open. | Atmosphere change, fire-watch absence, flooding or fire protection impairment. | Hot-work Permit Issuer
Work at height / leading edge | Work-at-height plan + scaffold/formwork inspection | WAH permit if required + rescue plan | Certified access, edge protection, rescue readiness and no lift conflict. | Guardrail/scaffold change, wind condition or lift encroachment. | WAH Supervisor
Concrete placement after lifting | Concrete-pour plan + CoP 38.0 + formwork permit-to-load | Pre-pour ITP release + pump setup approval | Formwork capacity, pump position, truck route, hose restraint, egress and dewatering ready. | Pump/truck move, hose conflict, formwork distress or water event. | Concrete / Formwork Supervisors

## References
SOURCES AND PROJECT-SPECIFIC COMPLETION REQUIREMENTS
ADPHC CoP 40.0 — False Work (Formwork), v4.1 | https://www.adphc.gov.ae/-/media/Project/ADPHC/ADPHC/PDF/OSHAD-SF/Codes-of-Practise/2026/COP-400--False-Work-Formwork-v41-English.pdf | Required design strength, normal laboratory cube testing and permit-to-strike logic.
Dubai Article 57 — Bylaw Concerning Building Requirements and Specifications | https://dlp.dubai.gov.ae/Legislation%20Reference/2021/Administrative%20Resolution%20No.%20(37)%20of%202021%20Amending%20the%20Bylaw%20Concerning.html | Written consultant consent for anchor removal; continuous monitoring and surcharge controls.
Dubai Municipality — Accreditation Certificates | https://www.dm.gov.ae/municipality-business/accreditation-certificates/ | DCL EIAC accreditation to ISO/IEC 17025 and Infrastructure/Building Materials Laboratories.
MOIAT — Emirates National Accreditation System | https://moiat.gov.ae/en/programs/404 | Federal ENAS ISO/IEC 17025 accreditation scheme for testing laboratories.
Abu Dhabi QCC — Central Testing Laboratories | https://www.qcc.gov.ae/en/Our-Operational-Sectors/Central-Testing-Labs | ISO 17025:2017 service context and accredited private-sector construction-testing partners.
ADPHC CoP 34.0 — Safe Use of Lifting Equipment and Lifting Accessories | https://www.adphc.gov.ae/-/media/Project/ADPHC/ADPHC/PDF/OSHAD-SF/Codes-of-Practise/2026/COP-340--Safe-Use-of-Lifting-Equipment-and-Lifting-Accessories-v41-English.pdf | Lift-plan, ground condition, exclusion-zone and crane-near-excavation controls.
ADPHC CoP 38.0 — Concrete Placing Equipment | https://www.adphc.gov.ae/Legislation/-/media/64D20E622271480B908A4863FA822C90.ashx | Formwork suitability and concrete-pump/excavation interfaces.
ASTM / EN / ACI technical references | ASTM C42/C42M; C597; C803/C803M; C805/C805M; C900; C1074; EN 12504-1/-2/-4; ACI 228.1R | Confirm the current edition and project-specification adoption before issuing an NDT test plan.
PROJECT-SPECIFIC COMPLETION
Enter the authority/development-zone name, issued permit conditions, consultant requirements and named third-party laboratory details on the Dashboard.
Confirm that each selected laboratory has a current ISO/IEC 17025 scope covering the exact test method; attach the certificate and scope to the project ITP.
Complete acceptance criteria, sample grid, correlation basis, test age and repair procedure only after approval by the structural engineer and temporary-works designer.

## Lists (hidden)
YES | PROCEED
NO | HOLD / REVALIDATE
N.A. | STOP WORK
HOLD