## Project Dashboard
Deep Excavation Trigger & Dewatering Pump LOTO Workbook
Enter project-specific values in pale-blue cells. All Alarm values, target heads, rate limits and PTW details require approval by the geotechnical, temporary-works, dewatering and electrical authorities before use.
Project and Permit Information
Project |  |  |  | Entry
Location / Jurisdiction |  |  |  | Entry
Contractor |  |  |  | Entry
Client / Main Contractor |  |  |  | Entry
Excavation Reference / Area |  |  |  | Entry
PTW Number |  |  |  | Entry
Isolation Certificate No. |  |  |  | Entry
Pump ID / Feeder / Panel |  |  |  | Entry
Authorized Person (AP) |  |  |  | Entry
Permit Holder |  |  |  | Entry
Competent Electrician |  |  |  | Entry
Dewatering Supervisor |  |  |  | Entry
Temporary Works Coordinator |  |  |  | Entry
Geotechnical / TWD Approval Ref. |  |  |  | Entry
AAA Trigger Calculation Inputs
Trigger Variable | Input Value | Unit | Alert % | Action % | Alarm % | Approval / Design Reference | Notes
Alert multiplier | 0.5 | factor |  |  |  | Published example; designer may amend | Use by stage/instrument after approval.
Action multiplier | 0.8 | factor |  |  |  | Published example; designer may amend | Use by stage/instrument after approval.
Inclinometer movement Alarm | 25 | mm |  |  |  | Example only — replace | Most onerous of design/asset/authority limit.
Inclinometer movement-rate Alarm | 2 | mm/day |  |  |  | Example only — replace | Set for current stage.
Piezometer internal target head | 10 | mRL |  |  |  | Example only — replace | Target design drawdown head.
Piezometer internal high-head Alarm | 11 | mRL |  |  |  | Example only — replace | No uplift/piping/inflow acceptance exceeded.
External allowable drawdown Alarm | 0.5 | m |  |  |  | Example only — replace | Protect adjacent ground/assets.
External drawdown-rate Alarm | 0.2 | m/day |  |  |  | Example only — replace | Set for aquifer and asset sensitivity.
The workbook calculates Alert and Action at 50% and 80% of a designer-approved Alarm input. The Alarm input itself is never generated by this workbook; it must be approved in the excavation, temporary-works and dewatering design package.

## AAA Dashboard
AAA Monitoring Dashboard — Deep Excavation
The values below are driven from the Project Dashboard inputs. Replace the illustrative Alarm inputs with project-designer-approved, stage-specific limits before issue. Frequency is a conservative benchmark for active work and must be revised by the approved monitoring plan and permit conditions.
Project
Area / excavation reference
PTW
TWC
Geotechnical / TWD approval
Approved Trigger Ladder — Enter Alarm Inputs on Project Dashboard
Metric | Alert | Action | Alarm | Unit | Active-work frequency | Alert / Action frequency | Design approval
Inclinometer: cumulative movement |  |  |  | mm | Daily minimum during active work* | Each shift or higher frequency per plan | Engineer / TWD
Inclinometer: movement rate |  |  |  | mm/day | Daily minimum during active work* | Each shift or higher frequency per plan | Engineer / TWD
Piezometer: internal head |  |  |  | mRL | Daily minimum during active work* | Each shift or higher frequency per plan | Geo / dewatering designer
Piezometer: external drawdown |  |  |  | m | Daily minimum during active work* | Each shift or higher frequency per plan | Geo / dewatering designer
Monitoring Frequency and Decision Escalation
Condition | Instrument readings | Decision / communication | Work control | Source status
Baseline / pre-start | Stable baseline series at approved frequency | Review and accept datum/instrument health before work | No progression below released level without accepted baseline | Project/design requirement
Active excavation / support / dewatering change | Daily minimum benchmark for inclinometers and piezometers* | Review trends before next stage; record consultant decision | Proceed only under released temporary-works stage / valid PTW | Published benchmark*; project may require more
Alert / atypical trend | Increase to each shift or higher as set by engineer | Validate data; inspect shoring, ground, water and pumps; notify TWC/designer | Continue only with documented engineer confirmation | AAA response framework
Action | Intensify per contingency plan | Stop affected work; issue stage hold; implement mitigation and review | Suspend affected PTW until revalidated/reissued | AAA response framework
Alarm / emergency | Continuous or near-real-time where applicable | Evacuate/make safe; emergency response; full engineering reassessment | Suspend relevant PTWs; restart only under renewed authority | AAA response framework
*Frequency note: MRT Corp guidance for works in a railway protection zone specifies daily inclinometer and piezometer readings during active construction and allows changes subject to acceptance. This workbook uses “daily” only as a conservative benchmark; the final frequency must follow the project monitoring plan, temporary-works design, asset-owner requirements and issued permit conditions. No current site readings are shown in this dashboard.

## AAA Trigger Register
AAA Trigger Register — Inclinometers and Piezometers
Pale-blue cells are project inputs. Formula cells calculate preliminary Alert and Action values. The designer must approve every Alarm input, rate limit, target level and construction-stage applicability.
Instrument Trigger Schedule
Instrument ID | Type | Location / Stage | Baseline | Target / Normal | Alarm Input | Unit | Alert | Action | Alarm | Alert Rate | Action Rate | Alarm Rate | Designer Approval Ref. | Current Status
I-04 | Inclinometer — cumulative movement | Wall panel / excavation stage 2 | 0 | N/A |  | mm | [7 empty] | Enter current reading
P-02 | Piezometer — internal head | Inside excavation / deepest stage |  |  |  | mRL | [7 empty] | Enter current reading
P-07 | Piezometer — external drawdown | Outside shoring / adjacent asset | 0 | 0 |  | m | [7 empty] | Enter current drawdown
Trigger Response and PTW Control
Level | Response
Normal / Green | Maintain approved reading frequency; validate data and inspect the work face.
Alert | Notify supervisors/TWC/monitoring lead; validate reading and datum; inspect and increase monitoring.
Action | Stop affected activity; secure/exclude area; notify designers; implement approved contingency plan.
Alarm / Emergency | Make area safe, evacuate if credible instability; activate emergency plan and obtain full engineer reassessment.
For every instrument, define separate Alarm values for each critical construction stage. Use an approved contingency plan before an Action level is reached; treat unexpected trend acceleration, failed instrument/datum or visual distress as a potential Action event even if a cumulative threshold has not yet been reached.
Note on O6: Enter a project status manually after comparing current reading and rate with the approved trigger register. Do not rely on an automated status alone without validating the reading and datum.

## PTW-LOTO Checklist
PTW Isolation and LOTO Checklist — Electrical Dewatering Pumps
Complete as a controlled attachment to the project PTW and electrical isolation certificate. It must be reviewed by the Authorized Person, Permit Holder, competent electrician and dewatering supervisor.
Controlled Work Information
Project |  |  | Date / Time
Location / Jurisdiction |  |  | Date / Time
PTW Number |  |  | Date / Time
Isolation Certificate No. |  |  | Date / Time
Pump ID / Feeder / Panel |  |  | Date / Time
Authorized Person |  |  | Date / Time
Permit Holder |  |  | Date / Time
Competent Electrician |  |  | Date / Time
Dewatering Supervisor |  |  | Date / Time
A. Planning and Permit Verification
No. | Verification requirement | Status | Evidence / corrective action | Initials | Date / Time
1 | Controlling PTW identifies exact pump, feeder/panel, work scope, duration, Permit Holder, AP, competent electrician and work party.
2 | Electrical isolation certificate is raised, cross-referenced to PTW and entered in the isolation register.
3 | Current single-line diagram, panel labels, feeder identification, local isolator and cable route positively identify every supply point.
4 | All energy sources identified: normal feeder, generator/ATS, UPS/control power, PLC/SCADA, float/pressure switch, auto-restart, VFD/capacitors and mechanical/water pressure.
5 | Duty/standby plan confirms a functional, tested standby pump, emergency power/fuel, approved discharge route and high-water alarm before target pump isolation.
6 | Dewatering supervisor confirms isolation will not breach water-level, groundwater, flood, uplift, piping or access/egress trigger limits.
7 | Affected persons and contractor interfaces notified in a common understood language; SIMOPS controlled.
8 | Work area dry, illuminated, accessible and clear of exposed electrical hazards; rescue route maintained.
9 | Competent electrician has authorisation, correct PPE/insulated tools and approved voltage-indicator/test instrument.
B. Isolation and LOTO Execution
No. | Verification requirement | Status | Evidence / corrective action | Initials | Date / Time
1 | Record water level, pump runtime/flow and duty/standby status; stop target pump by normal operating control.
2 | Disable every local, remote and automatic start signal: float switch, PLC/SCADA, timer, auto-restart and generator/ATS transfer logic.
3 | Open the identified primary energy-isolating device: feeder breaker, fused isolator, disconnect switch or plug-and-socket isolation as applicable.
4 | Isolate control power and all alternate electrical supplies, including generator, ATS, UPS and remote-panel feeds.
5 | Apply authorised lock and identification tag to every energy-isolating device. Tag is legible and suitable for wet/damp excavation conditions.
6 | For multiple exposed workers, use group lockbox/multi-lock hasp: every exposed worker applies their own personal lock.
7 | Release/restrain stored energy: VFD/capacitor discharge per manufacturer instruction; no rotation; pressure/backflow isolated or restrained.
8 | Prove tester on known live source; test absence of voltage at isolation point; re-prove tester on a known live source.
9 | Perform controlled try-start from all credible local, remote and automatic commands after confirming people are clear; verify no start occurs.
10 | Record isolation points, lock/tag numbers, test instrument ID, verification result, date/time and authorised signatures.
11 | AP verifies complete isolation and Permit Holder confirms workplace safe before PTW authorisation.
C. During Work and Shift Transfer
No. | Verification requirement | Status | Evidence / corrective action | Initials | Date / Time
1 | Original PTW, isolation certificate and LOTO diagram displayed or immediately available at work location; duplicate live PTW retained centrally.
2 | No lock/tag is bypassed, removed or transferred except under the project’s written authorised procedure.
3 | Dewatering supervisor continues monitoring water level, standby pump, emergency power/fuel, discharge route and weather/flood status.
4 | Any rising water, standby failure, groundwater trigger, changed scope or changed condition causes immediate stop-work and referral to AP.
5 | For shift change, isolation condition and responsibility transfer follow the written LOTO procedure; physical inspection, PTW revalidation/reissue and work-party briefing are complete.
D. Return to Service and Close-out
No. | Verification requirement | Status | Evidence / corrective action | Initials | Date / Time
1 | Work complete; tools, temporary leads and materials removed; guards/covers restored; terminals secure; area clean and dry.
2 | Personnel clear and affected persons notified before re-energisation; head count completed where applicable.
3 | Each authorised worker removes only their own personal lock/tag. Any exceptional removal follows the documented employer procedure and authority.
4 | Restore supply/control/automatic functions in approved sequence only after confirming safe-to-start condition.
5 | Controlled functional test verifies pump direction/rotation, electrical readings, flow, discharge route, high-water alarm, duty/standby changeover and emergency supply response as applicable.
6 | Record post-restoration water level and pump test result; AP closes isolation certificate and controlling PTW only after normal readiness is confirmed.
Status key: C = Compliant; PC = Partially Compliant; NC = Non-Compliant; NA = Not Applicable. A red/NC item that compromises isolation integrity, emergency dewatering resilience or electrical safety is a no-go until resolved and formally released.

## References
References and Use Conditions
This workbook applies the cited control framework but must be reviewed against the current site permits, employer procedure, authority NOCs, power-distribution arrangement and approved designs before issue.
Authoritative and Technical Sources
Ref. | Source | Application in this workbook | URL
1 | ADOSH-SF CoP 29.0 — Excavation Work | Ground conditions, dewatering, support systems and competent-person excavation inspection. | https://www.adphc.gov.ae/en/Legislation/Code-of-Practices
2 | MRT Corp Instrumentation & Monitoring Guidelines, 2018 | AAA governance; example Alert 50% and Action 80% of Alarm; Alarm derives from impact assessment/limiting controls and varies by construction stage. | https://www.mymrt.com.my/wp-content/uploads/2019/08/3.-MRT-Corp-Instrumentation-Monitoring-IM-Guidelines.pdf
3 | ADOSH-SF CoP 21.0 — Permit to Work Systems, Version 4.0 | AP verification; isolation certificates; controlling PTW; revalidation, change and emergency suspension. | https://www.adphc.gov.ae/-/media/Project/ADPHC/ADPHC/PDF/OSHAD-SF/Codes-of-Practise/21---Permit-to-Work-Systems--Eng.pdf
4 | ADOSH-SF CoP 24.0 — Lock-out / Tag-out (Isolation), Version 4.0 | Written energy-control program; lockout preferred where lockable; tag limitations; training, verification, group LOTO and restoration requirements. | https://www.adphc.gov.ae/-/media/Project/ADPHC/ADPHC/PDF/OSHAD-SF/Codes-of-Practise/24--Lockout--Tag-out-Isolation-Eng.pdf
Mandatory Project Approval Conditions
The geotechnical designer and Temporary Works Designer approve the final Alarm values, stage-by-stage movement and rate limits, target heads, drawdown limits and contingency measures.
The dewatering designer approves pump capacity, duty/standby resilience, isolation sequence and groundwater/stability controls before a duty pump is removed from service.
The employer’s electrical safety and LOTO procedure applies in addition to this checklist; only authorised and competent electrical persons may execute or verify electrical isolation.
The Authorized Person verifies the isolation certificate and all supporting controls before authorising the controlling PTW; the Permit Holder confirms the workplace is safe to commence work.