## Slide 1
TECHNICAL TEAM BRIEFING // UAE DEEP EXCAVATION
STAGE RELEASE,
AAA MONITORING &
DEWATERING-PUMP LOTO
A field-operable framework for intermediate shoring decisions, instrumentation sign-off, permit evidence and safe electrical pump isolation.
DUBAI / ABU DHABI • TEMPORARY WORKS • CONTROLLED ISSUE
SECTION A–A
GWL
RETAINED EXCAVATION
SITE SAFETY UAE
Use with the issued shoring permit & approved TW design

## Slide 2
AUTHORITY SUBMISSION LOGIC
Do not invent a universal
interim submission.
No public Dubai Municipality or Abu Dhabi DMT source reviewed prescribes the same third-party report and instrumentation sign-off for every intermediate shoring level.
01 / PUBLISHED BASELINE
Maintain technical evidence
Keep deflection and parameter records, consultant monitoring, risk controls and approved shoring design evidence current. Always prepare the stage pack.
02 / PERMIT CONDITION
Check the issued gate
Read the e-permit, authority/zone conditions, shoring review checklist and inspection request requirements before the next excavation or support stage.
03 / CHANGE OR BREACH
Escalate before proceeding
A trigger breach, design change or unexpected ground/water response goes to the designer and consultant before any progression.
KEY FINDING
The issued permit, jurisdiction, risk assessment, inspection workflow and any third-party appointment determine the actual upload/approval gate.
Dubai Municipality / DDA • Abu Dhabi DMT municipal electronic permitting
SITE SAFETY UAE
02

## Slide 3
DUBAI MUNICIPALITY / DDA
Dubai: published
shoring controls.
The published bylaw requires continuous control evidence. The issued permit determines whether that evidence is uploaded at a particular intermediate level.
01
SHORING > 2 M
Shoring is required for excavation deeper than 2 m; open slopes and shoring works must be constantly monitored.
02
ACTUAL RECORD
Contractor and consultant maintain on site the actual deflection and parameter records using inclinometers or similar devices.
03
SPECIALIST SUPERVISION
Experienced geotechnical engineers supervise the site; dewatering must be compatible with shoring performance.
04
THIRD-PARTY REVIEW
Explicit for four or more basements, special projects, projects close to water bodies; DDA permits add peer review.
EVIDENCE CHAIN
MONITOR
↓
RECORD
↓
REVIEW
↓
RELEASE
Source: Administrative Resolution No. 37 of 2021 — Article 57.
Dubai Administrative Resolution No. 37 of 2021, Article 57 • DDA shoring permit package
SITE SAFETY UAE
03

## Slide 4
ABU DHABI DMT / MUNICIPAL ELECTRONIC PERMITTING
Abu Dhabi DMT: permit
and stage controls.
DMT's municipal permit classification identifies Excavation / Shoring / Dewatering — All as requiring a Risk Assessment. The issued permit and inspection workflow determine any interim-level upload or sign-off.
01 / BEFORE WORK
Approve the safety case
Align risk assessment, shoring and dewatering method, instrumentation plan, emergency controls and permit interfaces to the approved design. Confirm the e-permit and all authority/asset-owner conditions.
02 / AT STAGE HOLD
Verify actual condition
Complete consultant/TWC inspection, monitoring trend review, water-control status, as-built checks and any required third-party verification. A raw spreadsheet is not an accepted stage release.
03 / RELEASE DECISION
Proceed, restrict or hold
Upload only the named evidence, record the decision and restrictions, set the next reading frequency and define escalation actions.
Abu Dhabi DMT / ADM MEPS EHS permit classification • ADOSH-SF v4.0 (July 2024)
SITE SAFETY UAE
04

## Slide 5
INTERMEDIATE SHORING LEVEL / CONTROLLED RELEASE
No pack. No progression.
Before excavating below the last released level, installing the next support level or changing dewatering duty, the technical evidence must show that the current safety case remains valid.
01
COMPILE
Freeze the current approved drawing, work sequence, monitoring data and water-control record.
02
INSPECT
Consultant/TWC walkdown verifies the installed support configuration, geometry and visible condition.
03
INTERPRET
Geotechnical review confirms instrument validity, trend and AAA status against stage-specific limits.
04
RELEASE OR HOLD
Named authority records the decision, restrictions, next reading frequency and escalation actions.
AUTHORITY UPLOAD ONLY WHERE PERMIT CONDITIONS REQUIRE IT
Stage release: wall, walers, struts, anchors, geometry and water control — one accepted stage
SITE SAFETY UAE
05

## Slide 6
INTERMEDIATE SHORING LEVEL / TECHNICAL RELEASE EVIDENCE
Instrumentation sign-off:
what must be certified.
A stage report is not a raw-data dump. It must demonstrate valid readings, compatible ground response and an explicit engineering decision.
01
DESIGN REFERENCE
Approved shoring/dewatering drawing, current excavation depth, support stage and applicable AAA limits.
02
INSTRUMENT VALIDITY
ID, location, depth, calibration/function check, datum stability and reading frequency confirmed.
03
TREND INTERPRETATION
Movement, rate of change and groundwater response interpreted — not just tabulated.
04
AAA STATUS
Alert / Alarm / Action status stated per instrument with the response actually taken.
05
WATER CONTROL
Internal and external head, duty/standby pump status, discharge route and high-water response.
06
ENGINEERING DECISION
Named geotechnical/TW engineer states proceed, restrict or hold with conditions and next review.
NO-GO
An unsigned trend chart is not a release. The decision must be named, dated and conditioned.
AAA = Alert / Alarm / Action trigger levels defined in the approved monitoring plan
SITE SAFETY UAE
06

## Slide 7
AAA TRIGGER ESCALATION
Three levels. Three
different responses.
Each level has a defined owner, timeframe and permitted work state. Escalation is automatic — it does not wait for a meeting.
ALERT
Increase attention
Raise reading frequency, notify TWC and consultant, verify instrument validity and record the cause review. Work may continue under review.
ALARM
Restrict and review
Restrict adjacent loading and excavation advance, mobilise geotechnical review and apply contingency measures before further progression.
ACTION
Stop and evacuate
Stop work, clear the influence zone, implement the designed emergency measure and rebuild the safety case before any restart.
RULE
Instrument fault is treated as the worst credible condition until the reading is proven valid.
Approved monitoring plan • Dubai Article 57 continuous monitoring • DMT risk assessment
SITE SAFETY UAE
07

## Slide 8
WATER CONTROL / RESILIENCE
Dewatering resilience is
part of the release.
Groundwater control failure changes the shoring load case within hours. Prove the redundancy before any stage progression or isolation.
01
DUTY / STANDBY
Tested standby pump of equal capacity, proven to start and deliver on the same discharge route.
02
POWER RESILIENCE
Independent power or fuel, generator/ATS proven, and control supply covered by the isolation plan.
03
ALARM & RESPONSE
High-water alarm, named responder, escalation contacts and a rehearsed flooding contingency.
04
DISCHARGE ROUTE
Approved receiving asset, permitted quality and no uncontrolled recharge into the excavation influence zone.
SECTION A–A
GWL
RETAINED EXCAVATION
Drawdown and inflow control must remain within the approved design envelope.
Dewatering must be compatible with shoring performance — Dubai Article 57
SITE SAFETY UAE
08

## Slide 9
PTW ISOLATION & LOTO / ELECTRICAL DEWATERING PUMPS
Isolate the pump only
with the water secured.
Do not isolate a duty pump if loss of pumping could create uncontrolled water rise, flooding, base-heave, piping, uplift or loss of safe access.
01
PLAN & PERMIT
Raise the electrical isolation certificate under the controlling PTW: pump, feeder, panel, scope, AP, permit holder and competent electrician. Record water level, flow and duty/standby status.
02
IDENTIFY SOURCES
Trace normal feeder, generator/ATS, control/UPS supply, VFD, remote PLC/SCADA, float/pressure switch and automatic restart commands. Do not rely on a stop button or HMI.
03
ISOLATE & LOCK
Open all energy-isolating devices, isolate control and alternate supplies, apply individual locks and tags, and prove dead at the point of work.
04
RESTORE UNDER CONTROL
Remove locks in the named sequence, confirm guards and level controls, restart with the water condition observed and record the restored duty/standby state.
FIRST PROVIDE A TESTED STANDBY PUMP, INDEPENDENT POWER/FUEL, HIGH-WATER ALARM AND ACCEPTED CONTINGENCY.
ADOSH-SF CoP 21.0 Permit to Work • CoP 15.0 Electrical Safety • isolation & LOTO
SITE SAFETY UAE
09

## Slide 10
TECHNICAL TEAM / INTERMEDIATE SHORING STAGE
Stage-gate decision
before proceeding.
Can the next excavation, support installation or dewatering change proceed without invalidating the approved safety case?
Q1
Is the installed system conforming?
Wall, struts/walers/anchors, connections, preload, geometry and loads match the accepted drawings and stage sequence.
TWC / CONSULTANT RELEASE
Q2
Is monitoring valid and within stage limits?
Instrument/datum checks complete; movement, rate and groundwater trends interpreted against approved AAA triggers.
GEOTECHNICAL REVIEW
Q3
Is water control resilient?
Internal/external head acceptable; duty/standby pumps, emergency power, discharge route and high-water response proven.
DEWATERING SIGN-OFF
Q4
Are permit and authority controls current?
Risk assessment, PTW/isolations, inspection request and any permit/third-party/authority condition satisfied.
PERMIT HOLDER
ANY “NO” IS A HOLD — NOT A CONDITIONAL PROGRESSION.
Stage-gate applies per location, support element and construction stage
SITE SAFETY UAE
10

## Slide 11
CLOSEOUT / CONTROLLED TECHNICAL RELEASE
Release only when
the evidence agrees.
The permit, temporary works, monitoring interpretation and water-control condition must describe the same safe stage of work.
DUBAI / PRIMARY SHORING CONTROL
Administrative Resolution No. 37 of 2021 — Article 57: design, monitoring, deflection records, third-party triggers, water-body controls.
DUBAI DEVELOPMENT ZONES
DDA shoring permit: permit package, soil investigation, calculations, drawings, review checklist and peer review for defined special projects.
ABU DHABI MUNICIPAL PERMIT
DMT / ADM MEPS EHS classification: excavation, shoring and dewatering require a risk assessment; check the issued e-permit conditions.
STAGE HOLD
GWL
RETAINED EXCAVATION
If ground, water or support condition changes — stop and rebuild the safety case.
SITE SAFETY UAE • ADOSH-SF v4.0 (July 2024) aligned