## Slide 1
PROJECT MANAGER BRIEFING // DEEP EXCAVATION GOVERNANCE
INSIDE AN
ACTIVE EXCAVATION
Temporary-shoring release, concrete-strength verification and simultaneous-operations control.
FOUNDATIONS • RETAINING WALLS • FORMWORK • LIFTING • DEWATERING
SECTION A–A
GWL
RETAINED EXCAVATION
SITE SAFETY UAE
ADOSH-SF v4.0 (July 2024) aligned

## Slide 2
01 / CONTROL CONTINUITY
The safety case continues
after concrete begins.
A completed pour, base slab or retaining-wall lift does not retire the excavation safety case — it adds a structural-work control layer.
01
Shoring
Maintain the approved support configuration until a staged, written release.
02
Dewatering
Keep duty/standby resilience and groundwater control operational.
03
Monitoring
Continue trend review through each pour, lift and support change.
04
PTW / SIMOPS
Revalidate the excavation permit and control work interfaces every shift.
MANAGEMENT RULE
Permanent works complement — never automatically replace — temporary works. The workface remains a retained excavation.
ADOSH-SF CoP 40.0 Excavation & Trenching • CoP 21.0 Permit to Work • CoP 26.0 Scaffolding
SITE SAFETY UAE
02

## Slide 3
02 / STRENGTH VERIFICATION
No generic strength
percentage releases support.
“70%” or “75%” is not a UAE-wide de-propping rule. Required stage strength = approved design load path + load combination.
01
SET BY DESIGN
The structural engineer and temporary-works designer define the strength required for the named support-removal stage.
02
VERIFY THE POUR
Traceable laboratory cube results against the engineer's acceptance criterion; alternate evidence needs written engineering acceptance.
03
WHOLE LOAD PATH
Connections, geometry, groundwater/uplift condition and retained support must match the stage calculation.
04
ISSUE RELEASE
Only the completed evidence pack enables the formal staged instruction to change the temporary system.
LOAD TRANSFER
PERMANENT SLAB
STRUT (STAGED RELEASE)
CoP 40.0: required design strength; normal verification by laboratory cube testing.
ADOSH-SF CoP 40.0 • Dubai Administrative Resolution No. 37 of 2021, Article 57
SITE SAFETY UAE
03

## Slide 4
03 / STAGED RELEASE PROTOCOL
Seven evidence gates.
One controlled release.
All gates must be accepted for the same location, support element and construction stage before the temporary system changes.
G01
LOAD-TRANSFER DESIGN
Approved temporary-works sequence and permanent load path.
G02
CONCRETE STRENGTH
Traceable laboratory verification against the stage criterion.
G03
PERMANENT WORKS
Connections, geometry, waterstops and configuration complete.
G04
WATER CONTROL
Dewatering resilience, groundwater status, no uncontrolled inflow.
G05
MONITORING RESPONSE
Acceptable trends; no unresolved movement or inspection concern.
G06
SIMOPS READINESS
Method, lift/exclusion plan, briefing and emergency arrangements.
G07
WRITTEN RELEASE
Named stage instruction, authorised signatories, revalidated permit.
RELEASE ONLY WHEN THE SYSTEM IS READY // DESIGN · STRENGTH · WATER · MONITORING · PERMIT
Stage release protocol — all seven gates, same location and stage
SITE SAFETY UAE
04

## Slide 5
04 / EVIDENCE GATE
A defensible release pack
leaves no doubt.
A change to a strut, anchor or temporary shoring element is authorised only when each record is traceable, current and reviewed by the named technical authority.
01
STAGE CALCULATION
Approved load-transfer sequence, retained support and required stage strength.
02
CONCRETE CERTIFICATE
Laboratory cube result linked to the actual pour, mix, sample and design-stage criterion.
03
ITP / QUALITY
Complete reinforcement, connections, waterstops and structural configuration.
04
MONITORING STATEMENT
Current inclinometer, piezometer and visual inspection status; no unresolved trigger.
05
WATER & SHORING
Dewatering resilience, groundwater condition and support-system inspection accepted.
06
METHOD & RELEASE
Removal sequence, lift/exclusion plan, PTW revalidation and signed staged instruction.
NO-GO
A missing record is a hold — not an administrative delay to be waived on site.
Auditable sign-off pack — traceable to pour, element, stage and signatory
SITE SAFETY UAE
05

## Slide 6
05 / DUBAI — ARTICLE 57
Anchors move only on written
consultant consent.
Dubai requires anchor removal on site only after the consultant's written consent. No verbal release. No expired permit. No support change before monitoring and dewatering condition is accepted.
01
RECORD MOVEMENT
Maintain deflection and other measured parameters on site using inclinometers or equivalent devices.
02
MONITOR CONTINUOUSLY
Contractor and consultant follow shoring behaviour through the construction sequence.
03
CONTROL SURCHARGE
Heavy equipment, loading/unloading and material storage must not impair the shoring system.
MONITOR → DECIDE
MONITORING
↓
ENGINEERING DECISION
↓
WRITTEN CONSENT
↓
RELEASE
Source: Dubai bylaw concerning building requirements & specifications — Article 57.
Dubai Administrative Resolution No. 37 of 2021 — Article 57
SITE SAFETY UAE
06

## Slide 7
06 / CONTROLLED SUPPORT CHANGE
Strut removal is an
exclusive work zone.
A controlled support change is not compatible with normal production work. The removal sequence takes priority over schedule pressure.
01
FREEZE WORK
Stop earthmoving, lifting, formwork, rebar, concrete placing and non-essential maintenance in the influence zone.
02
ESSENTIAL CREW
Controlled removal crew, monitoring personnel, appointed supervisor and emergency standby only.
03
STOP AUTHORITY
Stop for water ingress, unexpected movement, damaged support, lost exclusion or communication failure.
ABSOLUTE
No verbal release. No concurrent production work. No exception for programme pressure.
EXCLUSION PLAN
EXCLUSIVE STRUT-REMOVAL ZONE
× EARTHMOVING
× LIFTING
× FORMWORK / POUR
● CONTROLLED CREW + MONITORING + EMERGENCY STANDBY
Temporary-works designer sequence governs the order of removal.
ADOSH-SF CoP 40.0 • CoP 21.0 Permit to Work • CoP 34.0 Cranes & Lifting
SITE SAFETY UAE
07

## Slide 8
07 / SIMOPS SEPARATION
Separate people, plant and loads.
Internal formwork and reinforcement work cannot share uncontrolled space with earthmoving, crane operations or suspended loads.
ZONE 01
People route
Protected access and escape path. No plant crossing; no storage, hoses or lift activity may block it.
ZONE 02
Plant route
One-way travel, banksman control and a defined turning/swing envelope outside occupied structural workfaces.
ZONE 03
Lift exclusion
Dedicated lift corridor. No person may work beneath a suspended load or within its fall zone.
STOP WORK
If a barrier fails, a route changes or a lift crosses an occupied workface — freeze the conflicting task and reset the SIMOPS plan.
One workface, three controlled zones: exclusion · access · movement
SITE SAFETY UAE
08

## Slide 9
08 / PLANT, GROUND & SURCHARGE
Plant position needs
engineering approval.
A crane, telehandler, concrete pump or earthmover position can introduce local bearing failure or a surcharge that changes shoring behaviour.
01
GROUND BEARING
Confirm the actual working surface — not assumed ground, backfill or weak blinding — carries the planned wheel, track or outrigger loads.
02
SURCHARGE EFFECT
Check plant, material storage and delivered concrete against the temporary-works design load envelope.
03
POSITION & SET-BACK
Use the designer-accepted location, outrigger mats/base plates and controlled approach route.
04
LIVE CONDITION
Review water, monitoring and support condition before and during the operation; reassess after relocation.
NO-GO
Do not mobilise plant into an unapproved position merely because it is operationally convenient.
EDGE INFLUENCE
GWL
RETAINED EXCAVATION
Unapproved load near the crest changes the shoring design case.
ADOSH-SF CoP 34.0 Cranes & Lifting • CoP 36.0 MEWPs • CoP 40.0 Excavation
SITE SAFETY UAE
09

## Slide 10
09 / PRINCIPAL CONTRACTOR CONTROL
Daily SIMOPS is a
management control.
The workface changes every shift. The principal contractor coordinates subcontractors, routes, permits, water control and exclusion zones — not separate method statements.
01
SHIFT START
Review permits, monitoring, groundwater, weather, pump status, lifts, deliveries, routes and active exclusion zones.
02
WORK RELEASE
Align earthworks, lifting, formwork, shoring and dewatering leads; freeze incompatible work before it begins.
03
SUPERVISION
Maintain barriers, banksmen, communication channel, lift discipline and protected escape routes throughout.
04
HANDOVER
Transfer released/retained supports, open permits, monitoring holds and outstanding actions in writing.
DAILY CYCLE
SHIFT START — plan & status
↓
RELEASE — high-risk work
↓
SUPERVISE — routes & zones
↓
HANDOVER — state & holds
Active excavation workface — coordinated shift by shift.
ADOSH-SF CoP 21.0 Permit to Work • principal contractor coordination duties
SITE SAFETY UAE
10

## Slide 11
10 / ESCALATION AUTHORITY
STOP THE WORK
A project manager does not need to prove the technical cause before stopping work. An unresolved control failure is sufficient.
T-01
Strength / load path: missing, below-criterion or non-traceable concrete verification; incomplete permanent structural configuration.
T-02
Release failure: verbal instruction, missing signatory, expired PTW or a change outside the approved staged sequence.
T-03
Monitoring / water: trigger breach, adverse trend, unexpected inflow, failed duty/standby pump or unexplained groundwater change.
T-04
Support condition: damaged strut, waler, anchor or connection; cracking, bulging or loss of the approved geometry.
T-05
SIMOPS failure: lost exclusion zone, lift over an occupied workface, blocked escape route or communication breakdown.
THE MANAGEMENT DECISION: freeze the affected workface, protect the exclusion zone and obtain engineering review.
These events invalidate the current release, permit or SIMOPS arrangement until reassessed
SITE SAFETY UAE
11

## Slide 12
CLOSING STANDARD
Release only
on evidence.
Safe de-propping is a controlled transfer of load, water pressure and construction risk — not a construction convenience.
ENGINEERING DESIGN + VERIFIED STRENGTH + LIVE MONITORING + WRITTEN RELEASE + CONTROLLED EXECUTION
LOAD TRANSFER
GWL
RETAINED EXCAVATION
Temporary support → permanent load path, under written control.
PROJECT MANAGER STANDARD: NO EVIDENCE GAP · NO UNCONTROLLED SIMOPS · NO UNSUPPORTED CHANGE