## Dashboard
LOWER-BASEMENT SIMOPS — RISK MITIGATION & CRANE PERMIT DASHBOARD
TEMPLATE STATUS: all controls are PENDING until the project team records live evidence. Update the linked sheets before every shift and high-risk lift.
PROJECT / SHIFT SNAPSHOT
Project name |  |  |  | Location / authority
Basement level / grid |  |  |  | Date / shift
SIMOPS coordinator |  |  |  | Incident controller
Crane ID / lift plan |  |  |  | Concrete pour / formwork release
Excavation PTW / expiry |  |  |  | Emergency radio channel
LIVE RISK MITIGATION STATUS
Status | Count | Meaning
GREEN |  | Control accepted; monitor
AMBER |  | Condition / limitation; manage and review
RED |  | Stop or prohibit affected work
PENDING |  | Not yet assessed / no evidence entered
N.A. |  | Not applicable to this shift
CRANE LIFT / PERMIT INTERFACE SUMMARY
Interface | Permit status | Owner | Decision requirement
Lift plan / crane certification
Formwork / falsework release
Excavation / shoring PTW
Dewatering / electrical resilience
Emergency / rescue readiness
WORKBOOK NAVIGATION
Risk Status | Live mitigation controls and residual status
Permit Interface | Lift, formwork, excavation, dewatering and emergency permits
Emergency Readiness | Evacuation, rescue route and response-resource check
Action Register | Open actions, owners and close-out
References | Source and project-specific completion requirements

## Risk Status
SIMOPS RISK-MITIGATION STATUS REGISTER
Set status to GREEN, AMBER, RED, PENDING or N.A. RED means stop/prohibit the affected work until the condition is corrected and formally revalidated.
Ref | Risk-control interface | Required mitigation | Evidence / verification | Status | Responsible owner | Comments / action
R01 | Suspended-load / active floor | Clear/barricade lift/fall zone; no work beneath load; controlled all-clear handback. | Lift supervisor zone-clear record. | PENDING
R02 | Crane position / ground / shoring | Accepted bearing, set-back and surcharge check; no unapproved relocation. | TWD/geotechnical acceptance. | PENDING
R03 | Formwork / falsework floor | Approved configuration, permit-to-load and verified capacity for planned landing/storage. | Formwork inspection and consultant release. | PENDING
R04 | Lift plan / crane readiness | Actual load, radius, route, weather, accessories and operator competency match plan. | Appointed Person check. | PENDING
R05 | Concrete pump / hose | Pump route and hose zone outside evacuation route; shutdown/pressure control prepared. | Pre-pour check. | PENDING
R06 | Dewatering resilience | Duty/standby pumps, alarms and alternate response available. | Dewatering status check. | PENDING
R07 | Excavation / support condition | No unresolved shoring, monitoring, groundwater or visual stability trigger. | TWC monitoring statement. | PENDING
R08 | Emergency access / egress | Protected evacuation route and casualty-transfer route clear, lit and marked. | Route walkdown. | PENDING
R09 | Emergency command / communications | Incident Controller, rescue lead and radio channel appointed/tested. | Shift briefing and radio test. | PENDING
R10 | Casualty staging / external response | Staging point, gate guide and emergency contacts verified. | Emergency response check. | PENDING
R11 | Worker interface / briefing | Formwork/rebar/lifting/dewatering crews understand freeze, exclusions and stop-work. | Toolbox/SIMOPS record. | PENDING
R12 | Change management | Procedure for wind, rain, water, pump fault, monitoring alert, plant move or plan change. | Revalidation trigger record. | PENDING
R13 | Electrical / temporary power | Temporary power protects escape route; LOTO does not remove last effective pump. | Electrical AP confirmation. | PENDING
R14 | Fire / smoke / ventilation | Lower-level ventilation, emergency lighting, firefighting and smoke evacuation controls ready. | HSE inspection. | PENDING
R15 | Rescue equipment | First aid, stretcher/carry method, emergency lighting and rescue resources in place. | Equipment inspection. | PENDING
R16 | SIMOPS coordinator | One person controls sequence, zones, work freeze and restart authority. | Daily coordinator appointment. | PENDING
R17 | Delivery / plant route | No delivery, pump truck, telehandler or earthmover blocks egress or lift controls. | Traffic/supervision check. | PENDING
R18 | Incident restart | Permit suspension/revalidation and technical review required after event. | Restart gate record. | PENDING
R19 | NDT / concrete evidence | Strength evidence matches approved stage criterion; NDT limitations documented. | Structural engineer assessment. | PENDING
R20 | Support change / de-propping | Written staged release; exclusive work zone; no concurrent production activity. | TWD / consultant release. | PENDING
R21 | External contractor interface | Subcontractor responsibilities, emergency contacts and handover are current. | SIMOPS coordination minutes. | PENDING

## Permit Interface
CRANE LIFT — PERMIT INTERFACE MATRIX
Each active interface must be VALID before the related work proceeds. Use HOLD or EXPIRED to block the affected work and record the correction in the Action Register.
Interface | Controlling document | Linked permit / release | Pre-work acceptance | Permit status | Lead authority | Decision / hold point | Expiry / reference
Lift operation | Approved lift plan (CoP 34.0) | Routine / critical lift authorisation | Load, radius, route, weather, crane position, accessories, zone clearance. | PENDING | Appointed Person / Lifting Supervisor | Do not lift until valid and zone clear.
Active formwork / falsework | Formwork design + CoP 40.0 | Permit-to-load / pre-pour release | Approved configuration, capacity, inspection and protected egress. | PENDING | Formwork Supervisor / Consultant | Freeze work under lift/fall zone.
Excavation / temporary shoring | Excavation PTW + TWD plan | Excavation PTW / support change release | Monitoring, water, support condition and surcharge/bearing accepted. | PENDING | TWC / Geotechnical Authority | Suspend after trigger, water event or plant relocation.
Dewatering / electrical | Dewatering plan + CoP 24.0 LOTO | Isolation certificate / LOTO + standby verification | No isolation removes last effective pump; water-control resilience confirmed. | PENDING | Electrical AP / Dewatering Supervisor | Hold if backup unavailable.
Emergency evacuation / rescue | Level-specific emergency plan | Daily rescue-route and resource release | Route, staging point, roles, communications, gate guide and equipment ready. | PENDING | Incident Controller / HSE | No SIMOPS if evacuation route obstructed.
Concrete placing | Pour plan + CoP 38.0 | Pre-pour ITP / pump setup release | Formwork capacity, pump position, hose restraint, egress and water controls. | PENDING | Concrete + Formwork Supervisors | Stop for line/hose issue, formwork distress or route conflict.
Work at height / leading edge | WAH plan + access inspection | WAH permit / rescue plan as project system requires | Edge protection, access, rescue and no lift conflict. | PENDING | WAH Supervisor | Hold if lift enters work zone.
Hot work / waterproofing | Hot-work plan | Hot-work permit + fire watch | Combustibles, atmosphere, ventilation and emergency access controlled. | PENDING | Hot-work Permit Issuer | Stop for fire/smoke or lost fire watch.

## Emergency Readiness
LOWER-BASEMENT EMERGENCY EVACUATION & RESCUE READINESS
Inspect the actual workface before issuing the SIMOPS release. Do not depend on improvised access, crane hooks, struts, walings, formwork or rebar cages for casualty movement.
Ref | Emergency requirement | Verification standard | Status | Responsible | Evidence / time | Action / close-out
E01 | Incident Controller and rescue lead appointed with deputies | Names on shift board; authority understood. | PENDING
E02 | Two independently usable evacuation routes where reasonably practicable | Routes lead to safe transfer point; outside lift/fall and hose zones. | PENDING
E03 | No use of walings/struts/formwork/rebar/crane hook as emergency access | Designed stairs/ramps/walkways only. | PENDING
E04 | Casualty route and stretcher turning points checked | No obstruction, adequate clearance and lighting. | PENDING
E05 | Crane all-stop / load contingency briefed | Lift supervisor, operator and rescue lead communication tested. | PENDING
E06 | Concrete pump shutdown / pressure-control method briefed | Hose-whip zone and pressure controls identified. | PENDING
E07 | Dewatering duty/standby and electrical status checked | No maintenance/LOTO removes last effective pumping control. | PENDING
E08 | Emergency lighting and ventilation available | Route remains usable in power/smoke event per plan. | PENDING
E09 | First aid, stretcher/carry resources and staging point ready | Inspection passed; resources not blocked by materials. | PENDING
E10 | Emergency contact, security/gate guide and ambulance approach checked | Location code and basement access communicated. | PENDING
E11 | Crew drill / briefing completed | Actual route tested; no improvisation required. | PENDING
E12 | Restart gate after incident understood | Permits, monitoring, technical review and SIMOPS reset required. | PENDING

## Action Register
SIMOPS ACTION / HOLD REGISTER
Action ID | Source sheet / ref | Issue / action required | Risk status | Owner | Due date/time | Close-out evidence | Close-out status

## References
SOURCES AND PROJECT-SPECIFIC COMPLETION REQUIREMENTS
ADPHC CoP 29.0 Excavation Work v4.1 (Feb 2026) | https://www.adphc.gov.ae/Legislation/-/media/05B0DEBB23944BE287D57CAC4636739A.ashx | Emergency rescue, first-aid planning, foreseeable emergencies and access/egress controls.
ADPHC CoP 34.0 Safe Use of Lifting Equipment v4.1 | https://www.adphc.gov.ae/-/media/Project/ADPHC/ADPHC/PDF/OSHAD-SF/Codes-of-Practise/2026/COP-340--Safe-Use-of-Lifting-Equipment-and-Lifting-Accessories-v41-English.pdf | Lift emergency planning, communications and exclusion-zone controls.
ADPHC CoP 53.0 OSH Management during Construction Work v4.0 | https://www.adphc.gov.ae/-/media/Project/ADPHC/ADPHC/PDF/OSHAD-SF/Codes-of-Practise/53---OSH-Management--Eng.pdf | Principal contractor coordination, project OSH plan and construction interface management.
ADPHC CoP 40.0 False Work (Formwork) v4.1 | https://www.adphc.gov.ae/-/media/Project/ADPHC/ADPHC/PDF/OSHAD-SF/Codes-of-Practise/2026/COP-400--False-Work-Formwork-v41-English.pdf | Formwork inspection/release interface.
Project documents to complete before use | Approved MSRA; construction OSH plan; lift plan; concrete-pour plan; excavation PTW; temporary-works design; dewatering plan; emergency contact list; authority/development-zone conditions. | Project-specific controls always override a generic template where more stringent.
USAGE NOTE
This dashboard is a management template, not a real-time monitoring system. Complete it from actual shift inspections, permits, instrument results and route walkdowns; do not treat default PENDING values as accepted controls.

## Lists (hidden)
GREEN | VALID
AMBER | EXPIRES TODAY
RED | EXPIRED
PENDING | HOLD
N.A. | N.A.