## Dashboard
MULTI-CASUALTY RESPONSE & SIMOPS ENFORCEMENT DASHBOARD
TEMPLATE — enter actual project, level and shift evidence. It does not replace emergency-service directions, authority notice, technical rescue expertise or contractual/legal review.
PROJECT AND INCIDENT / DRILL REFERENCE
Project |  |  |  | Authority / development zone
Basement level / grid |  |  |  | Date / shift
Incident / drill reference |  |  |  | Incident Controller
Primary evacuation route |  |  |  | Secondary evacuation route
Emergency rendezvous / ambulance gate |  |  |  | Audit lead
READINESS / ROUTE STATUS
Status | Count | Management interpretation
GREEN |  | Accepted; maintain and monitor
AMBER |  | Correct before SIMOPS period
RED |  | Stop / prohibit affected work
PENDING |  | No evidence entered yet
N.A. |  | Not applicable
NON-CONFORMANCE / ENFORCEMENT STATUS
NC level | Open actions | Highest immediate response | Contractual status
NC-1 |  | Correct before lift | Project procedure
NC-2 |  | Stop affected task | Project procedure
NC-3 |  | Immediate all-stop / suspend PTWs | Contract/authority review
NC-4 |  | Suspend contractor scope | Contract/authority review
NC-5 |  | Emergency plan / statutory reporting | Authority-led investigation

## Emergency Readiness
LOWER-BASEMENT MULTI-CASUALTY EMERGENCY READINESS GATE
A RED item blocks the affected SIMOPS period. A PENDING item is not accepted evidence. Verify primary and secondary access separately.
Ref | Readiness item | Required project control | Owner | Status | Evidence / location / expiry | Action ID | Verifier / time
ER01 | Incident command | Named Incident Controller, deputy and shift roles; tested communication. |  | PENDING
ER02 | Primary evacuation route | Clear, protected from lift/fall/hose/plant zones; signed and lit. |  | PENDING
ER03 | Secondary evacuation route | Independently viable from primary route / mechanical access dependence. |  | PENDING
ER04 | Protected casualty path | Workface to casualty collection to ambulance transfer point remains clear. |  | PENDING
ER05 | Casualty collection / triage | Primary and alternate Warm Zone identified outside active hazard zones. |  | PENDING
ER06 | First aid & stretcher | First-aiders, kits, stretchers and trauma equipment accessible and inspected. |  | PENDING
ER07 | Emergency services interface | Gate guide, access plan, bilingual location card and emergency contacts ready. |  | PENDING
ER08 | Lifting / energy isolation | Crane, pump, plant, temporary power and water-control emergency arrangements agreed. |  | PENDING
ER09 | Collapse rescue boundary | No-entry limit, rescue capability and emergency-service handover protocol defined. |  | PENDING

## Command & Contacts
INCIDENT COMMAND, MEDICAL AND EMERGENCY CONTACTS
Complete per shift. The Incident Controller retains command until emergency services assume it. Record alternate role holders.
Role | Primary name / employer | Alternate | Radio / mobile | Core function | First report required | Status | Notes
Incident Controller |  |  |  | All-stop, scene zones, resource command | Event type, active hazards, known/missing people | PENDING
Rescue / Medical Lead |  |  |  | Triage/casualty collection; EMS handover | Casualty count, status, rescue limitation | PENDING
Lifting Isolation Lead |  |  |  | Secure crane/lift equipment and exclusion zone | Crane/load/isolation status | PENDING
Temporary Works / Structural Lead |  |  |  | No-entry/stability technical advice | Collapse extent, secondary-collapse risk | PENDING
Electrical / Dewatering Lead |  |  |  | Power/water decisions without worsening hazard | Electrical/water/pump status | PENDING
Access & Traffic Marshal |  |  |  | Ambulance route, gate escort, route protection | Gate, route and blockage status | PENDING
Headcount Lead |  |  |  | Worker/visitor reconciliation | Missing/evacuated/last-known locations | PENDING
Communications / Records Lead |  |  |  | Event log and notifications | Calls, decisions and authority refs | PENDING

## Route Inspection
LOWER-BASEMENT EVACUATION / CASUALTY ROUTE INSPECTION
Inspect at shift start, before high-risk SIMOPS and after any route/plant/monitoring/water change. A route that crosses a lift/fall zone is not accepted.
Ref | Route criterion | Pass condition | Frequency | Status | Finding / action | Route marshal | Close-out
RT01 | Primary route availability | Clear, stable, lit, signed and independent of lift/fall/pump/plant zones. | Shift start + pre-SIMOPS | PENDING
RT02 | Secondary route availability | Viable if primary/mechanical access fails; not dependent on same access source. | Shift start + change | PENDING
RT03 | Route segregation | No load travel, suspended load, hose, delivery or storage conflicts. | Pre-lift + continuous | PENDING
RT04 | Vertical transfer | Stairs/ramps/approved transfer method suitable for planned casualty movement. | Shift start + drill | PENDING
RT05 | Physical condition | No water/slurry/debris/trailing leads/rebar projections/open edges. | Shift start + continuous | PENDING
RT06 | Emergency lighting/communications | Functional lighting and two-way comms at route/control points. | Shift start + after change | PENDING
RT07 | Ambulance interface | Gate, escort route and handover point clear and known. | Shift start + drill | PENDING
RT08 | Event re-release | Affected route reopens only after technical/Incident Controller release. | After incident/change | PENDING

## Casualty Log
MULTI-CASUALTY ACCOUNTABILITY AND HANDOVER LOG
Use only during a drill or incident. Record factual information; protect personal/medical information under the project privacy process. Clinical decisions remain with medical services.
Casualty ID | Name / employer | Last-known location | Time found | Triage tag | Condition / mechanism | First-aider | Treatment / action | Transfer route | EMS handover time | Destination / ref | Notes

## NC & Enforcement Matrix
CONTRACTOR NON-CONFORMANCE AND ENFORCEMENT MATRIX
Authority sanctions are determined by the competent authority and permit/development-zone rules. Project contractual remedies apply only where the governing contract expressly permits them.
Level | Breach example | Immediate action | Authority / statutory route | Contractual project remedy — insert approved schedule | Return-to-work release | Status | Evidence / notice | Action ID
NC-1 | Minor procedural issue caught before exposure. | Correct before lift; record. | Site/SRA inspection finding if observed. | Observation / same-shift correction; no deduction unless contract permits. | Supervisor sign-off / rebrief. | PENDING
NC-2 | Material control weakness, barrier gap or incomplete interface before active exposure. | Stop affected task; correct boundary/route. | Potential regulatory non-compliance; permit escalation if required. | Formal NCR; corrective action; reinspection/rebrief cost recovery only if contract permits. | HSE + lifting/formwork release. | PENDING
NC-3 | Active formwork crew inside lift/fall zone; unauthorised SIMOPS; evacuation route blocked during lift. | Immediate all-stop; clear; suspend permits; preserve evidence. | Notify PC and permit/authority contact as required; enforcement determined by authority. | Major NCR; competence review/removal from task; recover technical/reinspection costs only if contract permits. | Joint lifting/formwork/SIMOPS revalidation. | PENDING
NC-4 | Wilful/repeated breach, barrier bypass/removal, lifting after stop-work or falsified permit. | Suspend contractor scope; remove from workface; client notice. | Immediate authority escalation per SRA/permit route. | Escalated NCR/default notice; individual/crew suspension; contractual recovery/deduction only after contract/legal review. | Senior management acceptance + competence reset. | PENDING
NC-5 | Injury, collapse, crane incident or serious dangerous occurrence. | Emergency plan; rescue; all-stop; isolate; preserve scene. | Statutory notifications / authority investigation. | No response-impeding punitive action; apply remedies after factual/contract review. | Authority + technical release; investigation close-out. | PENDING

## Action Register
CORRECTIVE ACTION AND RELEASE REGISTER
Action ID | NC level | Issue / risk | Owner | Due date/time | Status | Close-out evidence | Independent verifier | Release decision

## Risk 5x5
5 × 5 SIMOPS RISK MATRIX
Use the project-approved risk criteria. This visual matrix is a management aid and does not replace the project MSRA or technical temporary-works/lift design.
Likelihood \ Severity | 1 | 2 | 3 | 4 | 5
1 | 1 | 2 | 3 | 4 | 5
2 | 2 | 4 | 6 | 8 | 10
3 | 3 | 6 | 9 | 12 | 15
4 | 4 | 8 | 12 | 16 | 20
5 | 5 | 10 | 15 | 20 | 25
RISK RECORD
SIMOPS activity | Hazard | Initial L | Initial S | Initial risk | Controls / permit interfaces | Residual risk

## References
SOURCES AND COMPLETION CONDITIONS
ADPHC CoP 46.0 — Underground Construction (v4.1, Feb 2026) | https://www.adphc.gov.ae/Legislation/-/media/95BE43F5B9DA4C348C898B912934A98F.ashx | Safe underground access/egress; first aid; injured-person evacuation; rescue and emergency-service communication; secondary egress where mechanical access is normal.
ADPHC CoP 53.0 — OHS Management during Construction Work (v4.0, July 2024) | https://www.adphc.gov.ae/-/media/Project/ADPHC/ADPHC/PDF/OSHAD-SF/Codes-of-Practise/53---OSH-Management--Eng.pdf | Principal contractor must plan, coordinate, supervise and enforce compliance; non-compliant entities must stop work until compliant; SRA enforcement includes penalties.
Project-specific documents | Approved emergency plan, lift plan, formwork/temporary works plan, excavation PTW, SIMOPS plan, monitoring/dewatering plan, authority contacts and contract remedy schedule. | Complete all blank items and secure approval before implementation.

## Lists (hidden)
GREEN | NOT STARTED | LOW
AMBER | IN PROGRESS | MEDIUM
RED | COMPLETE | HIGH
PENDING | HOLD | CRITICAL
N.A. | N.A.