## Dashboard
CONTRACTOR NON-CONFORMANCE SEVERITY & ENFORCEMENT DASHBOARD
Template dashboard. Authority sanctions are determined by the competent authority and the active permit/development-zone route. Contractual deductions must be expressly authorised by the governing contract.
PROJECT / REVIEW REFERENCE
Project |  |  |  |  | Authority / development zone
Contract reference |  |  |  |  | Principal Contractor
Date / period |  |  |  |  | SIMOPS workfront
Permit / lift-plan reference |  |  |  |  | Review owner
Contract penalty schedule approved? |  |  |  |  | Authority / client contact
LIVE NON-CONFORMANCE STATUS
Severity | Open count | Mandatory immediate response | Authority track | Contractual track
NC-1 |  | Correct before lift | Authority inspection finding if observed | Observation / same-shift correction
NC-2 |  | Stop affected task; correct boundary/route | Potential regulatory non-compliance / permit escalation if required | Formal NCR; corrective action; cost recovery only if contract permits
NC-3 |  | Immediate all-stop; suspend affected permits | Notify Principal Contractor; authority / permit contact as applicable | Major NCR; competence review; cost recovery only if contract permits
NC-4 |  | Suspend contractor work scope | Immediate escalation under SRA / permit route | Escalated NCR/default notice; suspension/deduction only if contract permits
NC-5 |  | Emergency plan; preserve scene; statutory notifications | Authority investigation and sanctions determined by competent authority | Remedy only after factual, contractual and legal review
VISUAL SEVERITY / ENFORCEMENT TRACK

## NC Register
NON-CONFORMANCE REGISTER
Record actual project events. A RED/stop-work action is not closed by signature alone; record the positive technical/permit revalidation and contract/authority direction.
NC ID | Date / shift | Severity | Breach category | Workfront / level | Immediate controls taken | Authority / client notification reference | Status | Contract action reference | Close-out evidence

## Enforcement Tracks
AUTHORITY VERSUS CONTRACTUAL ENFORCEMENT TRACKS
Use this as an escalation map. Monetary values are deliberately not prefilled because neither CoP 53.0 nor the public sources reviewed state a universal AED penalty for exclusion-zone / unauthorised SIMOPS breaches.
Severity | Breach / exposure | Immediate control | Authority / regulatory track | Contractual project track | Required revalidation | Project action owner | Status
NC-1 | Minor procedural non-conformance | Correct before lift | Authority inspection finding if observed | Observation / same-shift correction |  |  | PENDING
NC-2 | Material control weakness | Stop affected task; correct boundary/route | Potential regulatory non-compliance / permit escalation if required | Formal NCR; corrective action; cost recovery only if contract permits |  |  | PENDING
NC-3 | Serious exposure / unauthorised SIMOPS | Immediate all-stop; suspend affected permits | Notify Principal Contractor; authority / permit contact as applicable | Major NCR; competence review; cost recovery only if contract permits |  |  | PENDING
NC-4 | Wilful or repeated high-potential breach | Suspend contractor work scope | Immediate escalation under SRA / permit route | Escalated NCR/default notice; suspension/deduction only if contract permits |  |  | PENDING
NC-5 | Incident / collapse / serious dangerous occurrence | Emergency plan; preserve scene; statutory notifications | Authority investigation and sanctions determined by competent authority | Remedy only after factual, contractual and legal review |  |  | PENDING

## Contract Settings
CONTRACTUAL REMEDY SETTINGS — COMPLETE BEFORE ADOPTION
Do not use a blank field as permission to levy a deduction. Complete only from the executed contract, employer instructions and legal review.
Setting | Project / contract entry | Approver | Effective date | Evidence / clause | Status | Notes
NCR classification procedure |  |  |  |  | PENDING
Work suspension authority |  |  |  |  | PENDING
Personnel removal / reauthorisation process |  |  |  |  | PENDING
Reinspection / engineering cost recovery |  |  |  |  | PENDING
Standby / delay / remedial cost recovery |  |  |  |  | PENDING
Liquidated / contractual deductions |  |  |  |  | PENDING
Client / developer escalation |  |  |  |  | PENDING
Authority notification contacts |  |  |  |  | PENDING
Appeal / dispute / close-out route |  |  |  |  | PENDING

## Action Register
CORRECTIVE ACTIONS, HOLDS AND RELEASES
Action ID | NC ID | Severity | Issue / risk | Owner | Due date/time | Status | Close-out evidence | Independent verifier

## References
REFERENCE REGISTER
ADPHC CoP 53.0 — OHS Management during Construction Work | https://www.adphc.gov.ae/-/media/Project/ADPHC/ADPHC/PDF/OSHAD-SF/Codes-of-Practise/53---OSH-Management--Eng.pdf | Principal Contractor must enforce compliance; must ensure non-compliant party stops work until compliant; Building and Construction SRA enforcement includes penalties.
Project specific documents | Approved contract and penalty schedule; SIMOPS plan; lift plan; formwork/temporary works plan; PTW procedure; client/developer authority matrix. | These control contractual remedies and actual authority notification routes; complete before using the dashboard.

## Lists (hidden)
NC-1 | OPEN
NC-2 | IN PROGRESS
NC-3 | CLOSED
NC-4 | HOLD
NC-5 | N.A.