## Start Here
Site Safety UAE — Mobilisation, Demobilisation & Final Clearance Control
Start here: complete the Project Dashboard first, then confirm the authority path, manage mobilisation, prepare handover, and close final utility/environmental controls. Hyperlinks below open each working sheet.
Order | Worksheet | What to use it for | How to use it | Go to sheet
1 | Project Dashboard | Enter site-specific details once. | The project, client, plot, emirate and jurisdiction populate the control sheets automatically. | Open Project Dashboard
2 | Authority Matrix | Confirm the authority route for the exact plot. | Record the mainland/free-zone/master-developer path and evidence of the client/consultant confirmation. | Open Authority Matrix
3 | Mobilisation Checklist | Release Day One only when critical readiness controls are complete. | Use Required?, Status and N.A./Removal Reason to retain a defensible site-start record. | Open Mobilisation Checklist
4 | Demob & Handover | Control completion, acceptance and safe removal. | Track authority-ready and client-ready requirements separately from physical construction completion. | Open Demob & Handover
5 | Utility & Env Clearance | Close final temporary utilities and environmental obligations. | First select Transfer, Temporary Disconnection or Demolition/Isolation. Then attach utility, waste, permit and rehabilitation evidence. | Open Utility & Environmental Clearance
6 | Authority Email Template | Edit and issue the final-clearance authority notification. | Replace every bracketed field, attach the verified evidence pack and obtain permit-holder/client approval before sending. | Open Authority Email Template
7 | Industrial & Zone Handover | Control permanent utility handover and meter-removal decisions. | Use this before final demobilisation for industrial, free-zone, landlord and master-developer controlled locations. | Open Industrial & Zone Handover
8 |  |  |  | #'Management View'!A1
Control principle: Never use one generic “utility clearance” tick. Confirm whether the completed asset receives a permanent-service transfer, temporary construction-supply removal, or demolition/redevelopment isolation.

## Project Dashboard
Site Safety UAE — Project Mobilisation, Demobilisation & Handover Control
Complete the highlighted project inputs once. These values automatically populate the checklist rows. Use the authority matrix to confirm the relevant route before relying on any requirement.
Project Name
Client / Developer
Plot / Site / Development
Emirate | Dubai
Jurisdiction / Zone Type | Mainland
Exact Free Zone / Master Developer (if applicable)
Project Type | High-rise / Mixed Use
Planned Day One
Target Handover Date
Appointed Consultant
Main Contractor
Project Manager
HSE Manager
Authority Contact / Portal Reference
Project setup rule: do not mark a permit/approval task “Not Applicable” without recording why and who confirmed it. Confirm the exact plot, zone and master developer before using an authority pathway.
Readiness Gates
Jurisdiction Confirmed
Day-One Critical Items Complete
Handover Critical Items Complete
Blocked Items

## Authority Matrix
Authority & Jurisdiction Matrix
Use this to decide which bodies are likely to control the project. Set each relevant row to Approved / Complete only after the exact plot, zone and project scope have been confirmed by the appointed consultant/client.
Emirate | Mainland Authority Path | Core Fire / Life Safety | Utility / Infrastructure Interfaces | Free Zone / Master Developer Prompt | Why It May Apply | Route Confirmed? | Evidence / Source Link | Project Owner | Target Confirmation Date | Notes / Conditions | Client / Consultant Confirmation
Dubai | Dubai Municipality | Dubai Civil Defence | DEWA; RTA/roads; telecoms; drainage/sewer as applicable | Identify DDA, Trakhees/PCFC or exact master developer before using mainland path | Building, enabling works, site setup or completion path | Not Started |  | Consultant
Abu Dhabi | DMT / relevant municipal pathway | Abu Dhabi Civil Defence Authority | Utility, road/corridor, telecoms, gas/district cooling as applicable | Confirm mainland, Al Ain, Al Dhafra, KEZAD, ADGM, Masdar or other developer control | Building, construction and completion path | Not Started |  | Consultant
Sharjah | Sharjah Municipality | Sharjah Civil Defence | SEWA; SRTA/right-of-way; telecoms; sewer/drainage as applicable | Confirm SAIF, Hamriyah, SPC or other zone/developer control | Building, utility, fire and completion path | Not Started |  | Consultant
Ajman | Ajman Municipality and Planning Department | General Department for Civil Defence | EtihadWE; telecoms; Ajman Sewerage; roads/infrastructure as applicable | Confirm Ajman Free Zone or developer procedure | Published building-permit, work-commencement and completion paths | Not Started |  | Consultant
Ras Al Khaimah | RAK Municipality / RAK Digital | Civil Defence as applicable | RAKWA; telecoms; General Resources Authority; utility interfaces | Confirm RAKEZ, Maritime City or other zone/developer control | Completion certificate has documented authority review | Not Started |  | Consultant
Fujairah | Fujairah Municipality | Civil Defence as applicable | Utilities; roads/public works; telecoms; port/coastal interfaces where applicable | Confirm Fujairah Free Zone, Port or developer controls | Building permit and completion pathway | Not Started |  | Consultant
Umm Al Quwain | Umm Al Quwain Municipality | Civil Defence as applicable | Utility, telecoms, road/infrastructure interfaces as applicable | Confirm UAQ Free Trade Zone or developer procedure | Building permit and completion pathway | Not Started |  | Consultant

## Authority Email Template
Authority Notification — Final Site Clearance & Environmental Handover
Editable working template. Replace every [bracketed field], confirm the current authority/portal route, and obtain permit-holder/client approval before issue. Communications are issued by Intermass.
Subject | Request for Final Site Clearance and Environmental Handover — [Project Name] — [Plot / Lease / Building No.] — [Authority Reference]
To | [Named authority officer / authority inbox]
Cc | [Client]; [Consultant]; [Master developer/free-zone authority]; [HSE/environment manager]; [Utility coordinator]
From | Intermass — [Project manager name / title]
Authority route selected | [Dubai Municipality / Abu Dhabi Municipality / DMT route / EAD / Trakhees / JAFZA / other zone authority]
Editable email body
Dear [Title and name / Authority Team], Intermass, on behalf of [Client / Permit Holder], respectfully notifies [Authority] that the works at [Project Name], Plot/Lease/Building [reference], located at [full location and jurisdiction], have reached the final site-clearance and handover stage. The project scope comprised [brief scope] under [building permit / environmental permit / environmental clearance / NOC / lease reference]. We request your review and confirmation of the remaining authority requirements for final clearance and environmental handover, including whether an inspection, portal submission, additional NOC, permit-condition closeout, utility evidence or site rehabilitation confirmation is required. Current closeout status: • Physical works and site housekeeping: [status] • Environmental permit / clearance conditions: [status / not applicable] • Waste and hazardous-material records: [status / not applicable] • Temporary utility removal: [status / not applicable] • Permanent service end state: [Transferred to client / remains in client account / removal requested] • Site rehabilitation / equipment removal: [status / not applicable] Attached for your review are [list attachments]. We kindly request confirmation of the appropriate final-clearance route and, where applicable, an inspection appointment or written confirmation of the remaining actions. Please advise if a specific portal submission, form, fee, original document or additional clearance is required. The project team contact for this request is [name, mobile, email]. We would appreciate acknowledgement of receipt and direction on the next step by [date]. Yours faithfully, For Intermass [Name] [Title] [Mobile] ¦ [Email] [Project address]
Authority-specific insert: Dubai — request the applicable municipal/environmental clearance route; Abu Dhabi — confirm municipal/DMT, utility-assets and EAD permit-condition route; Free zone — confirm NOC, asset/lease, utility and HSE/environmental clearance route. Keep facility handover separate from lease/licence/company termination.

## Mobilisation Checklist
Mobilisation Checklist
Complete the Project Dashboard first. This checklist is intentionally broader than a single authority pathway: use Required?, Status and Removal / N.A. Reason to keep only the items that apply to the verified project jurisdiction and contract.
ID | Project | Emirate | Site / Development | Stage | Checklist Item | Gate / Trigger | Authority / Client Interface | Suggested Evidence | Responsible Role | Target Date | Priority | Required? | Status | Removal / N.A. Reason | Authority / Client Ref. | Evidence Link / File ID | Expiry Date | Notes / Escalation
M-01 |  |  |  | Jurisdiction & Project Setup | Confirm plot, emirate, mainland/free-zone/master-developer jurisdiction | Before programme baseline | Client; Consultant | Written jurisdiction decision / plot or lease reference | Consultant |  | Critical | Yes | Not Started
M-02 |  |  |  | Appointments & Registration | Confirm consultant, contractor and key subcontractor appointment/registration requirements | Before permit package | Client; Consultant; Authority/Developer | Appointments; licences; registrations | Consultant |  | Critical | Yes | Not Started
M-03 |  |  |  | Document Control | Create authority register and document-submission schedule | Before first submission | Authority / Client | Authority register; submission programme | Document Controller |  | High | Yes | Not Started
M-04 |  |  |  | Permit Gate | Validate building permit / enabling-work permit status and conditions | Before physical works | Municipality / Free Zone / Master Developer | Permit; approved drawings; conditions | Consultant |  | Critical | Yes | Not Started
M-05 |  |  |  | Site Possession | Confirm site possession, access rights and developer/site rules | Before deliveries or workforce arrival | Client / Developer | Possession/access letter; logistics rules | Project Manager |  | Critical | Yes | Not Started
M-06 |  |  |  | Temporary Site Setup | Confirm mobilisation, hoarding, signboard, temporary works and excavation approvals where required | Before setup or ground disturbance | Municipality / Free Zone / Developer | Permit/NOC; site layout; method statement | Construction Manager |  | Critical | To be confirmed | Not Started
M-07 |  |  |  | Interfaces | Confirm authority, fire, utility, road, telecoms and drainage/sewer NOC requirements | Before related works | Relevant authority / utility | NOC tracker; drawings; correspondence | Utility Coordinator |  | Critical | To be confirmed | Not Started
M-08 |  |  |  | Drawing Control | Issue controlled approved construction drawings and document register | Before execution | Consultant / Client | Approved drawing register | Document Controller |  | Critical | Yes | Not Started
M-09 |  |  |  | HSE Planning | Approve HSE plan, emergency plan, risk register and site rules | Before workforce arrival | Client / Consultant | Approved plans; risk register | HSE Manager |  | Critical | Yes | Not Started
M-10 |  |  |  | Site Layout | Approve site layout: access, segregation, welfare, storage, lifting and emergency access | Before site setup | Client / Developer / Consultant | Approved layout drawing | Construction Manager |  | Critical | Yes | Not Started
M-11 |  |  |  | Public Protection | Install compliant hoarding, signage, lighting and security controls | Before opening workface | Authority / Client / Developer | Inspection/photo record; permit if required | Construction Manager |  | Critical | Yes | Not Started
M-12 |  |  |  | Welfare | Establish welfare, drinking water, sanitation, rest and first-aid arrangements | Before induction | Client / HSE | Welfare inspection; photos; service records | HSE Manager |  | Critical | Yes | Not Started
M-13 |  |  |  | Temporary Utilities | Verify temporary power, water, distribution boards, earthing and inspections | Before energisation/use | Utility / MEP / Developer | NOC; test records; inspection | MEP / Commissioning Manager |  | Critical | To be confirmed | Not Started
M-14 |  |  |  | Emergency Readiness | Establish fire points, emergency routes, muster area and emergency contacts | Before operational opening | HSE / Civil Defence interface | Emergency plan; drill/inspection record | HSE Manager |  | Critical | Yes | Not Started
M-15 |  |  |  | Plant & Lifting | Mobilise only approved plant, lifting equipment and competent operators | Before use | Client / HSE / Third Party | Plant register; certificates; operator records | Construction Manager |  | High | Yes | Not Started
M-16 |  |  |  | High-risk Work | Approve RAMS, lifting plans, traffic plans and permit-to-work workflow | Before high-risk activity | Client / Consultant / HSE | RAMS; permits; lifting plans | HSE Manager |  | Critical | Yes | Not Started
M-17 |  |  |  | People & Training | Complete workforce/subcontractor onboarding, induction and competency checks | Before access | HSE / HR | Induction and competency records | HSE Manager |  | Critical | Yes | Not Started
M-18 |  |  |  | Environment | Establish waste, spill, dust, noise and material-storage controls | Before impact-generating works | Authority / Client / HSE | Environmental plan; waste route; inspections | HSE Manager |  | High | Yes | Not Started
M-19 |  |  |  | Client Reporting | Agree reporting cadence, authority status and escalation route | Before Day One | Client / Consultant | Communication matrix; weekly dashboard | Project Manager |  | High | Yes | Not Started
M-20 |  |  |  | Day-One Release | Hold documented Day-One readiness review and record exceptions | Immediately before mobilisation release | Client / Consultant / Contractor | Signed readiness/go-no-go record | Project Manager |  | Critical | Yes | Not Started
Note on H10: Authority pathways vary by emirate and project jurisdiction. Do not assume a Dubai mainland route for a free-zone or master-developer project.

## Demob & Handover
Demobilisation & Client Handover Checklist
Start this tracker before physical completion. Track authority-ready and client-ready requirements separately; the physical works may finish before the project is legally or contractually ready for acceptance.
ID | Project | Emirate | Site / Development | Stage | Checklist Item | Gate / Trigger | Authority / Client Interface | Suggested Evidence | Responsible Role | Target Date | Priority | Required? | Status | Removal / N.A. Reason | Authority / Client Ref. | Evidence Link / File ID | Expiry Date | Notes / Escalation
D-01 |  |  |  | Closeout Control | Freeze closeout register and map every contract deliverable | 12–16 weeks before target handover | Client / Consultant | Closeout register; responsibility matrix | Document Controller |  | Critical | Yes | Not Started
D-02 |  |  |  | Completion Strategy | Agree authority, utility and client completion sequence | 12–16 weeks before handover | Authority / Utility / Client | Completion path workshop minutes | Project Manager |  | Critical | Yes | Not Started
D-03 |  |  |  | As-builts | Update as-built drawing schedule and red-line capture process | Throughout construction; weekly near completion | Consultant / Subcontractors | As-built tracker; red lines | Document Controller |  | Critical | Yes | Not Started
D-04 |  |  |  | Testing & Commissioning | Create testing, commissioning and witness schedule | 8–12 weeks before handover | Client / Consultant | T&C plan; witness invitations | MEP / Commissioning Manager |  | Critical | Yes | Not Started
D-05 |  |  |  | Quality Closeout | Close quality inspections, material approvals and non-conformances | Before final inspection requests | Consultant / QAQC | ITPs; NCR closure; material approvals | QA/QC Manager |  | Critical | Yes | Not Started
D-06 |  |  |  | Fire & Life Safety | Complete fire/life-safety testing and approval/clearance process | Before completion application | Civil Defence / Fire Consultant | Tests; certificates; clearance | MEP / Commissioning Manager |  | Critical | To be confirmed | Not Started
D-07 |  |  |  | Utilities & Infrastructure | Complete utility, telecoms, drainage/sewer and infrastructure clearances | Before permanent connection / completion | Utilities / Authority | Clearance/NOC; connection status | Utility Coordinator |  | Critical | To be confirmed | Not Started
D-08 |  |  |  | Authority Completion | Secure relevant municipal/free-zone completion-certificate pathway | Before occupation / operational handover | Municipality / Free Zone | Application; inspection evidence; certificate | Consultant |  | Critical | To be confirmed | Not Started
D-09 |  |  |  | Pre-handover Inspection | Execute joint pre-handover inspection | Before client handover | Client / Consultant | Signed inspection; snag register | Project Manager |  | Critical | Yes | Not Started
D-10 |  |  |  | Snag Closeout | Close snag/defect register with evidence and client sign-off | Before acceptance | Client / Consultant | Snag closure evidence | Construction Manager |  | Critical | Yes | Not Started
D-11 |  |  |  | O&M / Asset Data | Compile O&M manuals and asset register | Before document handover | Client / Consultant | O&M manuals; asset data; serials | MEP / Commissioning Manager |  | Critical | Yes | Not Started
D-12 |  |  |  | Warranties | Compile warranties, guarantees and supplier contacts | Before handover | Client / Commercial | Warranty schedule; guarantee certificates | Commercial / Procurement |  | High | Yes | Not Started
D-13 |  |  |  | Records Transfer | Transfer test certificates and statutory/third-party records | Before handover | Client / Authority | Certificate register; indexed records | QA/QC Manager |  | Critical | Yes | Not Started
D-14 |  |  |  | Client Training | Deliver client operational, emergency and maintenance training | Before handover | Client | Training plan; attendance; materials | MEP / Commissioning Manager |  | High | Yes | Not Started
D-15 |  |  |  | Asset / Access Transfer | Hand over keys, access cards, BMS credentials, drawings and data | On acceptance | Client / Developer | Signed transfer record | Project Manager |  | High | Yes | Not Started
D-16 |  |  |  | Residual Risk | Record residual risks and outstanding work | At provisional/conditional handover if applicable | Client / Consultant | Residual-risk register; action plan | HSE Manager |  | Critical | To be confirmed | Not Started
D-17 |  |  |  | Demob Plan | Approve demobilisation plan including sequence, traffic, lifting and utility isolation | Before removal begins | Client / HSE | Approved demob plan/RAMS | Construction Manager |  | Critical | Yes | Not Started
D-18 |  |  |  | Temporary Services | Isolate, disconnect and certify temporary services | Before temporary equipment removal | MEP / Utility | Isolation certificates; utility closure | MEP / Commissioning Manager |  | Critical | To be confirmed | Not Started
D-19 |  |  |  | Temporary Works Removal | Remove temporary works, welfare, plant and materials safely | During demobilisation | Client / HSE | Inspection/photo records; lift plans | Construction Manager |  | Critical | Yes | Not Started
D-20 |  |  |  | Waste Closure | Dispose of waste and hazardous materials through approved channels | During demobilisation | Environmental / Authority | Waste transfer notes; manifests | HSE Manager |  | High | Yes | Not Started
D-21 |  |  |  | Reinstatement | Reinstate roads, footpaths, landscaping and adjacent property where required | Before final release | Client / Developer / Authority | Inspection and acceptance record | Construction Manager |  | High | To be confirmed | Not Started
D-22 |  |  |  | Accounts & Access Closure | Close site permits, authority accounts, access permissions and registers | Final demobilisation | Authority / Client | Closure confirmations | Document Controller |  | High | To be confirmed | Not Started
D-23 |  |  |  | Archive | Archive final project HSE, quality and authority record | At final handover | Client / Company | Retention-ready indexed archive | Document Controller |  | High | Yes | Not Started
D-24 |  |  |  | Lessons Learned | Hold lessons-learned and final management review | Within 2–4 weeks after handover | Management / Client | Lessons-learned minutes; action register | Project Manager |  | Medium | Yes | Not Started
Note on H12: Authority completion requirements should be confirmed during the closeout workshop. See Authority Matrix and linked official sources in the accompanying report.

## Utility & Env Clearance
Final Utility & Environmental Clearance
Use this sheet before final removal works. Select the service end state first: transfer/energisation for the client, temporary supply disconnection, or demolition/redevelopment isolation. Authority requirements are conditional on the exact plot, permits, utility/provider and developer conditions.
ID | Project | Emirate | Site / Development | Clearance Stage | Checklist Item | End State / Trigger | Authority / Utility Interface | Suggested Evidence | Responsible Role | Target Date | Priority | Required? | Status | Removal / N.A. Reason | Authority / Utility Ref. | Evidence Link / File ID | Expiry Date | Notes / Escalation
UE-01 |  |  |  | End-State Decision | Select final utility end state | Every project: transfer/energisation, temporary disconnection/removal, or demolition/isolation. | Client / Developer / Consultant | Signed end-state decision / handover strategy | Project Manager |  | Critical | Yes | Not Started
UE-02 |  |  |  | Service Inventory | Create a complete utility and asset inventory | Every project. | Utility / Client / Developer | Meter and account register; service type; location; account holder | Utility Coordinator |  | Critical | Yes | Not Started
UE-03 |  |  |  | Service Classification | Classify every service as permanent or temporary | Every project. | Client / Consultant / Utility | Classification sign-off; isolation-point record | MEP / Commissioning Manager |  | Critical | Yes | Not Started
UE-04 |  |  |  | Financial Ownership | Confirm account holder, final-bill owner and deposit/refund responsibility | Every account to be closed or transferred. | Client / Utility / Commercial | Commercial responsibility confirmation | Commercial / Procurement |  | High | Yes | Not Started
UE-05 |  |  |  | Permanent Service Transfer | Plan permanent service transfer / client energisation | Client needs services to operate the completed asset. | Utility / Client / Developer | Transfer/energisation request; client acceptance | Utility Coordinator |  | Critical | To be confirmed | Not Started
UE-06 |  |  |  | Temporary Service Removal | Request temporary service disconnection or removal | Temporary construction/welfare supply ends. | Utility / Developer | Service request; isolation plan; disconnection confirmation | Utility Coordinator |  | Critical | To be confirmed | Not Started
UE-07 |  |  |  | Demolition Isolation | Confirm demolition/redevelopment utility-isolation route | Asset/area will be demolished or redeveloped. | Utility / Municipality / Developer | Demolition-specific service request, permit/NOC, isolation certificate | Consultant |  | Critical | To be confirmed | Not Started
UE-08 |  |  |  | Safe Isolation | Isolate and certify temporary electrical, water, gas and telecom systems | Before equipment or temporary distribution is removed. | MEP / HSE / Utility | LOTO/isolation certificate; final reading; removal inspection | MEP / Commissioning Manager |  | Critical | Yes | Not Started
UE-09 |  |  |  | Final Bill and Closure | Settle final bill and obtain provider closure/clearance evidence | Account/service is closing. | Utility / Commercial | Final invoice, settled bill, closure/clearance evidence | Commercial / Procurement |  | Critical | To be confirmed | Not Started
UE-10 |  |  |  | Dubai DEWA Certificate | Capture DEWA Clearance Certificate issue and expiry date | Dubai DEWA clearance certificate is relied upon. | DEWA | Clearance Certificate and settled final bill; expiry date | Document Controller |  | High | To be confirmed | Not Started
UE-11 |  |  |  | Environmental Scope | Confirm environmental permit, clearance conditions and closure applicability | Every project. | Municipality / EAD / Developer / Environmental Consultant | Permit register review and written applicability decision | HSE Manager |  | Critical | Yes | Not Started
UE-12 |  |  |  | Environmental Conditions | Close environmental permit/clearance conditions | Permit or clearance has conditions. | Responsible environmental authority / Developer | Conditions register, monitoring/inspection records, correspondence | HSE Manager |  | Critical | To be confirmed | Not Started
UE-13 |  |  |  | Waste Records | Retain waste and hazardous-material transfer/disposal records | Waste or hazardous material is generated or removed. | Approved Waste Contractor / Authority | Waste transfer notes, manifests, disposal certificates | HSE Manager |  | High | Yes | Not Started
UE-14 |  |  |  | Contamination Review | Inspect for spills, contamination or remediation need | Fuels, chemicals, generators, workshops/stores or hazardous materials used. | Environmental Consultant / Client / Authority | Inspection, corrective actions, remediation evidence where required | HSE Manager |  | High | To be confirmed | Not Started
UE-15 |  |  |  | Rehabilitation | Remove equipment and rehabilitate/reinstate the site | Closing facility, vacant plot, permit or developer condition requires it. | Municipality / Developer / Client | Removal inventory, final photographs, restoration acceptance | Construction Manager |  | Critical | To be confirmed | Not Started
UE-16 |  |  |  | Abu Dhabi EAD Cancellation | Submit EAD industrial environmental-licence cancellation | Relevant industrial facility holds the EAD environmental licence. | Environment Agency – Abu Dhabi / TAMM | TAMM application and final cancellation confirmation | HSE Manager |  | High | To be confirmed | Not Started
UE-17 |  |  |  | Sharjah Permit Cancellation | Submit cancellation of environmental permit to practise an activity | Relevant Sharjah activity permit applies after rehabilitation/removal/vacating. | Sharjah City Municipality | Rehabilitation, equipment removal, vacated-land evidence and cancellation approval | HSE Manager |  | High | To be confirmed | Not Started
UE-18 |  |  |  | Developer / Free-Zone Closeout | Close landlord, master-developer, free-zone and third-party conditions | Project is located in a controlled development/zone or has contractual conditions. | Developer / Free Zone / Client | NOC/clearance/acceptance confirmation | Project Manager |  | Critical | To be confirmed | Not Started
UE-19 |  |  |  | Dual Readiness Review | Conduct authority-ready and client-ready clearance review | Before handover and final demobilisation release. | Client / Consultant / Contractor | Two status decisions, exceptions and escalation owners | Project Director |  | Critical | Yes | Not Started
UE-20 |  |  |  | Clearance Dossier | Archive final clearance dossier | At final closeout. | Client / Company | Indexed final dossier linked to authority/client references | Document Controller |  | High | Yes | Not Started

## Industrial & Zone Handover
Industrial & Free-Zone Permanent Utility Handover / Meter Closure
Permanent-meter transfer and permanent-meter removal are different pathways. A permanent meter should normally transfer/retain for the operating client; removal is reserved for demolition, redevelopment or an approved no-longer-required service. Confirm the zone/master-developer route before any permanent-service change.
ID | Project | Emirate | Site / Development | Workstream | Checklist Item | End State / Trigger | Authority / Utility / Zone Interface | Completion Evidence | Responsible Role | Target Date | Priority | Required? | Status | Removal / N.A. Reason | Reference / Account / Meter No. | Evidence Link / File ID | Expiry Date | Notes / Escalation
PM-01 |  |  |  | Jurisdiction | Confirm municipality, utility, master developer/free zone, landlord and environmental regulator. | Every project. |  |  | Project Manager |  | Critical | Yes | Not Started
PM-02 |  |  |  | Operating Model | Confirm client occupation, FM appointment and payment responsibility for each permanent service. | Every project. |  |  | Project Director |  | Critical | Yes | Not Started
PM-03 |  |  |  | End-State Decision | Select permanent transfer/retain, temporary removal, or permanent meter removal. | Every meter/service. |  |  | Project Director |  | Critical | Yes | Not Started
PM-04 |  |  |  | Service Register | List all electricity, water, sewerage, gas, district cooling, telecom, fire-service and temporary systems. | Every project. |  |  | Utility Coordinator |  | Critical | Yes | Not Started
PM-05 |  |  |  | Service Classification | Classify each service as permanent, temporary, landlord/master-metered, district utility or embedded zone utility. | Every project. |  |  | MEP Manager |  | Critical | Yes | Not Started
PM-06 |  |  |  | Account Ownership | Record account holder, meter owner, service owner, final-bill payer and deposit/refund recipient. | Every account. |  |  | Commercial Manager |  | High | Yes | Not Started
PM-07 |  |  |  | Technical Readiness | Complete commissioning, protection settings, tests, labels, safe access and operating instructions. | Permanent service transfer/retain. |  |  | Commissioning Manager |  | Critical | To be confirmed | Not Started
PM-08 |  |  |  | Technical Handover | Issue as-builts, O&M manuals, warranties, training, spares and emergency contacts to client/FM. | Permanent service transfer/retain. |  |  | Document Controller |  | High | To be confirmed | Not Started
PM-09 |  |  |  | Joint Meter Reading | Take and sign final meter readings; photograph serial number and seals. | Every transfer/removal. |  |  | Utility Coordinator |  | High | Yes | Not Started
PM-10 |  |  |  | Client Account Transfer | Submit transfer/activation/account documents and obtain client confirmation. | Permanent service remains operational. |  |  | Utility Coordinator |  | Critical | To be confirmed | Not Started
PM-11 |  |  |  | Final Bill / Financial Closeout | Settle outgoing account and retain final bill/clearance evidence where required. | Account/service changes or closes. |  |  | Commercial Manager |  | Critical | To be confirmed | Not Started
PM-12 |  |  |  | Dubai DEWA Route | Confirm DEWA customer/premise/account route and retain required lease/tenancy, trade licence and account evidence. | Dubai project. |  |  | Utility Coordinator |  | High | To be confirmed | Not Started
PM-13 |  |  |  | Abu Dhabi Permanent Meter Removal | Use removal only with owner approval and demolition/redevelopment/no-longer-required-service basis. | Abu Dhabi permanent meter removal. |  |  | Utility Coordinator |  | Critical | To be confirmed | Not Started
PM-14 |  |  |  | Temporary Service Removal | Isolate, lock out, remove temporary cables/pipes/panels, record final reading and retain removal evidence. | Temporary systems only. |  |  | MEP Manager |  | Critical | To be confirmed | Not Started
PM-15 |  |  |  | Zone / Master Developer NOC | Obtain required NOC, lease/affection plan, approved as-builts, photographs and inspection/acceptance. | Free-zone/industrial development. |  |  | Project Manager |  | Critical | To be confirmed | Not Started
PM-16 |  |  |  | Facility vs Licence / Lease Closure | Decide whether this is only facility handover or company/lease/licence termination. | Free-zone tenant/leaseholder. |  |  | Commercial Manager |  | Critical | To be confirmed | Not Started
PM-17 |  |  |  | Industrial Environmental Closeout | Close permit conditions, waste, chemical/spill, equipment-removal and rehabilitation obligations. | Industrial/permitted activity. |  |  | HSE Manager |  | Critical | To be confirmed | Not Started
PM-18 |  |  |  | Client and Authority Readiness | Sign separate authority/utility-ready and client/FM-ready declarations; list exceptions. | Before final demob release. |  |  | Project Director |  | Critical | Yes | Not Started
PM-19 |  |  |  | Archive | Index requests, approvals, bills, readings, certificates, NOCs and handover records. | Final closeout. |  |  | Document Controller |  | High | Yes | Not Started
PM-20 |  |  |  | Demobilisation Release | Release final temporary works only after live-service protection and closeout dependencies are resolved. | Final release. |  |  | Project Director |  | Critical | Yes | Not Started

## Management View
Management View — Mobilisation, Completion & Handover Readiness
This dashboard is designed for weekly client/management review. It reports document status, blockers and dates; it does not replace programme control or formal authority confirmation.
Readiness Metric | Value | Management Meaning | Action / Decision Required
Mobilisation critical items complete |  | Day-One critical-path confidence | Escalate every incomplete critical item before release
Handover critical items complete |  | Completion and acceptance critical-path confidence | Review authority, utility, fire, test and client-acceptance gaps
All blocked items |  | Direct threats to planned milestone dates | Assign an executive owner and recovery action
Resubmissions due |  | Authority/client comment cycle exposure | Confirm comment-owner, revision date and re-submission date
Overdue target dates |  | Schedule risk that must be checked for Not Applicable/Removed status | Validate due date, status and programme effect
Expiry within 14 days |  | Permit/certificate continuity risk | Renew or confirm the next work activity before expiry
Final utility/environmental critical items complete |  | Final service, permit and rehabilitation closeout confidence | Escalate any incomplete critical temporary utility, environmental-permit or clearance item before release of final removal works
Industrial/free-zone critical handover items complete |  | Permanent-meter transfer, zone NOC, industrial environmental and final-demobilisation control | Escalate any critical item before transferring or removing a permanent service, and before releasing final temporary works.
Weekly client/management questions
Has the exact authority path been confirmed for the plot and scope?
Which permit, NOC, inspection, clearance or client decision is on the critical path to Day One or handover?
What was submitted, what comments were received and who owns the resubmission?
Which critical work fronts must not proceed until a permit, NOC, RAMS or inspection is complete?
Is the project separately authority-ready and client-ready for handover?
What will be removed at demobilisation, what will be transferred to the client, and who retains the record?

## Lists (hidden)
Emirates | Jurisdiction | Project Type | Status | Priority | YesNo | OwnerRole | Evidence
Dubai | Mainland | Villa / Residential | Not Started | Critical | Yes | Client / Developer | Permit / NOC
Abu Dhabi | Free Zone | Low-rise Residential | In Preparation | High | No | Consultant | Approved Drawing
Sharjah | Master Developer / Special Development | High-rise / Mixed Use | Submitted | Medium | To be confirmed | Project Manager | Inspection Report
Ajman | To be confirmed | Commercial / Fit-out | Comments Received | Low |  | Construction Manager | Test / Commissioning Report
Ras Al Khaimah |  | Industrial / Warehouse | Resubmission Due |  |  | HSE Manager | Certificate / Clearance
Fujairah |  | Infrastructure / Civils | Approved / Complete |  |  | QA/QC Manager | Photo Record
Umm Al Quwain |  | Other | Not Applicable |  |  | Document Controller | Training Record
|  |  | Removed - Client Approved |  |  | MEP / Commissioning Manager | Warranty / O&M
|  |  | Blocked |  |  | Utility Coordinator | Client Acceptance
[6 empty] | Commercial / Procurement | Other
Subcontractor
Other