## Contents
Crane Approval & Certification Milestone Tracker
Use this controlled tracker with the diagram. Complete yellow dashboard fields and do not pass a red hold point until evidence is accepted.
Tab | Purpose | Open
Project Dashboard | Enter the exact crane, plot, authority and responsible parties.
Milestone Tracker | Dubai/Abu Dhabi authority approval and third-party certification gates.
Authority & NOC Matrix | Authority stack, contact, condition and validity tracking.
Third-Party Cert Register | Inspection body, scope, certificate and expiry verification.
Incident Notification Matrix | Near-miss/non-compliance decision and authority-notification evidence.
References | Verified sources and project-specific evidence register.

## Project Dashboard
Project Dashboard
Complete these entries before using the milestone tracker. Authority names and notification contacts are project-specific.
Field | Project input | Control note
Project name |  | Legal project title.
Project reference |  | Permit/site reference.
Site / plot / Makani |  | Exact location.
Emirate |  | Dubai or Abu Dhabi.
Land jurisdiction / special zone |  | Mainland, port, free zone, master developer or other.
Primary construction authority |  | Municipality/free zone/port/developer.
Aviation / Civil Defence interface |  | NOC reference/contact or N/A.
Crane ID / make / model / serial |  | Exact machine configuration.
Crane owner / erection subcontractor |  | Company and 24-hour contact.
Principal contractor / appointed person |  | Name/mobile.
Independent inspection body / scope |  | Company, accreditation and authorised signatory.
Authority notification contacts |  | Current named contacts/portal and confirmation source.
Document review date |  | Update after each permit/configuration/incident change.

## Milestone Tracker
Authority Approval and Third-Party Certification Milestone Tracker
The tracker expresses public-source verified Abu Dhabi steps and Dubai confirmation points. The current authority NOC/permit conditions, manufacturer and independent inspection body set the final project requirements.
Project |  |  | Emirate
ID | Milestone / gate | Dubai authority path | Abu Dhabi authority path | Required controlled evidence | Responsible lead | Independent verifier | Hold / release criterion | Target date | Actual date | Status | Evidence reference
M-01 | Exact plot and authority stack | Confirm Dubai Municipality route and whether DCAA, Civil Defence, developer/free-zone/port requirements apply. | Confirm ADM/DMT route and whether ADPHC/ADOSH, airport, developer/port requirements apply. | Written jurisdiction/authority matrix and contact list. | Project Manager | HSE / Consultant | No mobilisation until responsible authority stack is written and acknowledged. |  |  | Open
M-02 | Engineering and configuration pack | Approved foundation, ties, configuration, load charts, erection/dismantling method, RAMS and rescue plan accepted by applicable route. | ADM permit route uses approved MEPS drawings; configuration/engineering evidence must match the permit. [1] | OEM manual, GA, foundation/tie calculations, drawings, component/serial details and survey. | Temporary Works / Structural Engineer | Appointed Person | No erection with unapproved or mismatched configuration. |  |  | Open
M-03 | Authority / NOC approvals | Confirm current Dubai Municipality and DCAA/airport/Civil Defence/developer conditions for exact plot. [2] | ADM/DMT tower-crane installation permit and approved drawings; airport light/interface requirement where applicable. [1] | Permits, NOCs, conditions register, approval validity and drawings. | Project Manager | Consultant / HSE | All required permits/NOCs current before erection. |  |  | Open
M-04 | Pre-erection readiness | Site and urban-interface controls confirmed against approved RAMS and authority conditions. | Erection company verifies permit and installation to approved drawings/specifications. [1] | Competence list, support-crane/rigging certificates, logistics/exclusion plan, weather/rescue/traffic controls. | Erection Supervisor | Appointed Person / HSE | No start until toolbox briefing and pre-erection hold point passed. |  |  | Open
M-05 | Erection and commissioning | Complete approved erection; record structural, electrical/access and safety-system commissioning. | Tower crane must remain within project boundary and pose zero collision operational/non-operational; anti-collision/zoning where applicable. [1] | Erection records, torque/pin/tie controls, electrical/earthing, brakes/limits/SLI/RCI, anemometer and anti-collision test. | Erection Subcontractor | Engineer / HSE | No operation before defects are closed and technical file is complete. |  |  | Open
M-06 | Independent inspection-body acceptance | Confirm inspection body accreditation/scope and Dubai/authority/developer acceptance. | Approved third-party annual crane inspection; verify accepted provider and scope. [1] | Accreditation/authority acceptance, scope, inspector/signatory competence and work order. | Crane Owner | Project HSE / Consultant | No test/examination by non-accepted or out-of-scope provider. |  |  | Open
M-07 | Thorough examination and tests | Tests follow OEM, inspection body and current authority/project procedure; generic load values prohibited. | ENAS framework requires functional, overload and safety tests for first/subsequent inspections; major repair requires periodic inspection and proof-load or other competent-person-specified test before service. [3] | Approved test method/RAMS, calibrated instruments, test configuration, exclusion, weather/communication controls and completed checklists. | Inspection Body | Appointed Person / HSE | No release until test/examination pass and all defects/actions are closed. |  |  | Open
M-08 | Certificate/report acceptance | Confirm certificate completeness and expiry with Dubai route/authority/client. | ADM requires annual approved third-party inspection; crane/gear intervals reflected in authority records. [1] | Unique certificate/report, crane serial/location/configuration, test type/date/result, restrictions, signatory and next due. | Crane Owner | Principal Contractor / Consultant | No operational handover with missing, incorrect, expired or conditional certificate. |  |  | Open
M-09 | Operational handover | Accept maintenance, competent operators, daily/weekly records, emergency/weather, boundary/aviation controls. | Daily/weekly competent-person checks, monthly third-party maintenance, annual inspection and ongoing anti-collision/aviation controls. [1] | Signed handover, maintenance plan, emergency procedure, weather/anti-collision controls, competence and certificates. | Principal Contractor | Appointed Person / HSE | All signatories release before operating. |  |  | Open
M-10 | Change / incident control | Reopen affected approvals/certification on major repair, configuration/tie/height change, incident or non-compliance. | Reassess/re-approve; notify/investigate per ADOSH seriousness/SRA route. [4] | Change record, revised design/RAMS, reinspection/retest, authority/client/developer notifications as required. | Project Manager | HSE / Consultant | Hold affected crane until written release. |  |  | Open

## Authority & NOC Matrix
Authority and NOC Matrix
Record every authority interface. The named person and notification route must be current, not copied from an old project.
Authority/interface | Why it applies | Required approval/condition | Reference/permit no. | Validity | Notification contact/portal | Owner | Status | Evidence link/file | Notes
Dubai Municipality | Dubai mainland construction/crane control | Current crane/erection/examination condition — confirm exact service/technical guideline. |  |  |  |  | Open
Dubai Civil Aviation Authority / airport | Height/position/lighting/airspace if applicable | Use-cranes/aviation NOC and conditions. |  |  |  |  | Open
Dubai Civil Defence | Emergency/fire/rescue interface | Project-specific construction/emergency condition. |  |  |  |  | Open
Abu Dhabi DMT/ADM | Abu Dhabi tower-crane installation | Installation permit and approved MEPS drawings. [1] |  |  |  |  | Open
ADPHC / concerned SRA | ADOSH incident/OSH control | Applicable ADOSH mechanism and SRA notification route. [4] |  |  |  |  | Open
Airport / aviation authority | Aviation interface | Lighting / height / operational conditions. |  |  |  |  | Open
Master developer / free zone / port | Plot-specific overlay | Developer/zone/port NOC, HSE rules, PTW or reporting conditions. |  |  |  |  | Open

## Third-Party Cert Register
Third-Party Certificate and Testing Register
Track inspection-body scope and each report/certificate. The correct scope, crane identification and authorised signatory are critical.
Record ID | Certificate/report | Inspection body | Accreditation/scope verified | Crane serial/configuration | Inspection/test type | Issue date | Expiry/next due | Authorised signatory | Authority/client accepted | Status | Evidence reference
TPI-01 | Inspection body accreditation/scope | [8 empty] | Open
TPI-02 | Erection commissioning / pre-test inspection | [8 empty] | Open
TPI-03 | Thorough examination report | [8 empty] | Open
TPI-04 | Load/proof/safety test record | [8 empty] | Open
TPI-05 | Lifting-accessory examination | [8 empty] | Open
TPI-06 | Anemometer calibration/function test | [8 empty] | Open
TPI-07 | Anti-collision/zoning system test | [8 empty] | Open
TPI-08 | NDT / structural assessment where directed | [8 empty] | Open
TPI-09 | Post-major-repair reinspection/retest | [8 empty] | Open

## Incident Notification Matrix
Incident Reporting and Authority Notification Matrix
This is a decision aid. Use the documented project authority contacts and procedure; emergency services and authority notification must never be delayed by internal paperwork.
Class | Trigger during handover | Immediate internal action | External notification assessment | Abu Dhabi route | Dubai / special-zone route | Evidence to retain | Release condition | Owner | Status | Record ref.
A — Emergency / serious | Structural failure, collapse/partial collapse, dropped load with injury/public risk, fatal/serious injury, uncontrolled crane, fire or other serious dangerous occurrence. | Rescue/999/998/997 as applicable; stop work; isolate; prevent access; preserve scene when safe; notify project crisis chain. | Police/Civil Defence/ambulance and authority/developer/aviation contacts as applicable; do not wait for classification paperwork. | ADOSH serious incident: Form G to concerned SRA within 24h for fatality or within max. 3 working days for serious dangerous occurrence/serious injury/serious illness; principal-contractor hierarchy applies. [4] | Immediately notify client/developer and applicable authority per permit/zone procedure. Public source review did not establish one universal DM time; confirm the exact contractual/authority route. DDA provides site accident report/investigation services and lists accident-notification circular. [5] | Photos/video only when safe/allowed, witness names, equipment/permit/certificate state, radio logs, drawings/configuration and site-access record. | Authority/police/Civil Defence direction plus competent engineer/inspection body release. | Project Director / HSE | Open
B — High-potential near miss | Near drop, collision/alarm, overload/limit activation, crane instability/significant movement, wrong component/tie/sequence, loss of anti-collision or safety device. | Stop work; land/load or make safe only per approved emergency method; quarantine crane/equipment; preserve evidence and notify principal contractor. | Assess permit/authority/developer/inspection-body/manufacturer notification immediately; escalate if serious dangerous occurrence threshold may be met. | Record all incidents; determine whether the near miss constitutes a serious dangerous occurrence requiring Form G/notification. [4] | Notify client/developer/zone manager and authority contact if permit or local procedure requires; do not restart pending written project release. | Alarm log, control settings, anemometer/weather, component serials, maintenance/inspection records, witness statements and photos. | Root-cause/corrective actions complete; reinspection/retest/authority release as required. | HSE Manager / Appointed Person | Open
C — Major non-compliance | Missing/expired permit, no accepted certificate, unapproved configuration, certificate mismatch, unauthorised person, bypassed safety device, inspection-body scope issue. | Immediate stop/hold; tag/quarantine; notify subcontractor, principal contractor, HSE and appointed person; prevent use. | Notify authority/developer/inspector/manufacturer according to permit/NOC/contract if the non-compliance affects a regulated condition or safety status. | Record/investigate; where incident or serious-risk event occurs, use ADOSH notification route. [4] | Use exact DM/free-zone/developer/port notification route; current approval may need formal suspension/reissue. | Permits, certificates, scope evidence, configuration records, photos, correspondence and corrective-action plan. | Corrective action verified; new/revised certificate/NOC/inspection only where required; written release. | Project Manager / HSE | Open
D — Minor deviation / observation | Housekeeping, documentation quality or minor procedure deviation with no immediate safety impact. | Correct promptly; log and brief relevant team; elevate if trend or condition changes risk. | Normally internal unless authority/developer condition requires notification. | Record as appropriate in internal OSH system. | Record under project/developer system. | Observation, action owner/due date and close-out proof. | Supervisor close-out and trend review. | Supervisor | Open

## References
References and Project Evidence Register
Verify the current authority revision and add project specific documents before issuing this tracker.
Ref. | Source | Verified use | URL | Project current evidence | Owner | Verified date
[1] | DMT/ADM Circular 001/2021 | Installation permit/MEPS drawings; erection/boundary/collision; inspection/maintenance; aviation lights. | https://www.dmt.gov.ae/-/media/Project/DMT/ADM/AboutUs/EHS/Circulars/Tower-crane-Circular-Jan-2021.pdf
[2] | Dubai Municipality / DCAA | Dubai construction reference and use-cranes aviation service; exact current conditions to be confirmed. | https://www.dm.gov.ae/wp-content/uploads/2022/04/code_of_safety_EN.pdf ; https://www.dcaa.gov.ae/services/building-constructions/use-cranes
[3] | MoIAT / ENAS ETR 06 | Inspection-body competence, tests, certificates and major-repair test/reinspection requirements. | https://moiat.gov.ae/-/media/site/moiat/microsite/enas/publications/technical-requirements/etr-06-for-lifting-equipment-inspection-bodies_rev0.ashx
[4] | ADPHC ADOSH-SF Mechanism 11.0 (July 2024) | Serious incident notification, investigation, preservation and principal-contractor reporting hierarchy. | https://www.adphc.gov.ae/-/media/Project/ADPHC/ADPHC/PDF/OSHAD-SF/Mechanisms/11---Incident-Notification-Eng.pdf
[5] | DDA construction services/circulars | DDA accident reporting/investigation services and current circular register. | https://dda.gov.ae/en/planning-development/construction ; https://dda.gov.ae/en/legal-database/circulars-and-announcements