CRANE SUBCONTRACTOR HANDOVER CHECKLIST

Erection, Dismantling and Third-Party Load-Testing Certification — Dubai and Abu Dhabi

| Document control | Detail |
| --- | --- |
| Status | Controlled subcontractor handover package — complete site-specific fields and secure competent/authority review before issue. |
| Version / date | 1.0 / 24 August 2026 |
| Applies to | Tower cranes and associated erection/dismantling support lifting equipment on Dubai or Abu Dhabi projects. |
| Handover stages | Pre-mobilisation; pre-erection; erection/commissioning; independent examination/load test; operational handover; pre-dismantling; dismantling close-out. |
| Primary owners | Principal contractor, crane owner/erection subcontractor, appointed person/lifting manager, temporary works coordinator, HSE manager, independent inspection body and consultant. |
| Review triggers | Authority/free-zone change; model/configuration/tie/climb change; major repair; incident; load test; permit expiry; change in subcontractor or inspection provider. |

| Critical limitation | This document is a structured handover and evidence-control checklist, not an erection, dismantling or load-testing method statement. The manufacturer’s current manual, engineered foundation/tie/climbing/dismantling design, authority conditions, approved RAMS and independent inspection-body requirements prevail. No crane may erect, climb, operate, dismantle or return to service on the strength of an incomplete checklist. |
| --- | --- |

# 1. Authority and Certification Baseline

The exact plot determines the authority stack. For mainland Abu Dhabi, Abu Dhabi City Municipality Circular No. 001/2021 requires an installation permit and adherence to approved MEPS drawings, confirms annual approved third-party inspection, six-month lifting-gear inspection, daily/weekly competent-person inspection and monthly third-party maintenance. [1] Dubai projects must confirm the current Dubai Municipality technical/examination conditions, Dubai Civil Defence requirements and the DCAA crane/aviation route where applicable. The federal ENAS ETR 06 source treats cranes as Class A1 lifting machines and describes inspection-body competence, tests, certificates and records. [2]

| Location / authority route | Handover condition before release |
| --- | --- |
| Abu Dhabi mainland | ADM/DMT crane installation permit and approved drawings; authority-accepted inspection/maintenance evidence; plot-boundary, anti-collision and aviation requirements confirmed. [1] |
| Dubai mainland | Current Dubai Municipality construction/crane-examination route confirmed; DCAA/airport condition reviewed for exact location/height; Civil Defence/developer conditions integrated. [3] [4] |
| Dubai/Abu Dhabi special zone, port or master developer | Written confirmation of whether Trakhees, DDA, port, developer or another authority adds to/replaces the municipal route. Do not rely on municipality approval alone. |
| Independent inspection body | ENAS/EIAC or authority-accepted scope for tower crane, testing/examination and certificate signature verified before appointment. [2] |

# 2. Subcontractor Handover Gate: Pre-Mobilisation and Pre-Erection

| Check | Required subcontractor handover evidence | Accept / hold |
| --- | --- | --- |
| Commercial and role control | Signed subcontract, scope matrix, crane ownership, nominated erection/dismantling supervisor, OEM/authorised technical team, appointed person/lifting manager interfaces and 24-hour escalation contacts. |  |
| Authority and permits | Exact plot authority matrix; current erection/use permit/NOC; building/temporary works approval; aviation/Civil Defence/utility/developer conditions; approved supplier/inspector evidence. |  |
| Engineering | Current manufacturer configuration; approved foundation/base design; geotechnical/ground condition; anchor/base-frame details; mast/tie/climbing design; maximum height, jib/counter-jib, ballast and load charts. |  |
| Erection/dismantling RAMS | OEM/engineered sequence, component weights, support-crane plan, rigging, exclusion zone, traffic/public interface, weather limits, fall protection, dropped-object controls, rescue plan and emergency contacts. |  |
| Personnel competence | Identity and role verification for erection crew, operator, rigger/slinger, signalman, maintenance crew, rescue personnel and supervisor; current certification/training/medical fitness where required. |  |
| Support crane and lifting gear | Valid certificate/examination, current configuration/load chart, rigging/accessory register, pre-use inspections, capacity check and designated operator/signalman. |  |
| Logistics and site readiness | Delivery route, laydown area, access, ground bearing, barricades, crane-component storage, emergency route, lighting, weather plan and public/traffic segregation. |  |

# 3. Erection Handover Checklist

| Stage | Mandatory evidence / hold point |
| --- | --- |
| Foundation release | Concrete/anchor/bolt records, survey, curing/design release, underground-service and excavation/dewatering confirmation, consultant/TWC acceptance. |
| Permit release | Erection permit/NOC and approved drawings match actual base coordinate, height, jib, ties and boundary envelope. |
| Start-of-work | Weather within approved task/OEM limit; support crane/rigging inspected; competent crew/toolbox briefing complete; rescue and emergency communication ready. |
| Assembly and torque | Component serial/condition traceability; approved mast/tie/bolt/pin sequence; torque/control records; no unapproved component/substitution/repair. |
| Electrical and access | Power/earthing/isolator, access ladders/walkways/rails/cab, lights, fire equipment and emergency-rescue access inspected. |
| Safety systems | Limit switches, emergency stop, brakes, SLI/RCI, anemometer, anti-two-block and anti-collision/zoning where required installed/tested with records. |
| Commissioning hold | No operational handover until independent inspection body examination, functional tests/load test as required, defect closure and certificate review are complete. |

# 4. Third-Party Examination and Load-Testing Certification Gate

The independent inspection body must work within its accepted/accredited scope. ETR 06 describes thorough examination including visual, dimensional, functional/operational, open-up, electrical and non-destructive testing as appropriate. It also states that first and subsequent inspections include functional, overload and safety tests; after a major repair a periodic inspection and proof-load test or other competent-person-specified inspection is required before return to normal service. [2] The actual test load, configuration and method must be set by the manufacturer, accepted inspection body, authority and approved test procedure—not copied from this checklist.

| Certification checkpoint | Required evidence |
| --- | --- |
| Inspection-body acceptance | Accreditation/approval certificate, scope covering tower crane/lifting equipment and signatory; authority/developer acceptance checked. |
| Pre-test documentation | Crane serial/model/configuration, manufacturer manual/load chart, prior certificates/defects, foundation/ties/engineering drawings, erection records, operator competence and test procedure. |
| Test equipment | Traceable calibration records for load cells, weights, gauges and instruments; correct ID and capacity. |
| Test controls | Approved risk assessment/method; exclusion zone; public/traffic control; weather limit; designated competent persons; radio/signals; emergency plan; no concurrent conflicting work. |
| Examination and test record | Actual scope/tests undertaken, observations/defects, functional/safety-device status, load/configuration, inspection date, result and restriction/derating if any. |
| Certificate acceptance | Unique report/certificate ID; issuing inspection body; client/owner; crane identification; location; dates/type of inspection; result/defects; authorised signatory; expiry/next due; authority-required fields. |
| Defect close-out | All safety-critical defects quarantined and rectified; reinspection/retest evidence and formal release recorded before operational handover. |

# 5. Operational Handover to Principal Contractor / End User

| Handover item | Receiving-party acceptance |
| --- | --- |
| Crane file | Manufacturer manuals, configuration/load charts, serial-number register, foundation/tie/erection documents, permits/NOCs, insurance and engineering drawings. |
| Certificates | Independent examination/load-test certificate, lifting-accessory records, electrical/earthing evidence, calibration records and current inspection planner. |
| Maintenance | OEM preventive-maintenance schedule, subcontractor maintenance responsibilities, daily/weekly/monthly records, defect/quarantine process and 24-hour contacts. |
| Operating controls | Operator/rigger/signalman authorisations, common-lift schedule, special/critical lift route, weather limits, anemometer/anti-collision records, boundary/aviation restrictions and communication protocol. |
| Emergency controls | Operator rescue plan, fire response, high-wind shutdown/parking method, incident contacts, emergency-access and urban/public interface controls. |
| Acceptance | Principal contractor, lifting manager, HSE manager, crane owner/subcontractor, consultant and authority/developer representative (if imposed) sign the controlled handover. |

# 6. Dismantling Handover Checklist

| Stage | Mandatory evidence / hold point |
| --- | --- |
| Engineering and authority review | Current dismantling configuration, tie-removal sequence, building-stage/temporary-works condition, approved method, authority/developer notice and aviation/boundary restrictions reviewed. |
| Pre-dismantling inspection | Competent examination of structural condition, ropes, pins/bolts, ties, access, safety systems, foundation and any damage/defect prior to planned dismantling. |
| Dismantling plan | OEM/engineered sequence; component weights/COG; support crane/rigging capacity; lifting path; laydown; exclusion; road/public/adjacent-building controls; weather limit; emergency rescue. |
| Crew and plant | OEM-authorised/competent dismantling crew; named supervisor/signalman; support-crane and gear certificates; communications and fall protection confirmed. |
| Execution controls | No early tie removal or unapproved sequence; torque/pin/component controls; controlled landing/stacking; dropped-object prevention; traffic segregation. |
| Close-out | Components identified/condition recorded; site left safe; foundation/base/temporary works removal managed; permits closed; post-work inspection and lessons/actions documented. |

# 7. Sign-Off and Escalation

| Role | Signature / date / comments |
| --- | --- |
| Crane owner / erection-dismantling subcontractor manager |  |
| Erection/dismantling supervisor |  |
| Appointed Person / Lifting Manager |  |
| Temporary Works Coordinator / Structural Engineer |  |
| Independent inspection body authorised signatory |  |
| Principal Contractor Project Manager |  |
| Principal Contractor HSE Manager |  |
| Consultant / developer / authority representative, if required |  |

# References

| Ref. | Source |
| --- | --- |
| [1] | DMT / Abu Dhabi City Municipality — Circular No. 001/2021, Safety requirement for tower cranes: https://www.dmt.gov.ae/-/media/Project/DMT/ADM/AboutUs/EHS/Circulars/Tower-crane-Circular-Jan-2021.pdf |
| [2] | MoIAT / ENAS — ETR 06, Technical Requirement for Lifting Equipment Inspection Bodies: https://moiat.gov.ae/-/media/site/moiat/microsite/enas/publications/technical-requirements/etr-06-for-lifting-equipment-inspection-bodies_rev0.ashx |
| [3] | Dubai Municipality — Code of Construction Safety Practice: https://www.dm.gov.ae/wp-content/uploads/2022/04/code_of_safety_EN.pdf |
| [4] | Dubai Civil Aviation Authority — Use Cranes service: https://www.dcaa.gov.ae/services/building-constructions/use-cranes |
| [5] | Project-specific authority, free-zone, port, developer, Civil Defence, utility, aviation, manufacturer and consultant conditions. |