## Contents
Crane Subcontractor Handover Control Workbook
Use separate tabs for the erection, load-test, operational handover and dismantling gates. Project data flows from the dashboard.
Tab | Purpose | Open
Project Dashboard | Project, authority, crane and subcontractor data
Authority Gate | Dubai/Abu Dhabi and special-zone authority/inspection acceptance check
Pre-Erection Handover | Mobilisation, engineering, people, plant and readiness
Erection & Commissioning | Erection execution, safety system and commissioning handover
Third-Party Load Test | Independent examination/test/certificate acceptance
Operational Handover | Turnover to principal contractor/end user
Pre-Dismantling Handover | Engineering, permit, RAMS and readiness
Dismantling Close-Out | Execution, component condition and site closure
Certificate Register | Certificate validity and document handover register
Defect & Release Log | Defects, quarantine and return-to-service evidence
Authority References | Evidence sources and current project requirements

## Project Dashboard
Project Dashboard
Complete yellow cells once. Use the exact plot authority and inspection-body acceptance, not only the emirate name.
Project information | Input | Control note
Project name |  | Legal project title.
Project reference |  | Job/permit reference.
Client / developer |  | Developer/master developer.
Principal contractor |  | Receiving party.
Site / plot / Makani |  | Exact location.
Emirate |  | Dubai or Abu Dhabi.
Land jurisdiction / special zone |  | Mainland, Trakhees, DDA, AD Ports, etc.
Construction authority |  | Municipality/free-zone/port/developer.
Aviation / Civil Defence reference |  | NOC/approval reference or N/A.
Crane ID / model / serial |  | Exact handover crane.
Crane owner / subcontractor |  | Company and 24-hour contact.
Erection/dismantling supervisor |  | Name/mobile.
Appointed Person / Lifting Manager |  | Name/mobile.
Independent inspection body |  | Company, accreditation/scope and signatory.
Handover date |  | Controlled issue date.

## Authority Gate
Authority, Permit and Inspection-Body Gate
No crane may be released to erection, load testing, operation or dismantling until the exact authority stack and independent inspection body are accepted.
Project |  |  | Emirate
No. | Authority / certification point | Required evidence | Status | Reference/action | Owner | Verified by | Date | Disposition
1 | Exact plot route | Written confirmation of municipality/free-zone/port/developer authority and HSE department. | No |  |  |  |  | Hold
2 | Abu Dhabi condition | Where applicable: ADM/DMT installation permit and approved MEPS drawings; plot-boundary, anti-collision and airport conditions confirmed. [1] | No |  |  |  |  | Hold
3 | Dubai condition | Where applicable: current DM crane/examination route plus DCAA/DCD/developer conditions confirmed for exact plot. | No |  |  |  |  | Hold
4 | Special-zone condition | Trakhees/DDA/port/master-developer route confirmed where plot is in its boundary; current circular/approved provider list obtained. | No |  |  |  |  | Hold
5 | Inspection body | ENAS/EIAC/authority acceptance and scope includes tower crane/examination/test; signatory acceptance verified. [2] | No |  |  |  |  | Hold
6 | Load-test procedure | Manufacturer, inspection body and authority requirements agree on test configuration/load/procedure and reporting. | No |  |  |  |  | Hold
7 | Personnel approval | Erection/dismantling/operation/rigging/signalling personnel competence is valid and accepted. | No |  |  |  |  | Hold
8 | Emergency/traffic/public | Erection/dismantling test plan includes urban interfaces, emergency access, rescue and authority/developer communications. | No |  |  |  |  | Hold
9 | Change control | Height/tie/jib/configuration, major repair, new subcontractor, authority condition or incident triggers re-review/re-approval. | No |  |  |  |  | Hold

## Pre-Erection Handover
Pre-Erection Subcontractor Handover
Complete before components are delivered/assembled or the erection support crane is mobilised.
Project |  |  | Emirate
Crane ID |  |  | Handover reference
No. | Handover category | Item / document | Required acceptance criterion | Status | Evidence reference | Submitted by | Verified by | Date | Disposition
1 | Commercial/roles | Subcontractor scope and role matrix | Signed scope, crane ownership, nominated supervisor, OEM/authorised technical support, lifting manager interface and escalation contacts. | No |  |  |  |  | Hold
2 | Authority | Permits/NOCs | Erection/use, foundation/ties, aviation, Civil Defence, utility, road/public/developer/free-zone approvals current. | No |  |  |  |  | Hold
3 | Engineering | Crane configuration | Manufacturer manual, GA/configuration, mast/ties, jib/counter-jib, ballast, max height and current load charts match proposal. | No |  |  |  |  | Hold
4 | Engineering | Foundation/base/ground | Approved foundation/base design, geotechnical data, anchor/bolt template, concrete/curing records, survey and no excavation/dewatering effect. | No |  |  |  |  | Hold
5 | RAMS | Erection/dismantling method | OEM/engineered sequence, component weights/COG, support crane plan, exclusion, weather, rescue, traffic/public and emergency controls approved. | No |  |  |  |  | Hold
6 | Personnel | Competence | Erection/dismantling crew, operator, rigger/slinger, signalman, maintenance and rescue personnel identity/competence/fitness validated. | No |  |  |  |  | Hold
7 | Support plant | Support crane/accessories | Current certification/load chart, rigging register, WLL, calibration where required, pre-use checks and named crew. | No |  |  |  |  | Hold
8 | Site readiness | Access/logistics | Delivery route, laydown, ground bearing, barriers, lighting, emergency route, weather plan and public/traffic segregation ready. | No |  |  |  |  | Hold
9 | Safety systems | System plan | Anemometer, SLI/RCI, anti-collision/zoning, lights, radios, emergency contacts and safety-device testing plan prepared. | No |  |  |  |  | Hold

## Erection & Commissioning
Erection and Commissioning Handover
Complete at erection hold points and before the independent inspection body attends.
Project |  |  | Emirate
Crane ID |  |  | Handover reference
No. | Handover category | Item / document | Required acceptance criterion | Status | Evidence reference | Submitted by | Verified by | Date | Disposition
1 | Permit release | Erection permit/drawings | Permit/NOC and approved drawings match actual base coordinate, height, jib, ties and boundary envelope. | No |  |  |  |  | Hold
2 | Foundation release | Foundation/TWC sign-off | Foundation, anchors/base frame, survey and structural release accepted; site condition unchanged. | No |  |  |  |  | Hold
3 | Start-of-work | Task briefing/weather | Crew briefed; weather within manufacturer/task limit; support crane/rigging checked; exclusion/rescue/emergency controls live. | No |  |  |  |  | Hold
4 | Assembly | Components and connections | Correct identifiable components; approved mast/tie/bolt/pin sequence; no unapproved substitution, damage or repair. | No |  |  |  |  | Hold
5 | Torque/control | Connection records | Specified torque, pins/retainers, bolts and structural checks recorded at prescribed hold points. | No |  |  |  |  | Hold
6 | Electrical/access | Electrical and safe access | Supply, earthing, isolator, access ladders/walkways/rails/cab, lights and fire equipment inspected. | No |  |  |  |  | Hold
7 | Safety devices | Functional test | Brakes, emergency stop, hoist/trolley/slew limits, SLI/RCI, anemometer, anti-two-block and anti-collision/zoning tested/recorded where fitted/required. | No |  |  |  |  | Hold
8 | Commissioning | Hold before operation | No operational use before independent examination/load test requirement, certificate review, defect closure and authorised release. | No |  |  |  |  | Hold

## Third-Party Load Test
Third-Party Examination and Load-Test Certification
Use before, during and after independent examination/load-testing. Do not insert a generic test load: follow the manufacturer, accepted inspection body, authority and approved procedure.
Project |  |  | Emirate
Crane ID |  |  | Handover reference
No. | Handover category | Item / document | Required acceptance criterion | Status | Evidence reference | Submitted by | Verified by | Date | Disposition
1 | Inspection-body acceptance | Accreditation/scope/signatory | Inspection body accepted by authority/client; scope covers tower crane and planned examination/testing; signatory verified. | No |  |  |  |  | Hold
2 | Crane identification | Serial/model/configuration | Certificate/test scope identifies exact crane, serial, configuration, height/jib, load chart and location. | No |  |  |  |  | Hold
3 | Pre-test records | Technical file | Manual, prior certificates, foundation/tie drawings, erection records, defects, maintenance history and operator competence available. | No |  |  |  |  | Hold
4 | Test procedure | Approved method/RAMS | Procedure defines scope, configuration, test load/instrumentation, exclusion, traffic/public controls, communications and stop criteria. | No |  |  |  |  | Hold
5 | Test instruments | Calibration/traceability | Load cells, weights, gauges and test equipment have valid identification/calibration/traceability. | No |  |  |  |  | Hold
6 | Test conditions | Site/weather readiness | Ground/area/exclusion secure; weather within approved limit; no conflicting lifting/public exposure; emergency plan and command live. | No |  |  |  |  | Hold
7 | Examination | Thorough scope | Visual, dimensional, functional/operational, electrical/open-up/NDT as applicable; safety devices and structural components assessed. | No |  |  |  |  | Hold
8 | Load/proof/safety tests | Actual record | Functional, overload/proof/safety tests completed only as specified by manufacturer/inspection body/authority; results recorded. | No |  |  |  |  | Hold
9 | Certificate | Mandatory data | Unique report ID, inspection body, client/owner, crane ID, location, date/type, result/defects, restrictions, signatory, next due and authority-required fields. | No |  |  |  |  | Hold
10 | Defects/release | Close-out | Safety-critical defects quarantined; corrective work/reinspection/retest evidence completed; written return-to-service issued. | No |  |  |  |  | Hold

## Operational Handover
Operational Handover to Principal Contractor
Complete only after all commissioning and independent examination/certification hold points have passed.
Project |  |  | Emirate
Crane ID |  |  | Handover reference
No. | Handover category | Item / document | Required acceptance criterion | Status | Evidence reference | Submitted by | Verified by | Date | Disposition
1 | Crane technical file | Controlled documents | Manuals, serial/configuration records, load charts, foundation/tie/erection drawings, permits/NOCs and insurance handed over. | No |  |  |  |  | Hold
2 | Certification pack | Certificates | Current independent examination/load-test certificate, accessory records, electrical/earthing and instrument calibration evidence included. | No |  |  |  |  | Hold
3 | Maintenance plan | Planned maintenance | OEM schedule, named provider, daily/weekly/monthly records, defect/quarantine and 24-hour support contacts accepted. | No |  |  |  |  | Hold
4 | People | Operating competence | Operator/rigger/signalman authorisations, site induction, common-lift and critical-lift controls transferred. | No |  |  |  |  | Hold
5 | Operational controls | Weather/communication | Manufacturer/project wind limits, anemometer, anti-collision/zoning, boundary/aviation and radio procedures verified. | No |  |  |  |  | Hold
6 | Emergency | Rescue/response | Operator rescue, fire/high-wind shutdown, incident contacts, emergency access and public/traffic controls briefed. | No |  |  |  |  | Hold
7 | Acceptance | Formal handover | Subcontractor, principal contractor, lifting manager, HSE, consultant/developer/authority sign as applicable. | No |  |  |  |  | Hold

## Pre-Dismantling Handover
Pre-Dismantling Subcontractor Handover
Complete before starting tie removal, mast removal or any dismantling lift.
Project |  |  | Emirate
Crane ID |  |  | Handover reference
No. | Handover category | Item / document | Required acceptance criterion | Status | Evidence reference | Submitted by | Verified by | Date | Disposition
1 | Authority/engineering | Dismantling authorisation | Current configuration, tie-removal sequence, building stage/temporary works, authority/developer notice and aviation/boundary conditions reviewed. | No |  |  |  |  | Hold
2 | Pre-dismantling inspection | Condition assessment | Competent inspection of structure, ropes, pins/bolts, ties, access, safety devices, foundation and defects before dismantling. | No |  |  |  |  | Hold
3 | Dismantling method | Approved sequence | OEM/engineered method details component weights/COG, tie sequence, support crane/rigging, laydown, traffic/public, weather and rescue. | No |  |  |  |  | Hold
4 | Personnel/plant | Competent resources | Authorised crew/supervisor/signalman; support crane/accessory certificates; communications and fall protection confirmed. | No |  |  |  |  | Hold
5 | Urban interface | Exclusion/logistics | Roads, pedestrians, adjacent structures, utilities, delivery routes, emergency access and public boundaries controlled. | No |  |  |  |  | Hold
6 | Emergency | Response plan | Rescue, severe weather, dropped object and structural emergency arrangements active; contacts/command clear. | No |  |  |  |  | Hold

## Dismantling Close-Out
Dismantling Close-Out and Subcontractor Release
Complete before the subcontractor demobilises and the work area is returned.
Project |  |  | Emirate
Crane ID |  |  | Handover reference
No. | Handover category | Item / document | Required acceptance criterion | Status | Evidence reference | Submitted by | Verified by | Date | Disposition
1 | Sequence adherence | Execution record | Dismantling followed approved sequence; no premature tie removal or unapproved method change. | No |  |  |  |  | Hold
2 | Component control | Identification/condition | Components are identified, safely landed/stacked, damage recorded and transport/laydown controlled. | No |  |  |  |  | Hold
3 | Site condition | Close-out inspection | Base/foundation/temporary works and surrounding area left safe; openings/excavations/anchorage addressed. | No |  |  |  |  | Hold
4 | Permit closure | Authority/developer | Permits/NOCs/aviation/developer conditions closed/updated as required. | No |  |  |  |  | Hold
5 | Records | Handover file | Dismantling record, defects, photos, incident/near miss and lessons/actions completed. | No |  |  |  |  | Hold
6 | Final acceptance | Sign-off | Subcontractor and principal contractor accept site closure; consultant/developer/authority sign if required. | No |  |  |  |  | Hold

## Certificate Register
Certificate and Document Handover Register
Record expiry, provider acceptance and handover status for every required certificate/document.
Project |  |  | Crane ID
Record ID | Document/certificate | Issuer/provider | Scope/serial/configuration | Issue date | Expiry/next due | Authority acceptance | Submitted by subcontractor | Verified by contractor | Status | File reference | Notes
CERT-001 | Crane installation/erection permit | [7 empty] | Open
CERT-002 | Foundation/tie/temporary works approval | [7 empty] | Open
CERT-003 | Erection RAMS/lift plan/rescue plan | [7 empty] | Open
CERT-004 | Support crane examination/load chart | [7 empty] | Open
CERT-005 | Rigging/accessory certificates | [7 empty] | Open
CERT-006 | Independent third-party examination/load-test certificate | [7 empty] | Open
CERT-007 | Maintenance record and schedule | [7 empty] | Open
CERT-008 | Operator/rigger/signalman competence | [7 empty] | Open
CERT-009 | Anemometer/anti-collision system test or calibration | [7 empty] | Open
CERT-010 | Aviation/Civil Defence/developer/free-zone NOC as applicable | [7 empty] | Open
CERT-011 | Dismantling method and permit | [7 empty] | Open
CERT-012 | Dismantling close-out report | [7 empty] | Open

## Defect & Release Log
Defect, Quarantine and Return-to-Service Log
Any safety-critical fault, non-conformance, missing certificate or failed test requires quarantine/hold and competent release.
Project |  |  | Crane ID
Defect ID | Date/time | Stage | Component/document | Issue | Safety classification | Immediate hold/quarantine | Corrective action | Responsible person | Release evidence | Authorised release
DEF-001 |  |  |  |  | Safety-critical
DEF-002 |  |  |  |  | Safety-critical
DEF-003 |  |  |  |  | Safety-critical
DEF-004 |  |  |  |  | Safety-critical
DEF-005 |  |  |  |  | Safety-critical
DEF-006 |  |  |  |  | Safety-critical
DEF-007 |  |  |  |  | Safety-critical
DEF-008 |  |  |  |  | Safety-critical
DEF-009 |  |  |  |  | Safety-critical
DEF-010 |  |  |  |  | Safety-critical
DEF-011 |  |  |  |  | Safety-critical
DEF-012 |  |  |  |  | Safety-critical
DEF-013 |  |  |  |  | Safety-critical
DEF-014 |  |  |  |  | Safety-critical
DEF-015 |  |  |  |  | Safety-critical
DEF-016 |  |  |  |  | Safety-critical
DEF-017 |  |  |  |  | Safety-critical
DEF-018 |  |  |  |  | Safety-critical
DEF-019 |  |  |  |  | Safety-critical
DEF-020 |  |  |  |  | Safety-critical
DEF-021 |  |  |  |  | Safety-critical
DEF-022 |  |  |  |  | Safety-critical
DEF-023 |  |  |  |  | Safety-critical
DEF-024 |  |  |  |  | Safety-critical
DEF-025 |  |  |  |  | Safety-critical
DEF-026 |  |  |  |  | Safety-critical
DEF-027 |  |  |  |  | Safety-critical
DEF-028 |  |  |  |  | Safety-critical
DEF-029 |  |  |  |  | Safety-critical
DEF-030 |  |  |  |  | Safety-critical

## Authority References
Authority References and Project Evidence
The public sources below support this form. Add current authority, free-zone, developer, manufacturer and consultant requirements before issue.
Ref. | Source | Verified use in this checklist | URL | Project evidence/current revision | Owner | Verified date
[1] | DMT/ADM Circular 001/2021 | Install permit/approved drawings, daily/weekly inspection, monthly maintenance, annual third-party inspection, anti-collision, NDT for 15+ years, aviation lights. | https://www.dmt.gov.ae/-/media/Project/DMT/ADM/AboutUs/EHS/Circulars/Tower-crane-Circular-Jan-2021.pdf
[2] | MoIAT/ENAS ETR 06 | Inspection-body competence, Class A1 crane framework, functional/overload/safety test, certificates and major-repair proof-load/reinspection considerations. | https://moiat.gov.ae/-/media/site/moiat/microsite/enas/publications/technical-requirements/etr-06-for-lifting-equipment-inspection-bodies_rev0.ashx
[3] | Dubai Municipality | Dubai construction safety reference; confirm exact current examination/permit conditions directly. | https://www.dm.gov.ae/wp-content/uploads/2022/04/code_of_safety_EN.pdf
[4] | Dubai Civil Aviation Authority | Crane aviation/height/position approval route where applicable. | https://www.dcaa.gov.ae/services/building-constructions/use-cranes
[5] | Manufacturer/consultant/special authorities | OEM manual, foundation/tie/climbing/dismantling design, Trakhees/DDA/port/developer/Civil Defence/utility conditions.