## Contents
Inspection Body Escalation and Project Exclusion Workbook
Use project-level suspension/exclusion terminology. External reporting and regulatory action remain authority decisions.
Tab | Purpose | Open
Project Dashboard | Case, provider, project, authority and decision panel data.
Triage & Containment | Classify concern and implement immediate safety/certificate controls.
Fact Review | Independently verify accreditation, scope, people, equipment, certificate and authority acceptance.
Provider Notice & CAPA | Issue controlled notice, receive response and assess corrective action.
Authority Referral Matrix | Determine current authority/EIAC/client/permit referral route.
Decision Panel | Record conditional approval, suspension or project exclusion decision.
Suspension & Exclusion Register | Controlled internal register; do not treat as a regulatory blacklist.
Reapproval Review | Verify conditions before restoration.
References | Official sources and project evidence.

## Project Dashboard
Project and Case Dashboard
Complete yellow cells. Every case must identify the exact provider, crane(s), permit/authority contacts and internal decision owners.
Field | Input | Control note
Case ID |  | Unique controlled case number.
Project/site/Makani |  | Exact location.
Emirate |  | Dubai or Abu Dhabi.
Land jurisdiction / authority |  | Municipality/free zone/port/developer.
Provider legal name / branch |  | As shown on accreditation/certificate.
Accreditation/scope reference |  | Current verification record.
Affected crane/certificate IDs |  | All potentially affected equipment/certificates.
Initial trigger/date |  | Factual trigger.
Project lead / HSE / procurement |  | Names/mobile.
Authority / permit contacts |  | Current verified contacts/portal.
Decision panel members |  | Names and conflicts declared.
Legal/contract review owner |  | Name/role.
Next review date |  | Case review/response deadline.

## Triage & Containment
Triage and Immediate Containment
Stop reliance on unsafe/suspect credentials while evidence is reviewed.
Project |  |  | Case ID
No. | Control area | Question / required evidence | Pass standard | Result | Risk | Evidence ref. | Owner | Due date | Review by | Disposition
1 | Evidence preservation | Case/evidence index | Certificates, reports, emails, portal screenshots, work orders, calibration/signatory evidence, crane configuration, photos and witness details secured. | No | High |  |  |  |  | Hold
2 | Immediate safety | Crane/certificate hold | Affected certificate reliance suspended; crane/use quarantined if safety credibility is uncertain; emergency action has priority. | No | High |  |  |  |  | Hold
3 | Classification | A–D risk class | Class based on verified factual trigger: critical integrity/safety, major capability, material process or minor observation. | No | High |  |  |  |  | Hold
4 | Affected scope | Impact identification | All cranes/sites/certificates/providers/subcontract arrangements affected are listed. | No | High |  |  |  |  | Hold
5 | Replacement | Independent cover | Accepted independent provider identified where needed for reinspection/retest. | No | High |  |  |  |  | Hold
6 | Internal notification | Project chain | HSE, project, appointed person, procurement, client/developer and legal/contract owner notified according to class. | No | High |  |  |  |  | Hold

## Fact Review
Independent Fact Review
Evidence-based review before suspension/exclusion decision or authority referral.
Project |  |  | Case ID
No. | Control area | Question / required evidence | Pass standard | Result | Risk | Evidence ref. | Owner | Due date | Review by | Disposition
1 | Accreditation | Status/scope | Official current accreditation, scope and legal entity/branch verified; suspension/expiry checked. | No | High |  |  |  |  | Hold
2 | Authority acceptance | Provider/project status | Current municipality/free-zone/port/developer/client acceptance is verified, not assumed from old list. | No | High |  |  |  |  | Hold
3 | Inspector/signatory | Person authorisation | Named person/scope/signature and competence independently verified. | No | High |  |  |  |  | Hold
4 | Instruments | Calibration/traceability | Test equipment IDs, valid calibration, capacity/range and traceability checked. | No | High |  |  |  |  | Hold
5 | Certificate | Actual crane/test | Certificate/report matches work order, serial/configuration, test method, instrument records and result. | No | High |  |  |  |  | Hold
6 | Technical review | OEM/engineering | Independent competent review of defect, test method, configuration and need for reinspection/retest. | No | High |  |  |  |  | Hold
7 | Provider response | Facts vs explanation | Provider response and supporting evidence are logged separately from verified findings. | No | High |  |  |  |  | Hold
8 | Conflict | Panel/reviewer | Reviewers declare/manage conflicts; original award/audit team not sole decision maker. | No | High |  |  |  |  | Hold

## Provider Notice & CAPA
Provider Notice, Response and Corrective Action
Give fair notice and use CAPA only where risk can be safely controlled.
Project |  |  | Case ID
No. | Control area | Question / required evidence | Pass standard | Result | Risk | Evidence ref. | Owner | Due date | Review by | Disposition
1 | Written notice | Factual allegation | Provider receives case ID, factual concerns, interim status, evidence request, response deadline and confidentiality/no-retaliation requirement. | No | High |  |  |  |  | Hold
2 | Interim status | Scope of hold | Notice clearly states whether certificate reliance, new work, specific site or all project work is suspended. | No | High |  |  |  |  | Hold
3 | Provider response | Right to respond | Response, documents, correction proposal and disputed facts are recorded. | No | High |  |  |  |  | Hold
4 | CAPA | Root cause/action | CAPA names root cause, actions, responsible owner, dates, reinspection/retest and prevention controls. | No | High |  |  |  |  | Hold
5 | Effectiveness | Independent verification | CAPA is verified by competent impartial reviewer, not accepted on provider assertion alone. | No | High |  |  |  |  | Hold
6 | Communication | Controlled wording | No public or unnecessary internal distribution; no “blacklisting” label in uncontrolled communication. | No | High |  |  |  |  | Hold

## Authority Referral Matrix
Authority and External Referral Matrix
External referral is fact-based and follows the current project authority matrix.
Project |  |  | Case ID
No. | Control area | Question / required evidence | Pass standard | Result | Risk | Evidence ref. | Owner | Due date | Review by | Disposition
1 | Immediate safety/serious event | Emergency services/Police/Civil Defence/current permit authority | Use emergency and permit route without internal-delay. | No | High |  |  |  |  | Hold
2 | EIAC accreditation concern | EIAC Inspection Bodies Accreditation Department/contact route | Use for accreditation/scope/symbol/impartiality/competence concerns; submit facts/evidence. | No | High |  |  |  |  | Hold
3 | Abu Dhabi permit/provider issue | Current DMT/ADM/project permit/HSE contact | Published approved list is historic; confirm current route/status directly. | No | High |  |  |  |  | Hold
4 | Abu Dhabi OSH incident | Concerned SRA/ADPHC route | Apply ADOSH incident mechanism only if incident/serious risk threshold is met. | No | High |  |  |  |  | Hold
5 | Dubai mainland/special-zone | Current DM/DCAA/DCD/free-zone/port/developer contact | Use exact NOC/permit/contract notification route; do not apply generic unverified timing. | No | High |  |  |  |  | Hold
6 | Client/procurement | Client legal/procurement governance | Internal exclusion/dispute route; document contract authority and decision record. | No | High |  |  |  |  | Hold

## Decision Panel
Suspension and Project Exclusion Decision Panel
Use an impartial, documented decision—never an informal verbal exclusion.
Project |  |  | Case ID
No. | Control area | Question / required evidence | Pass standard | Result | Risk | Evidence ref. | Owner | Due date | Review by | Disposition
1 | Decision authority | Panel mandate | Project/procurement/contract authority is verified; decision is internal project/vendor governance, not regulatory sanction. | No | High |  |  |  |  | Hold
2 | Evidence standard | Findings pack | Panel receives verified facts, provider response, risk analysis, technical review and authority/contract evidence. | No | High |  |  |  |  | Hold
3 | Proportionality | Decision level | Conditional approval, temporary suspension or project exclusion matches safety/integrity risk and response history. | No | High |  |  |  |  | Hold
4 | Exclusion controls | Scope/duration | Provider/site/service/duration/review date specified; no vague/open-ended or public “blacklist” label. | No | High |  |  |  |  | Hold
5 | Confidentiality | Need-to-know | Decision shared only with legitimate project/procurement/authority recipients. | No | High |  |  |  |  | Hold
6 | Appeal/review | Fair process | Provider has controlled review/appeal route; decision review date set. | No | High |  |  |  |  | Hold
7 | Authority referral | Boundary | Panel can refer concerns but cannot represent that an authority has sanctioned/blacklisted provider unless written evidence exists. | No | High |  |  |  |  | Hold

## Suspension & Exclusion Register
Suspension and Project Exclusion Register
Internal controlled register only. It must not be circulated as a public blacklist or treated as a regulatory sanction.
Case ID | Provider legal name | Service/site scope | Decision | Start date | End/review date | Reason category | Evidence summary | Panel approval | Provider notice sent | Authority referral ref. | Status
|  |  | Temporary suspension | [7 empty] | Open
|  |  | Temporary suspension | [7 empty] | Open
|  |  | Temporary suspension | [7 empty] | Open
|  |  | Temporary suspension | [7 empty] | Open
|  |  | Temporary suspension | [7 empty] | Open
|  |  | Temporary suspension | [7 empty] | Open
|  |  | Temporary suspension | [7 empty] | Open
|  |  | Temporary suspension | [7 empty] | Open
|  |  | Temporary suspension | [7 empty] | Open
|  |  | Temporary suspension | [7 empty] | Open
|  |  | Temporary suspension | [7 empty] | Open
|  |  | Temporary suspension | [7 empty] | Open
|  |  | Temporary suspension | [7 empty] | Open
|  |  | Temporary suspension | [7 empty] | Open
|  |  | Temporary suspension | [7 empty] | Open
|  |  | Temporary suspension | [7 empty] | Open
|  |  | Temporary suspension | [7 empty] | Open
|  |  | Temporary suspension | [7 empty] | Open
|  |  | Temporary suspension | [7 empty] | Open
|  |  | Temporary suspension | [7 empty] | Open
|  |  | Temporary suspension | [7 empty] | Open
|  |  | Temporary suspension | [7 empty] | Open
|  |  | Temporary suspension | [7 empty] | Open
|  |  | Temporary suspension | [7 empty] | Open
|  |  | Temporary suspension | [7 empty] | Open
|  |  | Temporary suspension | [7 empty] | Open
|  |  | Temporary suspension | [7 empty] | Open
|  |  | Temporary suspension | [7 empty] | Open
|  |  | Temporary suspension | [7 empty] | Open
|  |  | Temporary suspension | [7 empty] | Open

## Reapproval Review
Reapproval and Monitoring Review
Restore a provider only after all conditions and any authority/client requirements are verified.
Project |  |  | Case ID
No. | Control area | Question / required evidence | Pass standard | Result | Risk | Evidence ref. | Owner | Due date | Review by | Disposition
1 | Accreditation/scope | Official verification | Current scope/status/entity/branch accepted. | No | High |  |  |  |  | Hold
2 | People/equipment | Competence/calibration | Named people, signatory, instruments and methods reverified. | No | High |  |  |  |  | Hold
3 | Affected crane records | Reinspection/retest | New independent examination/test/certificates issued for affected cranes where needed. | No | High |  |  |  |  | Hold
4 | CAPA | Effectiveness | Root cause/actions verified by impartial reviewer; recurrence controls implemented. | No | High |  |  |  |  | Hold
5 | Authority/client | Acceptance | Written authority/client/free-zone/developer approval if applicable. | No | High |  |  |  |  | Hold
6 | Panel release | Controlled reapproval | Scope, monitoring, expiry/review date and sign-off recorded. | No | High |  |  |  |  | Hold

## References
References and Project Evidence
The external sources establish referral boundaries. Add current permit/NOC/contract/project evidence before using this procedure.
Ref. | Source | Use | URL | Project evidence | Owner | Verified date
[1] | EIAC | Accreditation body, inspection bodies and contact/complaints route. | https://eiac.gov.ae/about-us/ ; https://eiac.gov.ae/services/inspection-bodies/ ; https://eiac.gov.ae/contact-us/
[2] | DMT/ADM | Published approved TPI list (2021); must be reconfirmed current. | https://www.dmt.gov.ae/adm/-/media/Project/DMT/ADM/AboutUs/EHS/Circulars/approved%20Third%20Party%20Inspection%20Companies-English-Updated19April2021
[3] | MoIAT/ENAS ETR 06 | Inspection body scope, competence, testing and certificate requirements. | https://moiat.gov.ae/-/media/site/moiat/microsite/enas/publications/technical-requirements/etr-06-for-lifting-equipment-inspection-bodies_rev0.ashx
[4] | Project authorities | Current Dubai/Abu Dhabi municipality, free-zone, developer, port, aviation, Civil Defence, permit and contract requirements.